## Slide 1: Additional Considerations for 6G Timeline (RAN Perspective)
Source: RAN Chair
3GPP TSG#103 Joint Session
March 20th, 2024
RP-240790
AI 15

## Slide 2: Background: As Endorsed in TSG#102
First TSG-wide 6G workshop is expected to be in March 2025
  Right before the planned Rel-19 RAN1 functional freeze (June 2025). Detailed information for the workshop is TBD
Organization of a 3GPP Stage 1 workshop on IMT-2030 use cases is being discussed separately
  Refer to SP-231619
Studies for 6G in 3GPP are expected to start from Release 20
  Requirements studies:
    SA1 SID is expected to be approved in Sept’2024.
    RAN plenary SID (e.g., radio requirements and KPIs) is expected to be approved TBD (to be decided at RAN#103)
  Technology studies:
    SA2 SID is expected to be approved in June’2025. Other SA-WG SIDs (e.g., Security, etc.) are expected to be approved TBD
    RAN-WG SIDs are expected to be approved in June’2025
    CT-WG SIDs are expected to be approved in March’2026 (depends on SA2 SI work)
IMT-2030 submission and normative work for 6G in 3GPP are expected to start from Release 21
  Release 21 is expected to produce the 1st set of 3GPP 6G technical specifications, and will be the release for IMT-2030 submission before 2030
  Release 21 is expected to be delivered with a single drop (i.e., a single code freeze)
Target TSG#103 (March’2024) for the remaining detailed 6G timeline decisions
High-Level Considerations for 6G Timeline

## Slide 3: Proposal: Additional Details for 6G Timeline (RAN Perspective)
RAN plenary work is split into an ITU focused SI and General RAN SI
  IMT-2030 discussion is expected in RAN from 09/24 to 12/24
  RP SI Rel-20 focusing on ITU– IMT-2030: approval 12/24 until 06/25
  RP SI Rel-20 focusing on 6G General: approval 03/25 (after WS), until 06/26
Rel-20 is 18 months for 5G-Advanced, where the 6G Study is 21 months
  6G RAN 1/2/3/(4) SI Rel-20 approval 06/25 (as endorsed in RAN#102)
    RAN1 starts in 3Q/25 until 1Q/27
    RAN2/3/4 start in 4Q/25 until 2Q/27
Rel-21 timeline is to be decided no later than June 2026
  ASN.1 freeze is expected to be no earlier than March 2029