## Sheet1
Step | Action | Who does it? | Notes | Example output M.1457-13 | Example output M.2012-3 | Reference docs
1 | ITU-R sends an LS to the GCS Proponent, Transposing Organizations, and relevant External Organizations announcing the next revision of a Recommendation and providing the detailed timelines for the revision. | ITU-R WP5D |  | LS from ITU-R (Att.5.12 to Doc 5D/836): RP-141756 | LS from ITU-R (Att.5.13 to Doc 5D/82): RP-160510 | Doc IMT-2000/3Rev2 (M.1457); Doc IMT-ADV/25Rev2 (M.2012)
2 | 3GPP (via ATIS) replies to the LS in Step 1 indicating that 3GPP will contribute with the update. OPTIONAL: 3GPP may also decide at this stage which version of the specs to submit (e.g., Rel 13, September 2016 version) but it is not necessary to communicate this to ITU-R (see Step 3). In addition, 3GPP may clarify that "An update of the GCS is also foreseen." | TSG RAN Ad Hoc (through PCG)/ATIS |  | PCG34_08 (meeting "x") | PCG36_11 (meeting "y") | PCG Dec 29/07 & PCG29_23
3 | TSG RAN decides on a "snapshot" point for determining the versions of 3GPP Specs to be cited in the ITU Recommendations. This is invariably a given TSG RAN plenary meeting (e.g., #66). The "snapshot" meeting is given in the report of the RAN meeting where this was decided. Note that, in order to use a clean version of the selected “snapshot” (i.e., to allow for any “dot one” version which may have been created during the three month period between plenaries), the Specs being used are taken shortly before the following plenary meeting (in the case of previous example, #67). | TSG RAN | RAN Plenary #66 for M.1457-13; RAN#71 & RAN#73 for M.2012-3 |  |  | PCG Dec 29/07 & PCG29_23
4 | 3GPP (via ATIS) replies to the LS in Step 1, delivering further information including an indication that 3GPP will contribute with the updates as defined in Release xy and a summary of the proposed update. | TSG RAN Ad Hoc (through PCG)/ATIS |  | PCG34_36 (meeting "x+1") | PCG37_12 (meeting "y+1")
5 | The snapshot and transposition timeline (e.g., X+2A) is communicated to all the OPs in a PCG contribution, with the final decision captured in the PCG meeting record. Note that M.1457 and M.2012 alternate each year. | TSG RAN Ad Hoc Chair | New Step
6 | For each new revision of M.1457, TSG RAN produces a revised version of §5.1.1./§5.1.2 and §5.3.1/§5.3.2 listing all the 3GPP specs that form the global core spec set, which is submitted to the ITU by ATIS (including the summary and the rationale and the self-evaluation templates for the proposed update). | TSG RAN Ad Hoc (through PCG)/ATIS |  | PCG36_10
7 | For each new revision of M.2012, relevant sections are updated (specifically sections 1.1 and 1.2, including their subsections, of Annex 1), which is submitted to the ITU by ATIS (including the summary and the rationale, and the compliance templates 4.2.4 from Rec. ITU-R M.2133). | TSG RAN Ad Hoc (through PCG)/ATIS |  |  | PCG38_07
8 | The 3GPP Specification Manager feeds the list of specs into the database tool, and the tool provides an Excel file listing, for each subclause, the spec number, title, and the relevant version number of that spec (as agreed in Step 3 above) for each of the Releases of interest. | MCC
9 | The Excel file created in Step 8 is sent to PCG for approval (normally by email, since this exercise is often not aligned with physical meetings of PCG). This exercise may occasionally identify one or two errors in the list, but this is very rare. | MCC
10 | PCG approves the document in Step 9. | PCG
11 | A copy of the "snapshot" folder is also placed on the 3GPP FTP server (these folders replace the earlier CDs/DVDs that were originally requested by the ITU-R Secretariat for the GCS submission). In fact, these copies are trimmed somewhat to exclude Releases not relevant to the Recommendations in question. However, they do contain all the Specs, including those not cited in the relevant Recommendation. | MCC |  | http://www.3gpp.org/FTP/SPECS/zItuInfo/M.1457-13/ | http://www.3gpp.org/FTP/SPECS/zItuInfo/M.2012-3/
12 | MCC submits link to the GCS in Step 11 to the ITU-R Secretariat and copies ATIS. | MCC |  | http://www.3gpp.org/FTP/SPECS/zItuInfo/M.1457-13/ | http://www.3gpp.org/FTP/SPECS/zItuInfo/M.2012-3/
13 | ATIS updates the information required in Certification B, collects signatures from the GCS Proponents in Certification B, and sends it to the ITU-R Secretariat. | ATIS |  | 5D/78 (requires TIES account) | 5D/524 (requires TIES account)
14 | ITU-R WP 5D reviews the submitted material and reaches its conclusion on the acceptability of the update. The draft Revision of the Rec is then finalized and agreed (without the transposition references). | ITU-R WP5D |  | RP-161362 | 5D/TEMP/252-E (Requires a TIES account)
15 | MCC provides to the OPs and ITU-R WP5D the approved 3GPP list (Excel file) that identifies the Release and version of all the relevant specs to be transposed by relevant OPs. The format of this file was agreed by the ITU-R Secretariat in order to export the content into the ITU-R Recommendations. | MCC | The list may also includes an OP's transposed list in an effort to support other OPs' in their transposition process. |  |  | Action PCG37/07
16 | OPs should update the front matter of all the specs (e.g., to update copyright, OP name, etc.) referenced in the list that was generated in Step 15 and put the transposed specifications on a publicly available web server for access by the ITU. MCC will develop a tool (e.g., a Macro) that automates this updating process that can be customized by each OP with the appropriate language corresponding to their SDO. Each OP must provide a full description of the tailoring they perform to convert a raw 3GPP spec into its own publication. | MCC/Individual OPs | Modified Step
17 | OPs should take the Excel file in Step 15 and "personalize" it for their respective OP (e.g., include the OP-specific URL of the transposed specs, OP-specific file names, etc.). | Individual OPs
18 | OPs submit Certification C and "relevant business matters" form to the ITU-R Secretariat by the deadline indicated in Step 1 or in subsequent correspondence from ITU-R WP5D. | Individual OPs, timing coordinated by ATIS
19 | OPs transmit their SDO-specific list of material created in Step 16 (specifically the Excel file containing the details and URL to the transposed deliverables) to the ITU-R Secretariat by the deadline indicated in Step 1. | Individual OPs