## Slide 1: 3GPP TSG SA Management Report
Georg Mayer, 3GPP SA Chairman
PCG43_06
Agenda item: 4.3

## Slide 2: Executive Summary
Rel-16 work progresses as expected – still most of the work load
  Stage-2 was frozen in June 2019. SA2 finished work on Rel-16 exceptions. Stage-3 freeze is on target for March 2020.
  SA3, SA4, SA5 and SA6 are progressing according to plan
  Newly approved: 2 Study Items, 25 Work Items
Rel-17 work is picking up speed and progresses as expected
  SA1 finished R17 work by nearly 80%, expected 100% by December
  SA2 prioritization of Work Items in September and December
  More cross-TSG coordination between SA, RAN & CT
  R17 Content & Timeline will be finalized in December
  Newly approved: 18 Study Items, 20 Work Items
3 Rel-18 SA1 Studies approved
24 Technical Recommendations and 18 Technical Specifications approved
Improvements are ongoing
  Newcomer Orientation, Mentoring, Liaison Persons, Traceability

## Slide 3: Content
SA Leadership
General
Release 15 and Earlier
Release 16 (ongoing)
Release 17 (ongoing)
Release 18 (starting)
Improvements

## Slide 4: 3GPP SA Leadership

## Slide 5: TSG SA Officials (September 2019)
Georg Mayer
TSG SA Chairman
ETSI
georg.mayer@huawei.com
김래영 Laeyoung Kim
TSG SA Vicechair
TTA
laeyoung.kim@lge.com
Gregory (Greg) Schumacher
TSG SA Vicechair
ATIS
gregory.schumacher@sprint.com
中野 裕介 Yusuke Nakano
TSG SA Vicechair
ARIB
you-nakano@kddi.com
Maurice Pope
Secretary
MCC
maurice.pope@etsi.org

## Slide 6: SA1 Officials (September 2019)
José Luis Almodovar Chico
SA1 Chairman
ETSI jose.almodovarchico@tno.nl
이기동 Ki-Dong Lee
SA1 Vicechair
TTA
kidong.lee@lge.com
Gregory (Greg) Schumacher
TSG SA1 Vicechair
ETSI
gregory.schumacher@sprint.com
Alain Sultan
Secretary
MCC
alain.sultan@etsi.org
New

## Slide 7: SA2 Officials (September 2019)
Puneet Jain
SA2 Chairman
ATIS
puneet.jain@intel.com
Andy Bennett
SA2 Vicechair
ETSI
a.bennett@samsung.com
孙滔 Tao Sun
SA2 Vicechair
CCSA
suntao@chinamobile.com
Maurice Pope
Secretary
MCC
maurice.pope@etsi.org
New
New
New

## Slide 8: SA3 Officials (September 2019)
Noamen Ben Henda
SA3 Chairman
ETSI
noamen.ben.henda@ericsson.com
Alf Zugenmaier
SA3 Vicechair
ARIB
alf.zugenmaier@hm.edu
Adrian Escott
SA3 Vicechair
ATIS
aescott@qti.qualcomm.com
Mirko Cano Soveri
Secretary
MCC
mirko.cano@etsi.org
New

## Slide 9: SA4 Officials (September 2019)
Frédéric Gabin
SA4 Chairman
ETSI
frederic.gabin@ericsson.com
Nikolai Leung
SA4 Vicechair
ATIS
nleung@qti.qualcomm.com
Gilles Teniou
SA4 Vicechair
ETSI
gilles.teniou@orange.com
Paolino Usai
Secretary
MCC
paolo.usai@etsi.org

## Slide 10: SA5 Officials (September 2019)
Thomas Tovinger
SA5 Chairman
ETSI
thomas.tovinger@ericsson.com
邹兰 Zou Lan SA5 Vicechair
CCSA zoulan@huawei.com
Maryse Gardella
SA5 Vicechair
ETSI
maryse.gardella@nokia.com
Mirko Cano Soveri
Secretary
MCC
mirko.cano@etsi.org
Re-elected
New
New

## Slide 11: SA6 Officials (September 2019)
Suresh Chitturi
SA6 Chairman
TTA
s.chitturi@samsung.com
Alan Soloway
SA6 Vicechair
ATIS
asoloway@qti.qualcomm.com
Jukka Vialen
SA6 Vicechair
ETSI
jukka.vialen@airbus.com
Bernt Mattsson
Secretary
MCC
bernt.mattsson@etsi.org

## Slide 12: General

## Slide 13: TSG SA Dates
Meetings since PCG 41
  TSG SA 84 – Newport Beach, US, 5-7 June 2019
  TSG SA 85 – Newport Beach, US, 17-20 September 19 (4 day meeting)
Meetings before PCG 43
  TSG SA 86 – Sitges, Spain, 10-13 December 2019 (3.5 day meeting)
  TSG SA 87 – Jeju Island, KR, 18-20 March 2020

## Slide 14: For PCG Action
Could we have at least 2 weeks between plenaries and PCG please?

## Slide 15: Wednesday Speakers Series
Optional & voluntary event during plenaries Wednesday lunch break
Invited speaker on a topic related to the work of 3GPP
Talk should be about 45 minutes long, time for Q&A
Topics with relevance to the region/location of the meeting are invited with preference
If you have something in mind, please let us know

## Slide 16: Current Release Schedule Overview (SA/CT)
SA#84
Q2/2019
SA#85
Q3/2019
SA#86
Q4/2019
SA#87
Q1/2020
SA#88
Q2/2020
SA#89
Q3/2020
SA#90
Q4/2020
SA#91
Q1/2021
R16 stage 2
freeze
R16 stage 3
freeze
R16 code
freeze
R17 stage 1
freeze
R17 stage 2
freeze
R17 stage 3
freeze
R17
stage 1
~ 80%
SA#92
Q2/2021
RAN/SA
Rel-17
day
RAN
Rel-17
day
Rel-17 Schedule
(preliminary)
Rel-17
timeline
fix
Rel-16 Schedule
R18
stage 1
Initial input
Rel-18
(Schedule yet
unknown)
Rel-17 Planning
exceptions
start/ ongoing:
S1 normative
S2 studies
SA#93
Q3/2021
R17 code
freeze
9/19
12/19
3/20
6/20
9/20
12/20
3/21
9/21
6/21
6/19
SA#94
Q4/2021
12/21

## Slide 17: Approved TRs
Title | Specification | Version
TR 21.915 on Rel-15 Summary | 21.915 | 2.0.0
TR 22.826 v.2.0.0 on FS_CMED | 22.826 | 2.0.0
TR 22.827 v.2.0.0 on Study on Audio-Visual Service Production (FS_AVPROD) | 22.827 | 2.0.0
TR 22.829 on FS_EAV | 22.829 | 1.0.0
TR 22.831 v.1.0.0 on FS_MINT (Study on Support for Minimization of service Interruption) | 22.831 | 1.0.0
TR 22.832 v.1.1.0 on FS_eCAV (Study on enhancements for cyber-physical control applications in vertical domains) | 22.832 | 1.0.0
TR 22.834 Study on Support for Multi-USIM Devices (FS_MUSIM) | 22.834 | 1.0.0
TR 22.836 v.1.0.0 on FS_5G_ATRAC (Study on Asset Tracking Use Cases) | 22.836 | 1.0.0
TR 22.842 v.2.0.0 on Study on Network Controlled Interactive Service in 5GS (FS_NCIS) | 22.842 | 2.0.0
TR 22.854 v.2.0.0 on Feasibility Study on Multimedia Priority Service (MPS) Phase 2 | 22.854 | 2.0.0
TR 22.866 v.1.0.0 on FS_REFEC (Study on enhanced Relays for Energy eFficiency and Extensive Coverage) | 22.866 | 1.0.0
Presentation of TR 23.778 v2.0.0 for approval: Study on mission critical services access aspects | 23.778 | 2.0.0
Presentation of TR 23.784 v2.0.0 for approval: Study into discreet listening and logging for mission critical services | 23.784 | 2.0.0
Presentation of TR 23.973 version 1.0.0 'User Data Interworking, Coexistence and Migration' for approval | 23.973 | 0.2.0
Draft TR 26.801 User Equipment (UE) supporting handset mode with non-traditional earpieces (Release 16) v. 1.0.0 (FS_HaNTE) | 26.801 | 16.0.0
Draft TR 26.929 QoE parameters and metrics relevant to the Virtual Reality (VR) user experience (Release 16) v. 1.0.0 (FS_QoE_VR) | 26.929 | 16.1.0
TR 28.803 Study on management aspects of edge computing | 28.803 | 2.0.0
TR 28.804 Study on tenancy concept in 5G networks and network slicing management | 28.804 | 1.0.0
TR 28.805 Study on management aspects of communication services | 28.805 | 2.0.0
TR 28.806 Study on non-file-based trace reporting | 28.806 | 1.0.0
TR 33.807 Study on the security of the Wireless and Wireline Convergence for the 5G system architecture | 33.807 | 1.0.1
TR 33.814 Study on the security of the enhancement to the 5GC location services | 33.814 | 1.0.1
TR 33.815 Security of PARLOS | 33.815 | 1.0.1
TR 33.825 Study on the Security for 5G URLLC | 33.825 | 2.0.1

## Slide 18: Approved TS’s
Title | Specification | Version
Presentation of TS 23.273: '5G System (5GS) Location Services (LCS); Stage 2 (Release 16)', Version 1.0.0. | 23.273 | 1.0.0
Presentation of TS 23.286 v2.0.0 for approval: Application layer support for V2X services; Functional architecture and information flows | 23.286 | 2.0.0
Presentation of TS 23.287: 'Architecture enhancements for 5G System (5GS) to support Vehicle-to-Everything (V2X) services' for Approval | 23.287 | 2.0.0
Presentation of TS 23.288: 'Architecture enhancements for 5G System (5GS) to support network data analytics services (Release 16)'. | 23.288 | 1.0.0
Presentation of TS 23.316: 'Wireless and wireline convergence access support for the 5G System (5GS) (Release 16)'. | 23.316 | 1.0.0
Presentation of TS 23.434 v2.0.0 for approval: Service enabler architecture layer for verticals | 23.434 | 2.0.0
Draft TS 26.501 5G Media Streaming (5GMS); General description and architecture (Release 16) v. 2.0.0 (5GMSA) | 26.501 | 16.1.0
TS 28.404 Management of Quality of Experience (QoE) measurement collection; Concepts, use cases and requirements | 28.404 | 2.0.0
TS 32.160 Management and orchestration; Management service template | 32.160 | 2.0.0
TS 33.511 security assurance specification for the gNB network product class | 33.511 | 1.0.0
TS 33.512 5G Security Assurance Specification (SCAS) Access and Mobility Management Function | 33.512 | 1.0.1
TS 33.513 5G Security Assurance Specification (SCAS); User Plane Function (UPF) | 33.513 | 1.0.1
TS 33.514 5G Security Assurance Specification (SCAS) for the Unified Data Management (UDM) network product class | 33.514 | 1.0.1
TS 33.515 5G Security Assurance Specification (SCAS) for the Session Management Function (SMF) network product class | 33.515 | 1.0.1
TS 33.516 5G Security Assurance Specification (SCAS) Authentication Server Function (AUSF) | 33.516 | 1.0.1
TS 33.517 5G Security Assurance Specification (SCAS) for the Security Edge Protection Proxy (SEPP) network product class | 33.517 | 1.0.1
TS 33.518 5G Security Assurance Specification (SCAS) for the Network Repository Function (NRF) network product class | 33.518 | 1.0.1
TS 33.519 Security Assurance Specification (SCAS) for the Network Exposure Function (NEF) network product class | 33.519 | 1.0.1

## Slide 19: Latest Reports from SA WGs
SA1 Report – https://www.3gpp.org/ftp/tsg_sa/TSG_SA/TSGS_85/Docs/SP-190882.zip
SA2 Report – https://www.3gpp.org/ftp/tsg_sa/TSG_SA/TSGS_85/Docs/SP-190600.zip
SA3 Report – https://www.3gpp.org/ftp/tsg_sa/TSG_SA/TSGS_85/Docs/SP-190715.zip
SA4 Report – https://www.3gpp.org/ftp/tsg_sa/TSG_SA/TSGS_85/Docs/SP-190637.zip
SA5 Report – https://www.3gpp.org/ftp/tsg_sa/TSG_SA/TSGS_85/Docs/SP-190717.zip
SA6 Report – https://www.3gpp.org/ftp/tsg_sa/TSG_SA/TSGS_85/Docs/SP-190721.zip

## Slide 20: Release 15 and Earlier

## Slide 21: Release 15 and Earlier
All Studies and Work Items are 100 %, besides some IETF drafts.

## Slide 22: Release 16 (ongoing)

## Slide 23: Rel-16 Exception Sheets (SA#84)
Tdoc | Name | Acronym | WG | Status (SA#85)
SP-190433 | Exception sheet for eLCS | 5G_eLCS | SA WG2 | Completed
SP-190434 | Exception sheet for Rel-16 Vertical_LAN | Vertical_LAN | SA WG2 | Completed
SP-190435 | Exception sheet for 5G_URLLC | 5G_URLLC | SA WG2 | Completed
SP-190436 | Exception sheet for Rel-16 eV2XARC | eV2XARC | SA WG2 | Completed
SP-190437 | TS 23.316 5WWC Exception | 5WWC | SA WG2 | Completed
SP-190438 | Exception Sheet for ATSSS | ATSSS | SA WG2 | Completed
SP-190439 | 5G_CIoT Exception Sheet | 5G_CIoT | SA WG2 | Completed
SP-190546 | Exception sheet for Rel-16 WI 'Optimisations on UE radio capability signalling' (RACS) | RACS | SA WG2 | Completed (UCMF shifted to CT4)
SP-190582 | Exception sheet for Rel-16 5G_eSBA | 5G_eSBA | SA WG 2 | Completed
SP-190474 | Rel-16 Work Item Exception for eMCCI | eMCCI | SA WG6 | Completed
SP-190475 | Rel-16 Work Item Exception for eMCData2 | eMCData2 | SA WG6 | Completed

## Slide 24: Rel-16 SA1 Studies
Name | Acronym | Group | Completion | tdoc | Rapporteur
5G positioning services | FS_5G_HYPOS | S1 | 100% | SP-170589 | Ries, Lionel, ESA
LAN support in 5G | FS_5GLAN | S1 | 100% | SP-170456 | Nasielski, Jack, Qualcomm Incorporated
Study on 5G message service for MIoT | FS_5GMSG | S1 | 100% | SP-170704 | Zheng, Jianping, China Mobile
Study on using Satellite Access in 5G | FS_5GSAT | S1 | 100% | SP-170702 | MICHEL, Cyril
Study on Business Role Models for Network Slicing | FS_BMNS | S1 | 100% | SP-180169 | Covell, Betsy, Nokia
Study on Communication for Automation in Vertical Domains | FS_CAV | S1 | 100% | SP-170169 | Walewski, Joachim, Siemens AG
Enhancement of LTE for Efficient delivery of Streaming Service | FS_eLESTR | S1 | 100% | SP-160960 | China Telecommunications, XIA Xu
Study on enhancements to IMS for new real time communication services | FS_enIMS | S1 | 100% | SP-170703 | China Mobile, Hui Cai
Study on enhancements of Public Warning System | FS_FRMCS2 | S1 | 100% | SP-170588 | Merkel, Juergen, Nokia
Mobile Communication System for Railways 2 | FS_ID_UAS | S1 | 100% | SP-180172 | Eddy Hall; Qualcomm Incorporated
Study on Remote Identification of Unmanned Aerial Systems | FS_LUCIA | S1 | 100% | SP-170995 | Bischinger, Kurt; Deutsche Telekom
User Identities and Authentication | FS_MARCOM | S1 | 100% | SP-170453 | SyncTechno Inc., Hyounhee Koo
Study on Maritime Communication Services over 3GPP system | FS_PARLOS | S1 | 100% | SP-160904 | Covell, Betsy
Study on Improvement of V2X Service Handling | FS_V2XIMP | S1 | 100% | SP-180247 | SungDuck Chun; LG Electronics
Provision of Access to Restricted Local Operator Services by Unauthenticated UEs | FS_PARLOS | S1 | 100% | SP-160733 | SyncTechno Inc., Hyounhee Koo
Green if 100% complete

## Slide 25: Rel-16 SA2 Studies
Name | Acronym | Group | Completion | tdoc | Rapporteur
Shifted to CT WGs Study on Enhanced IMS to 5GC Integration | FS_eIMS5G | S2 | 70% | SP-180736 | Joul, Chris, T-Mobile USA
Stopped Study on encrypted traffic detection | FS_ENTRADE | S2 | 70% | SP-181111 | Chi Ren, China Unicom
Study on enhancement of URLLC supporting in 5GC | FS_5G_URLLC | S2 | 100% | SP-180118 | Hui Ni, Huawei
Study for single radio voice continuity from 5GS to 3G | FS_5G-SRVCC | S2 | 100% | SP-180239 | Chi Ren, China Unicom
Study on the Wireless and Wireline Convergence for the 5G system architecture | FS_5WWC | S2 | 100% | SP-170380 | Marco Spini, Huawei Technologies
Study on ATSSS | FS_ATSSS | S2 | 100% | SP-180732 | So, Tricci, ZTE
Study on 5G_CIoT | FS_CIoT_5G | S2 | 100% | SP-180614 | Sebastian Speicher
Study on Enhancement to the 5GC Location Services | FS_eLCS | S2 | 100% | SP-180734 | Ming Ai, CATT
Study of enablers for Network Automation for 5G | FS_eNA | S2 | 100% | SP-180792 | Xiaobo Wu, Huawei Technologies
Study on Enhancement of Network Slicing | FS_eNS | S2 | 100% | SP-180503 | ZTE, Tricci So
Study on Enhancements to the Service-Based 5G System Architecture | FS_eSBA | S2 | 100% | SP-180231 | Tao Sun (China Mobile)
Study on ETSUN | FS_ETSUN | S2 | 100% | SP-180731 | Laurent Thiebaut (Nokia)
Study on eV2XARC | FS_eV2XARC | S2 | 100% | SP-180733 | LaeYoung Kim, LG Electronics
Study on Stage 2 for PARLOS | FS_PARLOS_SA2 | S2 | 100% | SP-180501 | Nokia (Nicolas Drevon
Study on RACS | FS_RACS | S2 | 100% | SP-180599 | Haris Zisimopoulos, Qualcomm Incorporated
Study on UDICOM | FS_UDICoM | S2 | 100% | SP-190148 | Susana Sabater (Vodafone
Study on 5GS Enhanced support of Vertical and LAN Services | FS_Vertical_LAN | S2 | 100% | SP-180507 | Devaki Chandramouli, Nokia

## Slide 26: Rel-16 SA3 Studies
Name | Acronym | Group | Completion | tdoc | Rapporteur
Study on storage and transport of 5GC security parameters for ARPF authentication | FS_5GC_SEC_ARPF | S3 | 0% | SP-190708 | Evans, Timothy, Vodafone
Study on Security Impacts of Virtualisation | FS_SIV | S3 | 12% | SP-181236 | Alex Leadbeater, BT Plc
Study on authentication enhancements in 5GS | FS_AUTH_ENH | S3 | 15% | SP-190713 | Tsiatsis, Vlasios,
Study on SECAM and SCAS for 3GPP virtualized network products | FS_VNP_SECAM_SCAS | S3 | 30% | SP-180696 | Minpeng Qi, China Mobile
Study on Security for NR_IAB | FS_NR_IAB_Sec | S3 | 50% | SP-190106 | Rajavelsamy Rajadurai, Samsung,
Study on User Plane Integrity Protection | FS_UP_IP_Sec | S3 | 50% | SP-181035 | Evans, Tim, Vodafone
Study on Security Aspects of 3GPP support for Advanced V2X Services | FS_eV2X_Sec | S3 | 60% | SP-190108 | Joonwoong Kim, LG Electronics
Study on Long Term Key Update Process (LTKUP) Detailed solutions | FS_LTKUP_Detail | S3 | 60% | SP-181038 | Evans, Tim, Vodafone
Study on 5G security enhancement against false base stations | FS_5GFBS | S3 | 66% | SP-180690 | Ivy Guo, Apple
Study on authentication and key management for applications based on 3GPP credential in 5G | FS_AKMA | S3 | 70% | SP-180443 | Jin Peng, China Mobile
Study on the security of the Wireless and Wireline Convergence for the 5G system architecture | FS_5WWC_SEC | S3 | 75% | SP-180438 | He Li, Huawei Technologies
Study on Security for 5GS Enhanced support of Vertical and LAN Services | FS_Vertical_LAN_SEC | S3 | 78% | SP-180697 | Jerichow, Anja (Nokia)
Study on Security aspects of Enhancement of Network Slicing | FS_eNS_SEC | S3 | 80% | SP-180692 | 
Study on Security Aspects of the 5G Service Based Architecture | FS_SBA_Sec | S3 | 80% | SP-180598 | Christine Jost, Ericsson
Study on evolution of Cellular IoT security for the 5G System | FS_CIoT_sec_5G | S3 | 90% | SP-180440 | Henrik Normann, Ericsson
Study on supporting 256-bit algorithms for 5G | FS_256_Algo | S3 | 100% | SP-171054 | Evans, Tim, Vodafone Group
Study on the security of URLLC for 5GS | FS_5G_URLLC_SEC | S3 | 100% | SP-180910 | Rong Wu, Huawei Technologies
Study on security aspects of single radio voice continuity from 5G to UTRAN | FS_5G_UTRAN_SEC | S3 | 100% | SP-180209 | Feng Gao, China Unicom
Stopped - Study of KDF negotiation for 5G System Security | FS_5GS_KDF | S3 | 100% | SP-180691 | Ahmad Muhanna
Study on Security of the enhancement to the 5GC location services | FS_eLCS_Sec | S3 | 100% | SP-180694 | Wei Zhou, CATT
Study on Long Term Key Update Procedures | FS_LTKUP | S3 | 100% | SP-170413 | Evans, Tim, Vodafone
Study on Security Aspects of PARLOS | FS_PARLOS_Sec | S3 | 100% | SP-180442 | Greg Schumacher, Sprint
Green if new since last PCG

## Slide 27: Rel-16 SA4 Studies
Name | Acronym | Group | Completion | tdoc | Rapporteur
Study on eXtended Reality (XR) in 5G | FS_5GXR | S4 | 60% | SP-180667 | Thomas Stockhammer, Qualcomm Incorporated
Study on Typical Traffic Characteristics of Media Services | FS_TyTrac | S4 | 60% | SP-180666 | Thomas Stockhammer, Qualcomm Incorporated
Study on ambient noise test methodology for evaluation of acoustic UE performance | FS_ANTeM | S4 | 70% | SP-180986 | Jan Reimes, HEAD acoustics GmbH
Study on V2X Media Handling and Interaction | FS_mV2X | S4 | 90% | SP-170799 | Jung, Kyunghun, Samsung Electronics Co., Ltd
Study on 5G enhanced Mobile Broadband Media Distribution | FS_5GMedia_Distribution | S4 | 100% | SP-170334 | Bouazizi, Imed, Samsung Electronics Co., Ltd.,
Study on Media Handling Aspects of Conversational Services in 5G Systems | FS_5G_MEDIA_MTSI | S4 | 100% | SP-170336 | Oyman, Ozgur, Company: Intel
Study on E2E_DELAY | FS_E2E_DELAY | S4 | 100% | SP-170837 | Oyman, Ozgur, Company: Intel,
Study on EVS Float Conformance Non Bit-Exact | FS_EVS_FCNBE | S4 | 100% | SP-170618 | Fabrice Plante, Intel
Study on UEs Supporting Handset Mode with Non-Traditional Earpieces | FS_HaNTE | S4 | 100% | SP-190041 | Schevciw, Andre, Qualcomm Incorporated
Study on QoE metrics for VR | FS_MBMS_IoT | S4 | 100% | SP-170592 | Cedric thienot, Expway
Study on Typical Traffic Characteristics of Media Services | FS_QoE_VR | S4 | 100% | SP-170614 | Ericsson (Gunnar Heikkilä

## Slide 28: Rel-16 SA5 Studies
Name | Acronym | Group | Completion | tdoc | Rapporteur
Study on autonomous network levels | FS_ANL | S5 | 0% | SP-190928 | China Mobile
Study on protocol enhancement for real time communication | FS_PROTIMP | S5 | 0% | SP-180597 | Olaf Pollakowski, Nokia
Study on non-public networks management | FS_OAM_NPN | S5 | 10% | SP-190137 | ZHANG, Kai, Huawei
Study on management and orchestration aspects with integrated satellite components in a 5G network | FS_5GSAT_MO | S5 | 30% | SP-190138 | MICHEL, Cyril, THALES
Study on Self-Organizing Networks (SON) for 5G | FS_SON_5G | S5 | 80% | SP-180827 | Joey Chou, Intel
Study on Charging Aspects of Network Slicing | FS_NETSLICE_CH | S5 | 85% | SP-181065 | Chen Shan, Huawei
Study on management aspects of communication services | FS_CSMAN | S5 | 100% | SP-180923 | Groenendijk, Jan, Ericsson
Study on management aspects of edge computing | FS_MAN_EC | S5 | 100% | SP-180390 | Joey Chou, Intel
Study on non-file-based trace reporting | FS_OAM_RTT | S5 | 100% | SP-181076 | Andrianov, Anatoly, Nokia
Study on integration of ONAP and 3GPP configuration management services for 5G networks | FS_ONAPCINT | S5 | 100% | SP-181075 | Li Gang, Ericsson
Study on integration of ONAP DCAE and 3GPP management architecture | FS_ONAPDCAE | S5 | 100% | SP-181074 | ORANGE (Jean-Michel Cornily
Study on tenancy concept in 5G networks and network slicing management | FS_TENANCYC | S5 | 100% | SP-180815 | ZHU, Lei (Huawei

## Slide 29: Rel-16 SA6 Studies
Name | Acronym | Group | Completion | tdoc | Rapporteur
Study on Mission Critical services support over 5G System | FS_MCOver5GS | S6 | 40% | SP-181136 | Verweij, Kees, The Police of the Netherlands
Study on location enhancements for mission critical services | FS_enhMCLoc | S6 | 70% | SP-180921 | Dom Lazara, Motorola Solutions
Study on application architecture for the Future Railway Mobile Communication System (FRMCS) Phase 2 | FS_FRMCS2_SA6 | S6 | 100% | SP-181133 | Oettl, Martin, Nokia
Study on MBMS APIs for MC Services | FS_MBMSAPI_MC | S6 | 100% | SP-180237 | Ling Zhang, TD Tech Ltd
Study into discreet listening and logging for mission critical services | FS_MCLOG | S6 | 100% | SP-181138 | Chater-Lea, David, Motorola Solutions
Study on MC services access aspects | FS_MCSAA | S6 | 100% | SP-181135 | Joakim Åkesson, Ericsson
Study on V2XAPP | FS_V2XAPP | S6 | 100% | SP-171071 | Niranth Amogh, Huawei Telecommunications India

## Slide 30: Rel-16 SA1 Work Items
Name | Acronym | Group | % Complete | tdoc | Rapporteur
5G positioning services | 5G_HYPOS | S1 | 100% | SP-180329 | Ries, Lionel, ESA
LAN support in 5G | 5GLAN | S1 | 100% | SP-180593 | Almodovar Chico, Jose Luis, KPN
Integration of Satellite Access in 5G | 5GSAT | S1 | 100% | SP-180326 | MICHEL, Cyril, Thales
5G Voice Service Continuity | 5GVSC | S1 | 100% | SP-171077 | Qun Wei, China Unicom
Business Role Models for Network Slicing | BRMNS | S1 | 100% | SP-180773 | Covell, Betsy, Nokia
Service requirements for cyber-physical control applications in vertical domains | cyberCAV | S1 | 100% | SP-180321 | Joachim W. Walewski (Siemens)
Enhancement of LTE for Efficient delivery of Streaming Service | eLSTR | S1 | 100% | SP-180322 | Xia, Xu, China Telecom
Enhancements to IMS for new real time communication services | enIMS | S1 | 100% | SP-180137 | China Mobile, Hui Cai
Enhancements of Public Warning System | ePWS | S1 | 100% | SP-170998 | Hyounhee Koo, SyncTechno Inc.
Stage 1 of Remote Identification of Unmanned Aerial Systems | ID_UAS | S1 | 100% | SP-180771 | Eddy HALL, Qualcomm incorporated
Maritime Communication Services over 3GPP System | MARCOM | S1 | 100% | SP-180594 | Hyounhee Koo, SyncTechno Inc
Inter-RAT Mobility requirements for real time service | MOBRT | S1 | 100% | SP-180592 | Yang Xu, Oppo
Mobile Communication System for Railways 2 | MONASTERY2 | S1 | 100% | SP-170451 | Merkel, Juergen, Nokia
Message Service Within the 5G System requirements | MSGin5G | S1 | 100% | SP-180920 | Zheng, Jianping, China Mobile
Stage 1 of Multi-device and multi-identity | MuD | S1 | 100% | SP-180315 | Peter Bleckert, Ericsson
Provision of Access to Restricted Local Operator Services by Unauthenticated UEs | PARLOS | S1 | 100% | SP-170449 | Covell, Betsy Nokia
Policy delivery to UE for background data transfer | PDBDT | S1 | 100% | SP-180324 | Takatsugu Kito, KDDI
QoS Monitoring | QoS_MON | S1 | 100% | SP-180141 | Amar Deol
New Services and Markets Technology Enablers – Phase 2 | SMARTER_Ph2 | S1 | 100% | SP-180589 | Li, Alice, Vodafone
User Identities and Authentication | UIA | S1 | 100% | SP-180328 | 
Improvement of V2X service Handling | V2XIMP | S1 | 100% | SP-181013 | SungDuck Chun; LG Electronics

## Slide 31: Rel-16 SA2 Work Items
Name | Acronym | Group | % Complete | tdoc | Rapporteur
Architecture enhancements for the support of Integrated access and backhaul (IAB) | IABARC | S2 | 33% | SP-190627 | Hong Cheng, Qualcomm Incorporated
Architecture enhancements for 3GPP support of advanced V2X services | eV2XARC | S2 | 90% | SP-181121 | LaeYoung Kim, LG Electronics
Enablers for Network Automation for 5G | eNA | S2 | 92% | SP-181123 | Xiaobo Wu, Huawei Technologies
5GS Enhanced support of Vertical and LAN Services | Vertical_LAN | S2 | 97% | SP-181120 | Devaki Chandramouli, Nokia
Cellular IoT support and evolution for the 5G System | 5G_CIoT | S2 | 98% | SP-181118 | Sebastian Speicher
Enhancement to the 5GC LoCation Services | 5G_eLCS | S2 | 100% | SP-181119 | Ming Ai, CATT
Enhancements to the Service-Based 5G System Architecture | 5G_eSBA | S2 | 100% | SP-181125 | Tao Sun (China Mobile)
Single radio voice continuity from 5GS to 3G | 5G_SRVCC | S2 | 100% | SP-180897 | Chi Ren, China Unicom
Enhancement of URLLC support in the 5G Core network | 5G_URLLC | S2 | 100% | SP-181233 | Hui Ni, Huawei
S6b Optional for ePDG connected to 5GS | 5GS_S6b_Optional | S2 | 100% | SP-190447 | Irfan Ali, Cisco
Wireless and Wireline Convergence for the 5G system architecture | 5WWC | S2 | 100% | SP-181117 | Marco Spini, Huawei Technologies
Access Traffic Steering, Switch and Splitting support in the 5G system architecture | ATSSS | S2 | 100% | SP-181124 | So, Tricci, ZTE
SBA aspects of enhanced IMS to 5GC integration | eIMS5G_SBA | S2 | 100% | SP-190181 | T-Mobile USA, Christopher Joul
Enhancement of Network Slicing | eNS | S2 | 100% | SP-181232 | ZTE, Tricci So
Enhancing Topology of SMF and UPF in 5G Networks | ETSUN | S2 | 100% | SP-181116 | 
Provision of Access to Restricted Local Operator Services by Unauthenticated UEs | PARLOS | S2 | 100% | SP-180738 | Nokia (Nicolas Drevon
Optimisations on UE radio capability signalling | RACS | S2 | 100% | SP-190180 | Haris Zisimopoulos
Reliable Data Service Serialization Indication | RDSSI | S2 | 100% | SP-190446 | Starsinic, Michael, Convida Wireless LLC
User data interworking, Coexistence and Migration | UDICOM | S2 | 100% | SP-190182 | Alessio Casati, Nokia
5GS Transfer of Policies for Background Data Transfer | xBDT | S2 | 100% | SP-180509 | Takeshi Usui KDDI
(IETF) 0-RTT TCP Convert Protocol (draft-ietf-tcpm-converters) | ATSSS | S2-IETF | 30% |  | 
(IETF) TCP Extensions for Multipath Operation with Multiple Addresses (draft-ietf-mptcp-rfc6824bis) | ATSSS | S2-IETF | 80% |  | 

## Slide 32: Rel-16 SA3 Work Items
Name | Acronym | Group | % Complete | tdoc | Rapporteur
Cellular IoT support and evolution for the 5G System | 5G_CIoT | S3 | 0% | SP-190897 | Henrik Normann, Ericsson
Enhancement to the 5GC LoCation Services | 5G_eLCS | S3 | 0% | SP-190900 | Wei Zhou, CATT
Security for the Service-Based 5G System Architecture | 5G_eSBA | S3 | 0% | SP-190899 | Nagendra Bykampadi, Nokia
Authentication and key management for applications based on 3GPP credential in 5G | AKMA | S3 | 0% | SP-190711 | Xiaoting Huang, China Mobile
Security aspects of Enhanced Network Slicing | eNS | S3 | 0% | SP-190712 | Suresh.p.nair@nokia.com
Security for Integrated access and backhaul for NR | IAB | S3 | 0% | SP-190902 | Rajavelsamy Rajadurai, Samsung
Security aspects of Service Enabler Architecture Layer for Verticals | SEAL | S3 | 0% | SP-190901 | Rajavelsamy Rajadurai (Samsung)
Security of URLLC for 5GS | 5G_URLLC_SEC | S3 | 30% | SP-190351 | Rong Wu, Huawei Technologies
5GS Enhanced support of Vertical and LAN Services | Vertical_LAN_SEC | S3 | 30% | SP-190352 | Jerichow, Anja, Nokia
Mission Critical Services Security Enhancements | MCXSec | S3 | 45% | SP-180596 | Woodward, Tim, Motorola Solutions, Inc
Security aspects of Enhancements for Common API Framework for 3GPP Northbound APIs | eCAPIF | S3 | 90% | SP-1901240 | Rajavelsamy Rajadurai, Samsung
Security aspects of single radio voice continuity from 5GS to UTRAN | 5GS_UTRAN_SEC | S3 | 100% | SP-190703 | Feng Gao, China Unicom
Security of Wireless and Wireline Convergence for the 5G system architecture | 5WWC | S3 | 100% | SP-190898 | He Li, Huawei Technologies
Security Assurance Specification for 5G | SCAS_5G | S3 | 100% | SP-180689 | Marcus Wong, Huawei Technologies
(IETF) The Transport Layer Security (TLS) Protocol Version 1.3 (RFC 8446) | TEI16 | S3-IETF | 100% |  | 
Lawful Interception Report Rel-16 | LIR16 | S3LI | 0% | SP-190342 | Nag Rao, Nokia
Lawful Interception Rel-16 | LI16 | S3LI | 40% | SP-181210 | Alex Leadbeater, BT

## Slide 33: Rel-16 SA4 Work Items
Name | Acronym | Group | % Complete | tdoc | Rapporteur
RTCP Verification for Real-Time Services | RTCPVer | S4 | 0% | SP-190639 | Burman, Bo, Ericsson LM,
5G Media Streaming stage 3 | 5GMS3 | S4 | 25% | SP-190464 | Frédéric GABIN, Ericsson
VR QoE metrics | VRQoE | S4 | 25% | SP-190331 | Gunnar HEIKKILÄ
Enhancements to Framework for Live Uplink Streaming | E_FLUS | S4 | 75% | SP-180285 | Lo, Charles, Qualcomm Incorporated
Media Handling Extensions for 5G Conversational Services | 5G_MEDIA_MTSI_ext | S4 | 80% | SP-190640 | Oyman, Ozgur, Company: Intel
EVS Floating-point Conformance for Non Bit-Exact | EVS_FCNBE | S4 | 80% | SP-180983 | Fabrice, Plante, Intel
Service Interactivity | SerInter | S4 | 80% | SP-170796 | Lo, Charles, Qualcomm Incorporated
Media streaming architecture | 5GMSA | S4 | 100% | SP-180984 | Paul Szucs – Sony Europe B.V.
Alternative EVS implementation using updated fixed-point basic operators | Alt_FX_EVS | S4 | 100% | SP-180286 | Pawate, Raj, Cadence Design Systems Inc
Usage of CAPIF for xMB API | CAPIF4xMB | S4 | 100% | SP-180031 | Thorsten Lohmar, Ericsson LM
Coverage and Handoff Enhancements for Multimedia | CHEM | S4 | 100% | SP-180664 | Nikolai Leung
Media Handling Aspects of RAN Delay Budget Reporting in MTSI | E2E_DELAY | S4 | 100% | SP-180662 | Oyman, Ozgur, Company: Intel
Addition of HLG HDR to TV Video Profiles | HLG_HDR | S4 | 100% | SP-180287 | Paul Szucs, Sony Europe Limited
MCData File Distribution support over xMB | MC_XMB | S4 | 100% | SP-180665 | Thiénot Cédric, Expway

## Slide 34: Rel-16 SA5 Work Items
Name | Acronym | Group | % Complete | tdoc | Rapporteur
KPI reporting (Enhancement of performance assurance for 5G networks including network slicing) | 5G_SLICE_ePA-KPI | S5 | 0% | SP-190881 | ZHU, Weihong, ZTE Corporation
Network Slice Management Charging in 5G System | 5GS_NSMCH | S5 | 0% | SP-190788 | Gardella, Maryse, Nokia
Network Slice Performance and Analytics Charging in 5G System | 5GS_NSPACH | S5 | 0% | SP-190780 | Chen Shan, Huawei
Closed loop SLS Assurance | COSLA | S5 | 0% | SP-190781 | Groenendijk, Jan, Ericsson
Enhancing Topology of SMF and UPF in 5G Networks | ETSUN | S5 | 0% | SP-190880 | Dong, Jia, China Mobile
Management Aspects of 5G Service-Level Agreement | MA5SLA | S5 | 0% | SP-190789 | Hu, Yushuang, CMCC
Enhancement of 3GPP management system for multiple tenant environment support | MEMTANE | S5 | 0% | SP-190786 | Zhu, Lei, Huawei
Streaming trace reporting | OAM_RTT | S5 | 0% | SP-190782 | Andrianov, Anatoly, Nokia
Self-Organizing Networks (SON) for 5G networks | SON_5G | S5 | 0% | SP-190785 | Joey Chou, Intel
IMS Charging in 5G System Architecture | 5GSIMSCH | S5 | 10% | SP-190367 | Jahangir, Zeeshan, T-Mobile USA
Trace Management in the context of Services Based Management Architecture | TM_SBMA | S5 | 10% | SP-181073 | Andrianov, Anatoly, Nokia
Integration of ONAP and 3GPP 5G management framework | ONAP3GPP | S5 | 25% | SP-190139 | SMITH David K., AT&T
NRM enhancements | eNRM | S5 | 40% | SP-190778 | Jing Ping, Nokia
Intent driven management service for mobile network | IDMS_MN | S5 | 45% | SP-180899 | Zou Lan, Huawei
Volume Based Charging Aspects for VoLTE | VBCLTE | S5 | 55% | SP-180813 | Chen, Ai, China Mobile
Network Exposure Charging in 5G System Architecture | 5GS_Ph1_NEFCH | S5 | 60% | SP-181070 | Tornkvist, Robert, Ericsson
Discovery of management services in 5G | 5GDMS | S5 | 65% | SP-181072 | Attila Horvat, Huawei Technologies Sweden AB
Charging AMF in 5G System Architecture Phase 1 | 5GS_Ph1_AMFCH | S5 | 70% | SP-181071 | Gardella, Maryse, Nokia
Energy efficiency of 5G | EE_5G | S5 | 70% | SP-180819 | CORNILY, Jean-Michel, ORANGE
Management of QoE measurement collection | QOED | S5 | 70% | SP-181069 | Petersen, Robert, Ericsson
Enhancement of performance assurance for 5G networks including network slicing | 5G_SLICE_ePA | S5 | 85% | SP-190247 | Xiaowei Sun (China Mobile)
Network policy management for mobile networks based on NFV scenarios | NETPOL | S5 | 85% | SP-180821 | China Mobile Hao Zhang
Charging Enhancement of 5GC interworking with EPC | 5GIEPC_CH | S5 | 100% | SP-181067 | Chen Shan, Huawei
Methodology for 5G management specifications | METHOGY | S5 | 100% | SP-180822 | Groenendijk, Jan, Ericsson
OAM aspects of LTE and WLAN integration | OAM_LTE_WLAN | S5 | 100% | SP-180820 | Yizhi Yao, Intel Corporation
Nchf Online and Offline charging services | OFSBI_CH | S5 | 100% | SP-181066 | Zhu Lei, Huawei

## Slide 35: Rel-16 SA6 Work Items
Name | Acronym | Group | Completion | tdoc | Rapporteur
Application layer support for V2X services | V2XAPP | S6 | 100% | SP-180898 | Niranth Amogh, Huawei Telecommunications India
Enhanced Mission Critical Push-to-talk architecture phase 2 | enh2MCPTT | S6 | 100% | SP-190068 | Dom Lazara; Motorola Solutions
Enhancements to Functional architecture and information flows for Mission Critical Data | eMCData2 | S6 | 100% | SP-180378 | Shih, Jerry, AT&T
MBMS APIs for Mission Critical Services | MBMSAPI_MCS | S6 | 100% | SP-180380 | Ling Zhang, TD Tech Ltd.
Enhanced Mission Critical System Migration and Interconnection | eMCSMI | S6 | 100% | SP-180379 | Chater-Lea, David; Motorola Solutions
Enhanced Mission Critical Communication Interworking with Land Mobile Radio Systems | eMCCI | S6 | 100% | SP-180680 | Monnes, Peter, Harris Corporation
Application Architecture for Mobile Communication System for Railways 2 | MONASTERY2 | S6 | 100% | SP-190064 | Oettl, Martin, Nokia
Enhancements for Common API Framework for 3GPP Northbound APIs | eCAPIF | S6 | 100% | SP-181137 | Basavaraj Pattan, Samsung

## Slide 36: Security Assurance SCAS_5G 100%
NESAS/SCAS is the only standardized security evaluation scheme available for mobile network industry
GSMA defines and maintains NESAS
  Cover audit of the vendor’s product development and lifecycle management process, test laboratory accreditation, dispute resolution process.
3GPP defines SCAS
  Defines security requirements and test cases for mobile network equipment
s d
UDM
S
AUSF
S
AMF
S
SMF
G
UPF
B
gNB
S
NRF
s g
SEPP
s g
SEPP
S
NRF
S
SMF
G
UPF
S
NEF
S
NEF
Internet, voice and other services
N2
N9
N32
B
ng-eNB
N4
N3
N2
N4
TS 33.516
TS 33.515
TS 33.514
TS 33.513
TS 33.512
TS 33.511
TS 33.518
TS 33.517
TS 33.519
Visited PLMN
Home PLMN
Xn
Service-Based Interface

## Slide 37: Release 17 (ongoing)

## Slide 38: Rel-17 SA1 Studies
Name | Acronym | Group | Compl. | tdoc | Rapporteur
Study on Future Railway Mobile Communication System3 | FS_FRMCS3 | S1 | 80% | SP-190321 | Gach, Guillaume, UIC,
Enhancements for cyber-physical control applications in vertical domains | FS_eCAV | S1 | 85% | SP-190092 | Michael Bahr, Siemens AG
Communication Service Requirements for Critical Medical Applications | FS_CMED | S1 | 90% | SP-180783 | Mathieu Lagrange, b<>com
Multimedia Priority Service (MPS) Phase 2 | FS_MPS2 | S1 | 90% | SP-190315 | Singh, Ray P; Vencore Labs
Enhanced Relays for Energy eFficiency and Extensive Coverage | FS_REFEC | S1 | 95% | SP-180785 | Jose Luis Almodovar Chico, KPN
Support for Multi-USIM Devices | FS_MUSIM | S1 | 98% | SP-190091 | Liao, Ellen C, Intel
Asset Tracking for 5G | FS_5G_ATRAC | S1 | 100% | SP-180922 | Thierry Berisot, NOVAMINT
Audio-Visual Service Production | FS_AVPROD | S1 | 100% | SP-181015 | Roland Beutler, EBU
5G Enhancement for UAVs | FS_EAV | S1 | 100% | SP-180909 | Qun Wei, China Unicom
Support for Minimization of service Interruption | FS_MINT | S1 | 100% | SP-190090 | SungDuck Chun; LG Electronics
Network Controlled Interactive Service | FS_NCIS | S1 | 100% | SP-180341 | YANG Ning, Oppo

## Slide 39: Rel-17 SA2 Studies
Name | Acronym | Group | Compl. | tdoc | Rapporteur
Study on system architecture for next generation real time communication services | FS_NG_RTC | S2 | 0% | SP-180508 | Yi Jiang
Study on Application Awareness Interworking between LTE and NR | FS_AAI_LTE_NR | S2 | 30% | SP-180122 | Biao Long, China Telecom
Study on System enhancement for Proximity based Services in 5GS | FS_5G_ProSe | S2 | 0% | SP-190443 | Qiang Deng, CATT
Study on enhancement of support for 5G LAN-type service | FS_5GLAN_enh | S2 | 0% | SP-190454 | Runze Zhou, Huawei
Study on service-based support for SMS in 5GC | FS_SB_SMS | S2 | 0% | SP-190184 | Georg Foti
Study on Architectural enhancements for 5G multicast-broadcast services | FS_5MBS | S2 | 0% | SP-190442 | Dario Serafino Tonesi, Huawei
Study on architecture aspects for using satellite access in 5G | FS_5GSAT_ARCH | S2 | 70% | SP-181253 | MICHEL, Cyril
Study on enhancement of support for 5WWC | FS_5WWC_Ph2 | S2 | 0% | SP-190562 | Huan Li, Huawei
Study on Access Traffic Steering, Switch and Splitting support in the 5G system architecture Phase 2 | FS_ATSSS_Ph2 | S2 | 0% | SP-190558 | So, Tricci, ZTE
Study on Enhancement to the 5GC LoCation Services-Phase 2 | FS_eLCS_ph2 | S2 | 0% | SP-190452 | Ming Ai, CATT
Study on Enablers for Network Automation for 5G - phase 2 | FS_eNA_Ph2 | S2 | 0% | SP-190557 | Xiaobo Wu, Huawei Technologies
Study on enhancement of support for Edge Computing in 5GC | FS_enh_EC | S2 | 0% | SP-190185 | Hui Ni, Huawei
Study on enhanced support of Non-Public Networks | FS_eNPN | S2 | 0% | SP-190453 | Peter Hedman
Study on Enhancement of Network Slicing Phase 2 | FS_eNS_Ph2 | S2 | 0% | SP-190931 | So, Tricci, ZTE
Study on enhancement of 5G UE Policy | FS_eUEPO | S2 | 0% | SP-190449 | Changhong Shan, Intel
Study on V2X services – Phase 2 | FS_eV2XARC_Ph2 | S2 | 0% | SP-190631 | LaeYoung Kim, LG Electronics
Study on supporting Unmanned Aerial Systems Connectivity, Identification, and Tracking | FS_ID_UAS_SA2 | S2 | 0% | SP-181114 | Qualcomm Incorporated, Stefano Faccin
Study on enhanced support of Industrial IoT | FS_IIoT | S2 | 0% | SP-190932 | Nokia, Devaki Chandramouli,
Study on Multimedia Priority Service (MPS) Phase 2, Stage 2 | FS_MPS2_St2 | S2 | 0% | SP-190629 | Don Lukacs; Perspecta Labs
Support for Multi-USIM Devices | FS_MUSIM | S2 | 0% | SP-190248 | Sašo Stojanovski, Intel
Study on service-based support for SMS in 5GC | FS_SB_SMS | S2 | 0% | SP-190184 | George Foti
Study on UPF enhancement for control and SBA | FS_UPCAS | S2 | 0% | SP-190187 | Dan Wang, China Mobile
Study on the Usage of User Identifiers in the 5G System | FS_UUI5 | S2 | 0% | SP-190450 | Starsinic, Michael, Convida Wireless LLC

## Slide 40: Rel-17 SA4 & SA5 Studies
Name | Acronym | Group | Compl. | tdoc | Rapporteur
Study on VR Streaming Conformance and Guidelines | FS_VR_CoGui | S4 | 0% | SP-190642 | Igor CURCIO
Name | Acronym | Group | Compl. | tdoc | Rapporteur
New Study on enhancement of Management Data Analytics Service | FS_eMDAS | S5 | 0% | SP-190930 | Yao, Yizhi, Intel

## Slide 41: Rel-17 SA6 Studies
Name | Acronym | Group | Compl. | tdoc | Rapporteur
Study on support of the 5GMSG Service | FS_5GMARCH | S6 | 20% | SP-190559 | Liu, Yue, China Mobile
Study on application layer support for Factories of the Future in 5G network | FS_FFAPP | S6 | 20% | SP-181139 | Shao Weixiang, ZTE Corporation
Study on Mission Critical services over 5G multicast-broadcast system | FS_MC5MBS | S6 | 20% | SP-190929 | Val Oprescu, AT&T
Study on enhancements to application layer support for V2X services | FS_eV2XAPP | S6 | 25% | SP-190477 | Niranth Amogh, Huawei Telecommunications India
Study on application layer support for Unmanned Aerial System (UAS) | FS_UASAPP | S6 | 25% | SP-181252 | Niranth Amogh, Huawei
Study on Application Architecture for enabling Edge Applications | FS_EDGEAPP | S6 | 70% | SP-190065 | Nishant Gupta, Samsung

## Slide 42: Rel-17 SA1 Work Items
Name | Acronym | Group | Compl. | tdoc | Rapporteur
Support for Multi-USIM Devices | MUSIM | S1 | 50% | SP-190309 | Liao, Ellen C, Intel
Broadcast / Multicast requirements supporting Mission Critical Services in 5G | 5MBS_eMC | S1 | 80% | SP-190822 | Toobe, Jens, BDBOS
Audio-Visual Service Production | AVPROD | S1 | 80% | SP-190304 | Wagdin, Ian, BBC
Communication Service Requirements for Critical Medical Applications | CMED | S1 | 80% | SP-190306 | Lagrange, Mathieu, b<>com
5G Enhancement for UAVs | EAV | S1 | 80% | SP-190308 | Qun Wei, China Unicom
Enhancements for cyber-physical control applications in vertical domains | eCAV | S1 | 80% | SP-190310 | Bahr, Michael, Siemens AG
Support for Minimization of service Interruption | MINT | S1 | 80% | SP-190814 | SungDuck Chun; LG Electronics
Complete Gap Analysis for Railways Mobile Communication System | MONASTERYEND | S1 | 80% | SP-190312 | Gach, Guillaume, UIC
Network Controlled Interactive Service | NCIS | S1 | 80% | SP-190303 | Ning YANG, oppo
Multimedia Priority Service (MPS) Phase 2 | MPS2 | S1 | 85% | SP-190561 | Singh, Ray P; Perspecta Labs
Enhanced Relays for Energy eFficiency and Extensive Coverage | REFEC | S1 | 90% | SP-190307 | Norp, Toon, KPN
Asset Tracking for 5G | ATRAC | S1 | 95% | SP-190816 | Thierry Berisot, NOVAMINT
Enhanced Calling Name Service Analytics Interworking | eCNAM_An | S1 | 100% | SP-190818 | Hala.Mowafy@ericsson.com
Enhancement for the 5G Control Plane Steering of Roaming for UE in CONNECTED mode | eCPSOR_CON | S1 | 100% | SP-190820 | Minokuchi, Atsushi, NTT DOCOMO
Multi-Device and multi-identity Enhancements | MuDE | S1 | 100% | SP-190823 | Adrian.buckley@vivo.com
Verification-modified Calling Name Display | VMOD_DISPLAY | S1 | 100% | SP-190085 | Hala Mowafy, Ericsson

## Slide 43: Rel-17 SA2/3/4/5/6 Work Items
Name | Acronym | Group | Compl. | tdoc | Rapporteur
5G System Enhancement for Advanced Interactive Services | 5G_AIS | S2 | 0% | SP-190564 | Lei Yixue, Tencent
Supporting Flexible Local Area Data Network | FLADN | S2 | 0% | SP-190563 | LG Electronics, Hyunsook Kim
Integration of GBA into 5GC | GBA_5G | S3 | 0% | SP-190714 | Vlasios Tsiatsis, Ericsson
Terminal Audio quality performance and Test methods for Immersive Audio Services | ATIAS | S4 | 10% | SP-190040 | Stéphane Ragot, Orange
Support of Immersive Teleconferencing and Telepresence for Remote Terminals | ITT4RT | S4 | 20% | SP-180985 | Ye-Kui Wang , Huawei Technologies Co. Ltd.
EVS Codec Extension for Immersive Voice and Audio Services | IVAS_Codec | S4 | 26% | SP-170611 | 
MC services support on IOPS mode of operation | MCIOPS | S6 | 10% | SP-190480 | Camilo.solano@ericsson.com
Enhancements to Application Architecture for the Mobile Communication System for Railways Phase 2 | eMONASTERY2 | S6 | 70% | SP-190565 | Oettl, Martin, Nokia
(Small) Technical Enhancements and Improvements for Rel-17 | TEI17 |  | 0% |  | 

## Slide 44: Rel-17 Prioritization @SA#85
Prioritization of Rel-17 (Study/Work) items is only required for SA2, all other SA WGs can cover the estimated efforts for their planned items in the estimated time frame.
The prioritization discussions were made under the current assumption that Rel-17 is a 15 month release and that in the remaining 12 months there will be 7 SA2 meetings.
SA#85 categorized all Rel-17 SA2 items into three categories
  in – i.e. the item will definitely be contained in Rel-17, but might undergo further down-scoping until SA#86 (see next slides)
  in* – i.e. the item has a chance to become part of Rel-17, given that time in SA2 is available after all (down-scoped) in items are served.
  out – i.e. the item will not be in Rel-17.
The items listed included all known Rel-17 SA2 items as well as all SA1 items for which so far no corresponding SA2 item has been created.
Note that some of the in items are currently estimated to use more than the maximal available SA2 TUs per item.
The prioritization took many factors into account, e.g.
  prioritized lists by companies which were consolidated by the SA Chairman;
  dependencies with RAN as well as with outside boides (e.g. IETF);
  estimated SA2 Time Units per item.

## Slide 45: Prioritized R17 List – in & in*

## Slide 46: Prioritized R17 List – out & others
shifted to CT
try to merge
with ID-UAS

## Slide 47: Rel-17 Prioritization @SA#86
SA2 was tasked to break down all Rel-17 items into individual work tasks. SA2 will not perform any down-scoping.
SA#86 will prioritize the work tasks as listed by SA2. This means that items which are marked in/in* might be reduced in their scope and thus more Time Units will be available for other items.
For each item a moderator was named who will consolidate initial input from individual members on the prioritization the work tasks of that item. For this purpose a new SA_DRAFTS mailing list will be created.
Moderators will present their consolidated input at SA#86.
Individual members are requested to bring further input contributions to the SA#86 Rel-17 prioritization discussion.
For more details see endorsed papers SP-190949 and SP-190950.

## Slide 48: Example Work-Task Breakdown: 5GProSe
Work Task ID | Work Task Title | RAN Dependency | TU Estimate
WT#1 | ProSe architecture | No | 1
Public Safety and commercial related proximity services |  |  | 
WT#2.1 | direct discovery | Yes | 4
WT#2.2 | one-to-many direct communication | Yes | 1
WT#2.3 | one-to-one direct communication | Yes | 2
WT#2.4 | PC5 authorization and group management | Yes | 1.5
WT#2.5 | QoS support | Yes | 1.5
WT#2.6 | Path selection/switching | Yes | 1
WT#2.7 | Charging | No | 1.5
WT#2.8 | UE-to-UE relay mechanism | Yes | 3
Public Safety specific related proximity services |  |  | 
WT#3.1 | UE-to-Network Relay | Yes | 2
WT#3.2 | direct discovery out of coverage | Yes | 0.5
WT#3.3 | one-to-many direct communication out of coverage | Yes | 0.5
WT#3.4 | one-to-one direct communication out of coverage | Yes | 0.5

## Slide 49: Rel-17 Timeline
SA#82 agreed that Rel-17 should be assumed a 15 month release, whereby the final timeline will be discussed again in December 2019 at SA/RAN/CT#86.
15 month means that from the Rel-16 freeze date in a working group (e.g. SA2) the WG will be granted 15 months to work on Rel-17.
The assumption of 15 month currently puts the end of SA2 Rel-17 work to September 2020 (SA#89).
Based on the above it is assumed that CT will get 9 month afterwards to finish Rel-17 work, i.e. until SA#92 (June 2019), where Rel-17 then would be frozen.
Input contributions and comments were received at SA#85 (and previous SA meetings) already, indicating that some companies suggest 18 month for Rel-17.
From SA side the Rel-17 Timeline therefore is still open and will be, as agreed in SA#82, discussed and decided in December early during SA#86, in order to be able to give related guidance to RAN during SA/RAN joint session (planned for Wednesday December 11th).

## Slide 50: Release 18

## Slide 51: First Rel-18 SA1 Studies
Name | Acronym | Group | Compl. | tdoc | Rapporteur
Study on evolution of IMS multimedia telephony service | FS_MMTELin5G | S1 | 0% | SP-190836 | Yan Di, China Mobile, yandi@chinamobile.com
Study on sharing administrative configuration between interconnected MCX Service systems | FS_SACI_MCS | S1 | 0% | SP-190837 | Toobe, Jens, BDBOS
Study on Supporting of Railway Smart Station Services | FS_RAILSS | S1 | 0% | SP-190838 | Han, Andrew Min-gyu, Hansung University

## Slide 52: Cross-TSG Coordination

## Slide 53: Cross TSG Coordination
Joint SA/RAN/CT 1-day meetings were held during SA#84 and SA#85 mainly on the topic of Rel-17 planning, prioritization and content.
SA, SA1 and SA2 leadership and Rel-17 rapporteurs compiled input documents to the joint sessions in order to reflect forseeable Rel-17 requirements from and impacts on RAN (see RP-192212 for SA1 and RP-192213 for SA2).
For similar future sessions it is recommended that RAN rapporteurs/moderators undergo a similar effort, i.e. to summarize their forseeable impacts towards SA in separate documents, which then could be discussed at the joint meeting. This would allow for a much more focussed discussion and would also free time from the busy plenary agenda.
For SA#86 at least one joint SA/RAN session is planned, possibly more. This most likely depends on the time-line discussion.

## Slide 54: Improvements

## Slide 55: Improvements
The SA Chairman together with the CT and RAN TSG chairs started a new ongoing activity to collect, discuss and if possible realize improvements to 3GPP in order to
  Make 3GPP more accessible for new delegates;
  Allow for better engagement with outside (standards) bodies or MRPs;
  Identify possible problems within the existing 3GPP processes.
The following slides give an overview of four such activities which were started at SA#84 and SA#86
  Newcomer Orientation Session
  Mentoring
  Liaison Persons
  Traceability of Work Items
The latest items under discussion can also be found in SP-190843.

## Slide 56: Newcomer Orientation Session
A first Newcomer Orientation Session was held at SA/CT#85 (1 hour) during which basic 3GPP concepts were presented and new delegates had the chance to ask questions. 12 attendees categorized themselves as “newcomers”, for 6 of them SA#86 was either their first or second meeting.
The introduction slides in SP-190845 were presented.
Further Newcomer Orientation Sessions are currently discussed to be held at the November meetings in Reno.
Newcomer Orientation as well as Mentoring activities is currently driven by the TSG SA and TSG CT chairs. It is intended to gain initial experience with this new offer from 3GPP and then widen the scope also to RAN and more Working Groups.

## Slide 57: Mentoring
A new Mentoring Process was created. A group of interested delegates, either mentors or mentees (new delegates) met during SA#85 and discussed first steps on how such a mechanism could work.
It was agreed that for the moment no 1-to-1 association of mentees and mentors is needed, but that the mentors should rather act as a pool who can be addressed either directly at meetings, by mail or via a new mailing list.
A new mailing list 3GPP_MENTORING was created and is now active.

## Slide 58: 3GPP Mentors
Miikka Poikselkä
miikka.poikselka@nokia.com
SA, SA2
Adrian Neal
adrian.neal@vodafone.com
SA, CT, SA1, SA5, SA6
Kevin Holley kevin.holley@bt.com
SA, RAN, SA1
Gregory (Greg) Schumacher
gregory.schumacher@sprint.com
SA, SA1, SA3, SA3-LI

## Slide 59: Liaison Persons
3GPP SA intends to collect all currently active 3GPP Liaison persons to other bodies, so that delegates are aware whom to contact in case communication with such a body is needed.
3GPP SA also encourages 3GPP delegates who attend other bodies to consider becoming Liaison persons for that body, in order to strengthen and streamline the communication between 3GPP and that body.
It was proposed to collect the information about all Liaison persons (see following slides) on a 3GPP web site.

## Slide 60: Tasks of a Liaison Person
A Liaison person (short: Liaison) is a contact between 3GPP and a dedicated external (standards) body, sometimes even only to a specific working group of an external body.
A Liaison should
  attend both 3GPP meetings and meetings of the external body on a regular basis;
  give general information about 3GPP status on specific topics (e.g. status of a release, work items, which items are currently discussed on a specific issue) to the external body;
  support the liaison exchange between the external body and 3GPP;
  report regularly to 3GPP on the ongoing work in the external body.
Statements made by a Liaison in her/his role need to be an accurate representation of the current status of 3GPP work.
3GPP does not finance the attendance at or trips to meetings of other bodies

## Slide 61: 3GPP Liaisons
IETF
Internet Engineering Task Force
Lionel Morand
lionel.morand@orange.com
ITU-R
International Telecommunication Union – Radiocommunication Sector
Giovanni Romano (RAN/SA) giovanni.romano@telecomitalia.it
NGMN
Next Generation Mobile Networks
Kevin Holley kevin.holley@bt.com
ITU-T
International Telecommunication Union – Telecommunication Standardization Sector
Gregory (Greg) Schumacher
gregory.schumacher@sprint.com

## Slide 62: 3GPP Liaisons
IALA
International Association of Marine Aids to Navigation and Lighthouse Authorities
구현희 Hyounhee Koo
koo@synctechno.com
ESOA
EMEA Satellite Operator’s Association
Michel Cyril cyril.michel@thalesaleniaspace.com
MPEG (ISO/IEC JTC 1/SC 29/WG 11)
Moving Picture Experts Group
Primary LS to MPEG
David Singer (SA4) singer@apple.com
MPEG (ISO/IEC JTC 1/SC 29/WG 11)
Moving Pictures Expert Group
Secondary LS to MPEG
Mary-Luc Champel (SA) champelmaryluc@xiaomi.com

## Slide 63: 3GPP Liaisons
TCG
Trusted Computing Group
Alec Brusilovsky (SA3) alec.brusilovsky@interdigital.com

## Slide 64: Traceability of Work Items
During the 2nd 5G Vertical User Workshop (9-10 July 2019, Rome) a vertical industries requested 3GPP to make the progress and flow of work between stages, WGs and TSGs more visible and transparent.
3GPP currently doesn’t offer a tool or mechanism by which it could be determined how the different work items within a release are interconnected.
A revised Work Item template (SP-190952) was approved by SA, mandating rapporteurs to clearly list Work Items of earlier stages, of which requirements are covered in the current WI.
The information provided in the new WI template, if correctly filled out, would provide the base data to create charts as the one on this slide.
RAN SideLink
SA2 ProSe
CT1 ProSe
SA1 NCIS
SA1 ATRAC
SA1 REFEC
SA1 AVPROD
CTx ProSe

## Slide 65: Thank You!
Georg Mayer
3GPP SA Chairman
mail: georg.mayer@huawei.com
phone: +43 699 1900 5758