## Slide 1
Source: Samsung, Coolpad, Fiberhome, Oppo, Potevio, Xinwei, Xiaomi
NR Schedule
Agenda Item: 9.3, Document for: Decision
RP-161190
3GPP TSG RAN Meeting #72
Busan, Korea, 13 - 16 June 2016

## Slide 2: Introduction
Work on NR is progressing under schedule based on 2-phase approach (for normative work):
There is a proposal in RP-160812 to introduce an additional phase, i.e., 3-phase approach
In this contribution, we share our view on NR schedule and a possible way to move forward
 | Start | Completion | Note
Technology SI | March 2016 | March 2017 | 
Phase 1 WI | March 2017 | June 2018 | for early commercialization
Phase 2 WI | June 2018 | Dec 2019 | for fulfillment of all requirements and IMT-2020 submission
 | Schedule | Note
Phase A: Non-StandAlone (NSA) NR | ~ Dec 2017 (at latest March 2018) as part of Rel-15 | Priority on below and above 6GHz licensed bands, eMBB & low latency in UP, LTE as anchor with CP, connected to EPC
Phase B: StandAlone (SA) NR | ~ Sep 2018 (at latest Dec 2018) as a part of Rel-15 | All RAN functions for SA operation, 5G CN, NAS protocol
Phase C: Full IMT-2020 NR | ~ at latest Dec 2019 as Rel-16 | Full IMT-2020 NR

## Slide 3: Observations on 3-Phase Approach for NR Standardization
Motivation for the ‘3-phase approach’ is to expedite the 1st NR specs (by 6 months)
  Majority of L1/L2 features are common for non-standalone (NSA) and standalone (SA) and therefore, NSA NR in Dec 2017 is equivalent to 6-month (40%) reduction in work time without a reduction in work scope (compared to the existing schedule)
  Reduction in work time could limit the extent of key L1/L2 features introduced for NR
In order to expedite NR standardization, the first phase of NR in ‘3-phase approach’ will only support NSA while SA is to be supported in later phases
  Initial batch of NR UEs (only supporting NSA) will not be able to operate in a NR-only network (where there is no LTE support)
  Alternative would be to maintain LTE network as long as there are operational NSA-only NR UEs

## Slide 4: Comparison of Specification Work between SA and NSA (1/2)
L1 and L2 are common between SA and NSA
The main differences are in L3
  Mobility
  System information
  Paging
  RRC connection management
The work load of the L3 components listed above is not trivial, but it should be noted that workload for L1/L2 is much higher
Dual Connectivity (DC)-type mobility required for NSA is not that simple as having been thought (recognized in RAN2#94)
Tech Component |  | Stand-Alone | Non Stand-Alone
L1 | Waveform & Multiple Access | common | 
 | Frame Structure | common | 
 | Channel Coding | common | 
 | MIMO | common | 
 | L1 Procedures and Signaling | common | 
 | Physical Layer Channels | common | 
 | Physical Layer Signals | common | 
L2 | PDCP | common | 
 | RLC | common | 
 | Random Access | common | 
 | Scheduling | common | 
 | Other MAC functions | common | 
L3 | Measurement | common | 
 | UE states | common | 
 | Mobility | HO, idle mobility | DC type
 | System Information | MIB, SIB1,.. | MIB
 | Paging | Required | Not required
 | RRC Connection Management | Setup/reconfiguration | reconfiguration

## Slide 5: Comparison of Specification Work between SA and NSA (2/2)
Intensive discussion expected regarding how to support LTE – NR DC
  In case the LTE DC mechanism is reused, LTE specifications have to be continuously updated according to new releases of NR so that LTE MeNB understands new NR parameters
  Otherwise, new DC mechanism should be discussed from scratch
Dual connectivity between LTE nodes
Dual connectivity between LTE and NR

## Slide 6: Conclusion
While we recognize industry demand for expedited NR standardization, quality of NR specifications should not be compromised in the process
Proposal
  Maintain the current NR schedule, i.e., Phase 1 in June 2018 and Phase 2 in Dec 2019
  Specify the support for both SA and NSA in NR Phase 1 WI with priority on <6GHz and >6GHz licensed bands
  Other details of NR Phase 1 WI scope should be decided taking into account the SI outcome
  The remaining features that are required to fulfill NR requirements but are not supported in Phase 1 should be specified in NR Phase 2 WI

## Slide 7: Annex A: 3GPP Time Plans for New RAT’s
UMTS
Prep
“Tstart”
June 1997 (SMG#23)
Proposals are grouped
into concept groups
Study Item (SI)
Jan 1998
Agreed to submit both
W-CDMA & TD-CDMA
to ITU
Dec 1998
Start of 3GPP
WorkItem (WI)
March 2000
Rel-99 “completed”
Corrections
Oct 1991
ETSI TC SMG put
in charge of UMTS spec
Year 1
Year 2
Year 3
Year 4
Year 5
Sept 2003
Still many corrections
E.g. 25.331 RP 21 :
RP-030484,
RP-030485,
….
Year 6
June 2001
First trial
network
Launced
Sept 2002
First
europe
“Comm”
network
LTE
Dec 2001
First
Europe
Network
(no UE’s
yet)
Prep
March 2005
LTE workshop
Tokyo
Study Item (SI)
Sept 2006
RAN#33:
WG WI’s
started
June 2006
RAN#32:
SI
extended
WorkItem (WI)
March 2009
RAN#43
Rel-8
ASN.1 freeze
Sept 2007
Original Stage-3
finalisation date
(RP-060630)
Dec 2009
First
commercial
network
NR (current schedule)
Dec 2004
SID
Approved
(RP-040461)
Prep
Sept 2015
RAN
Workshop
Phoenix
Dec 2015
RAN
SID
Approved
RP-15227
June 2017
Expected
Finalisation
of SI
WorkItem (WI)
Study Item (SI)
June 2018
Rel-15
Finalisation
LTE: Very few corrections, but SI+WI 15 months delayed
UMTS: Years of delay due to corrections
NR: current schedule is already very tight
~3 years shorter than UMTS
~18 months shorter than LTE
Sept 2018
Rel-15
ASN.1 freeze
March 2017
Expected
Start of WI

## Slide 8: Thanks!