## Slide 1: SA WG3 Status report for FS_eNA_SEC_Ph3
Chang Liu
China Mobile

## Slide 2
The TR has 6 KIs and 14 solution, with 3 KIs don’t have any solution by now
November meeting:
  Solution completion(including evaluation and solving ENs)
  Add 5 solutions
  Some documents not treated, result in some KI don’t have solutions by now.
January meeting
  Last meeting to add solutions to the existing key issues.
  Add conclusions
  WID proposal
February meeting:
  Start normative work
  Finalize TR
April meeting:
  Normative work
May meeting:
  Finalize normative work
Overall plan
FS_eNA_Ph3_SEC Status

## Slide 3
Key Issues | Solutions | Solution status
#1: Protection of data and analytics exchange in roaming case | Solution #5: Access control and anonymization for data and analytics exchange in roaming | Evaluation
 | Solution #8: Protection of data and analytics exchange in roaming case | Evaluation
 | Solution #14: Protection of data and analytics exchange in roaming case using Secure Multi-party Computation | 4 ENs
#3: Security for AI/ML model storage and sharing | Solution #1: Authorization of AI/ML model retrieving | 1 EN
 | Solution #2: Authorization and Authentication of ML model transfer | 3 ENs Evaluation
 | Solution #3: AI/ML model authorization and retrieval | 1 ENs Evaluation
 | Solution #4: AI/ML model storage and sharing security | 2 ENs
TR Summary
FS_eNA_SEC_Ph3 Status

## Slide 4
Key Issues | Solutions | Solution status
 | Solution #7: Secured and authorized AI/ML model transfer and retrieval | 1 EN Evaluation
 | Solution #10: Authorization of AI/ML model sharing between different vendors and usage of one-time URLs | 4 ENs
 | Solution #11: Secured and authorized AI/ML model sharing between different vendors | 5 ENs
 | Solution #12: Secured and authorized AI/ML model sharing between different vendors | 3 ENs
 | Solution #13: Support authorization of AI/ML model sharing By NWDAF containing MTLF | 4 ENs
#4: Anomalous NF behaviour detection by NWDAF (from R17) | Solution #6: Anomalous NF behaviour detection by NWDAF | 
 | Solution #9: Anomalous NF behaviour event related data collection and anomalous NF detection | 5 ENs
TR Summary
FS_eNA_SEC_Ph3 Status

## Slide 5
Key Issues | Solutions | Solution status
#2:Authorization of selection of participant NWDAF instances in the Federated Learning group | No solutions | 
#5: KI on Security for NWDAF-assisted application detection | No solutions | 
#6: Key issues on Cyber-attack detection(from R17) | No solutions | 
TR Summary
FS_eNA_SEC_Ph3 Status

## Slide 6: FS_eNA_SEC_Ph3 status after SA3#107Adhoc-e
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
950021 | Study on security aspects of enablers for Network Automation for 5G - phase 3 | FS_eNA_SEC_Ph3 | Rel-18 | S3 | Mar-2023 | 35% | 60% | Current solutions completion and 5 new solutions added
General
  TR 33.738 v0.4.0 contains 6 key issues and 14 solutions
Dependencies:
  SA3 solution procedure need to be aligned with SA2.

## Slide 7: FS_eNA_SEC_Ph3 status after SA3#107Adhoc-e
Contentious Issue:
  May have some technical contentious issue on solution selection.
Focus for the Next Meeting :
  Current solution completion
  New solutions for current KIs(KI#2,KI#5,KI#6)
  Evaluations and conclusions
Overall Plan:
  See dedicated slide
Risks:
  No conclusions in SA3 109 meeting. The WID proposal is based on the TR conclusions, the WID proposal may be delayed if there is still no conclusion added in next meeting.