| Radiocommunication Study Groups |  |
| --- | --- |
| 28th Meeting of Working Party 5D Munich, Germany, 3 - 11 October 2017 |  |
| Attachment 7.4 to Document 5D/758 (Source: Document 5D/TEMP/388(Rev.1)) |  |
|  | 11 October 2017 |
|  | English only |
| Working Party 5D |  |
| Liaison statement to EXTERNAL ORGANIZATIONS on the schedule for updating Recommendation ITU-R M.2012 to Revision 4 |  |

Introduction

Working Party 5D (WP 5D) thanks the relevant External Organizations for their successful work in regards to completion of the draft Revision 3 of Recommendation ITU-R M.2012 – “Detailed specifications of the terrestrial radio interfaces of International Mobile Telecommunications-Advanced (IMT-Advanced)” which has now been sent to Study Group 5 and will be available as a published ITU-R Recommendation after its approval by the Member States.

WP 5D wishes to inform the relevant External Organizations that it is commencing the cycle for the development of the Revision 4 update of Recommendation ITU-R M.2012 and provides a detailed schedule for Revision 4 of Recommendation ITU-R M.2012.

Background

This liaison provides guidance to External Organizations regarding updates of the terrestrial radio interfaces in the development of Revision 4 of Recommendation ITU-R M.2012 “Detailed specifications of the terrestrial radio interfaces of International Mobile Telecommunications-Advanced (IMT-Advanced)”.

Confirmed meeting dates of WP 5D for 2018 and 2019 will be published on the ITU website (http://www.itu.int/events/upcomingevents.asp?sector=ITU-R&lang=en).

Procedure

The procedure outlined in document IMT-ADV/25 (Rev.2) Procedure for the development of draft revisions of Recommendation ITU-R M.2012 applies to the development of this Revision 4.

Schedule

For the Revision 4 update of Recommendation ITU-R M.2012 a completion date of the WP 5D meeting No. 33, currently planned for 9-13 December 2019 had previously been chosen. However, this completion date might need to be shifted to meeting No. 32 in July 2019.

It should be noted that 2019 is an ITU-R World Radio Conference (WRC) year and that WP 5D will hold only two ordinary meetings (with one meeting for preparation for CPM) in a 2019 instead of the usual three meetings per year. It also should be considered that WP 5D meeting No. 33 is planned after Study Group 5 (SG 5) meeting in late July 2019 so that the revised Recommendation will be considered in SG 5 meeting in 2020.

Thus, on an exceptional basis the timeframes associated with the announcement of this revision update cycle may be somewhat amended from the “placeholder” meetings designated in IMT-ADV/25 (Rev.2). In particular, WP 5D seeks the possibility to merge Y+2A and Y+2B meetings to one Y+2 meeting in order to send this revision to SG 5 meeting in late July 2019. Therefore, WP 5D would like to be informed by GCS Proponents and Transposing Organizations of existing RIT/SRIT if there are any difficulty on this special schedule (one Y+2 meeting at meeting No. 31 in October 2018). WP 5D will change the completion date to WP 5D meeting No. 32, currently planned for July 2019 if no difficulties are informed by GCS Proponents and Transposing Organizations and no new RIT/SRIT proposal is received at No. 29 meeting of WP 5D.

WP 5D announces that the first formal meeting in the meeting cycle (“Meeting Y”) of the update development of Revision 4 of Recommendation ITU-R M.2012 will be WP 5D meeting No. 29, which is scheduled for 31 January – 7 February 2018. It should be noted that the contribution deadline for WP 5D meeting No. 29 is also the cut-off date for the submission of new candidate RIT and SRIT proposals for inclusion in Revision 4.

The detailed timeline for the Revision 4 update of Recommendation ITU-R M.2012 which accommodates the currently planned/anticipated schedule of meetings for WP 5D and SG 5 through the 2018 and 2019 time frame and some milestone activities/actions may be found in Document IMT-ADV/30 Schedule for Revision 4 Update of Recommendation ITU-R M.2012. Document IMT-ADV/30 may be accessed at https://www.itu.int/md/R07-IMT.ADV-C-0029/en. For convenience it is also enclosed to this liaison as Attachment.

The dates in Document IMT-ADV/30 were developed considering not only the WP 5D and SG 5 dates but also with a view towards coordinating with the understood planned dates of the relevant External Organizations to the extent they were known.

Some adjustment of these dates might be required to accommodate availability of facilities at specific venues in conjunction with the scheduling of the ITU-R WP 5D and SG 5 meetings. Every effort will be made to keep these dates as listed. Please check the ITU website in case meeting details have changed (http://www.itu.int/events/monthlyagenda.asp?lang=en).

As appropriate Document IMT-ADV/30 will be updated to accommodate such date changes and further correspondence with the External Organization could be forthcoming throughout the update cycle as warranted by the circumstances.

External Organizations are encouraged to consult the ITU-R IMT-Advanced web page (http://www.itu.int/ITU-R/go/rsg5-imt-advanced/) which may be updated dynamically to provide additional information.

WP 5D kindly requests to GCS Proponents and Transposing Organizations of existing RIT/SRIT to provide their views on schedule in time for WP 5D meeting No. 29 (31 January – 7 February 2018).

WP 5D looks forward to the continued cooperation with the External Organizations in the on-going work on the IMT-Advanced terrestrial radio interfaces.

| Contact: Sergio BUONOMO Counsellor, ITU-R SG 5 | E-mail: sergio.buonomo@itu.int |
| --- | --- |

Attachment:	Document IMT-ADV/30 (Public access)

______________

____________________

Including currently identified GCS Proponents and Transposing Organizations for Rec. ITU-R M.2012.