| Radiocommunication Study Groups |  |
| --- | --- |
| Attachment 5.12 to Document 5D/532 (Source: Document 5D/TEMP/279) |  |
|  | 16 October 2013 |
|  | English only |
| Working Party 5D |  |
| Liaison statement to External Organizations on the schedule for updating Recommendation ITU-R M.2012 to Revision 2 |  |

Introduction

Working Party 5D thanks the relevant External Organizations for their successful work in regards to the course of action to be taken towards the completion and approval of Revision 1 of Recommendation ITU-R M.2012 – “Detailed specifications of the terrestrial radio interfaces of International Mobile Telecommunications-Advanced (IMT-Advanced)” which will be sent to Study Group 5 and will be available as a published ITU-R Recommendation.

Working Party 5D wishes to inform the relevant External Organizations that it is commencing the cycle for the development of the Revision 2 update of Recommendation ITU-R M.2012 and provides a detailed schedule for Revision 2 of Recommendation ITU-R M.2012.

Background

This liaison provides guidance to External Organizations regarding updates of the terrestrial radio interfaces in the development of Revision 2 of Recommendation ITU-R M.2012 “Detailed specifications of the terrestrial radio interfaces of International Mobile Telecommunications-Advanced (IMT-Advanced)”.

Confirmed meeting dates of WP 5D for 2014 and 2015 will be published on the ITU website (http://www.itu.int/events/upcomingevents.asp?sector=ITU-R&lang=en).

Procedure

The procedure outlined in Document IMT-ADV/25 “Procedure for the development of draft revisions of Recommendation ITU-R M.2012” applies to the development of Revision 2.  Document IMT-ADV/25 may be accessed at http://www.itu.int/md/R07-IMT.ADV-C-0025/en.

Schedule

For the Revision 2 update of Recommendation ITU-R M.2012 a completion date of the Working Party 5D meeting No. 22, currently planned for 10-17 June 2015 has been chosen.

It should be noted that 2015 is an ITU-R World Radio Conference (WRC) year and that WP 5D will hold only two meetings in a 2015 instead of the usual three meetings per year.  Thus, on an exceptional basis the timeframes associated with the announcement of this revision update cycle may be somewhat amended from the “placeholder” meetings designated in Document IMT-ADV/25.  In particular, the announcement of the start of the update cycle for Revision 2 is being made from the October 2013 meeting.

Working Party 5D announces that the first formal meeting in the meeting cycle (“Meeting Y”) of the update development of Revision 2 of Recommendation ITU-R M.2012 will be WP 5D meeting No.18, which is scheduled for 12-19 February 2014. It should be noted that the contribution deadline for WP 5D meeting No.18 is also the cut-off date for the submission of new candidate RIT and SRIT proposals for inclusion in Revision 2.

The detailed timeline for the Revision 2 update of Recommendation ITU-R M.2012 which accommodates the currently planned/anticipated schedule of meetings for WP 5D and Study Group 5 through the 2014 and 2015 time frame and some milestone activities/actions may be found in Document IMT-ADV/28 “Schedule for the Revision 2 Update of Recommendation ITU-R M.2012.  Document IMT-ADV/28 may be accessed at http://www.itu.int/md/R07-IMT.ADV-C-0028/en.  For convenience it is also enclosed to this liaison as Attachment.

The dates in Document IMT-ADV/28 were developed considering not only the WP 5D and Study Group 5 dates but also with a view towards coordinating with the understood planned dates of the relevant External Organizations to the extent they were known.

Some adjustment of these dates might be required to accommodate availability of facilities at specific venues in conjunction with the scheduling of the ITU-R WP 5D and Study Group 5 meetings. Every effort will be made to keep these dates as listed. Please check the ITU website in case meeting details have changed (http://www.itu.int/events/monthlyagenda.asp?lang=en).

As appropriate Document IMT-ADV/28 will be updated to accommodate such date changes and further correspondence with the External Organization could be forthcoming throughout the update cycle as warranted by the circumstances.

External Organizations are encouraged to consult the ITU-R IMT-Advanced web page (http://www.itu.int/ITU-R/go/rsg5-imt-advanced/) which may be updated dynamically to provide additional information.

Working Party 5D looks forward to the continued cooperation with the External Organizations in the on-going work on the IMT-Advanced terrestrial radio interfaces.

Contact:	Sergio Buonomo				E-mail: sergio.buonomo@itu.int
	Counsellor, ITU-R SG 5

Attachement: Document IMT-ADV/28 (PDF version)

_________________

____________________

Including currently identified GCS Proponents and Transposing Organizations for Recommendation ITU-R M.2012.