## General
Last Update: November-10, 2024
3GPP TSG CT WG1 Meeting #152 - C1-246383
3GPP TSG CT WG3 Meeting #138
3GPP TSG CT WG4 Meeting #126 - C4-245287
Orlando, US, 18th – 22nd November 2024
Source: | Apple
Title: | MASSS Work plan
Document for: | Information
Agenda Item: | 19.45
Work Item / Release: | Rel-19
Latest WID | CP-242259
Completion Status: | CT #105: 0%

## CT1
Number | Desciption | Related LS or other WG tdoc(s) | CT1 Impact | CT1 Spec | CT1 meeting | Volunteered company/delegate | Contribution(s) Meeting #, Tdoc # | Status | Comments
TR 23.700-54 Key Issue #2.1: MPQUIC steering functionality to steer, switch and split non-UDP traffic
1 | MA PDU Session and PDN connections updates due to MPQUIC-IP/MPQUIC-UDP/MPQUIC-E | S2-2409918 (Huawei, CableLabs, Samsung, Apple) | Yes | TS 24.501, TS 24.193 | CT1#152 | LGE
2 | Support for MPQUIC-IP and MPQUIC-E steering functionalities | S2-2411170 (Ericsson, Apple, CableLabs, Lenovo, Interdigital, Nokia, Charter Communications, Samsung, CATT) | Yes | TS 24.193 | CT1#152 | Nokia, Ericsson, Lenovo, LGE, Apple
3 | Updates of the PCC rules, ATSSS rules and N4 rules of the MPQUIC-IP/MPQUIC-UDP/MPQUIC-E functionalities | S2-2411233 (Huawei, CableLabs, Apple, Charter Communications, Samsung, Nokia, Ericsson) | Yes | TS 24.193 | CT1#152 | Nokia, LGE, Apple
4 | Support QoS of proxying IP and Ethernet in HTTP over MPQUIC | S2-2411177 (CATT, Huawei, ETRI) | Yes | TS 24.193 | CT1#152
5 | Support of additional MPQUIC functionalities and enabling correct header compression in NG-RAN | S2-2411173 (Samsung)
6 | Support of enabling correct header compression to be performed by NG-RAN | S2-2411232 (Samsung)

## CT3
Number | Desciption | Related LS or other WG tdoc(s) | CT3 Impact | CT3 Spec | CT3 meeting | Volunteered company/delegate | Contribution(s) Meeting #, Tdoc # | Status | Comments
TR 23.700-54 Key Issue #2.1: MPQUIC steering functionality to steer, switch and split non-UDP traffic
1 | MA PDU Session and PDN connections updates due to MPQUIC-IP/MPQUIC-UDP/MPQUIC-E | S2-2409918 (Huawei, CableLabs, Samsung, Apple)
2 | Support for MPQUIC-IP and MPQUIC-E steering functionalities | S2-2411170 (Ericsson, Apple, CableLabs, Lenovo, Interdigital, Nokia, Charter Communications, Samsung, CATT)
3 | Updates of the PCC rules, ATSSS rules and N4 rules of the MPQUIC-IP/MPQUIC-UDP/MPQUIC-E functionalities | S2-2411233 (Huawei, CableLabs, Apple, Charter Communications, Samsung, Nokia, Ericsson) | Yes | TS 29.512 | CT3#138
4 | Support QoS of proxying IP and Ethernet in HTTP over MPQUIC | S2-2411177 (CATT, Huawei, ETRI)
5 | Support of additional MPQUIC functionalities and enabling correct header compression in NG-RAN | S2-2411173 (Samsung)
6 | Support of enabling correct header compression to be performed by NG-RAN | S2-2411232 (Samsung)

## CT4
Number | Desciption | Related LS or other WG tdoc(s) | CT4 Impact | CT4 Spec | CT4 meeting | Volunteered company/delegate | Contribution(s) Meeting #, Tdoc # | Status | Comments
TR 23.700-54 Key Issue #2.1: MPQUIC steering functionality to steer, switch and split non-UDP traffic
1 | MA PDU Session and PDN connections updates due to MPQUIC-IP/MPQUIC-UDP/MPQUIC-E | S2-2409918 (Huawei, CableLabs, Samsung, Apple) | Yes | TS 29.571 | CT4#126 | Nokia, Huawei
2 | Support for MPQUIC-IP and MPQUIC-E steering functionalities | S2-2411170 (Ericsson, Apple, CableLabs, Lenovo, Interdigital, Nokia, Charter Communications, Samsung, CATT) | Yes | TS 29.244 | CT4#126 | Ericsson, Nokia, Huawei
3 | Updates of the PCC rules, ATSSS rules and N4 rules of the MPQUIC-IP/MPQUIC-UDP/MPQUIC-E functionalities | S2-2411233 (Huawei, CableLabs, Apple, Charter Communications, Samsung, Nokia, Ericsson) | Yes | TS 29.244 | CT4#126
4 | Support QoS of proxying IP and Ethernet in HTTP over MPQUIC | S2-2411177 (CATT, Huawei, ETRI)
5 | Support of additional MPQUIC functionalities and enabling correct header compression in NG-RAN | S2-2411173 (Samsung)
6 | Support of enabling correct header compression to be performed by NG-RAN | S2-2411232 (Samsung)

## LSs
Incoming liaision statements (LS)
Tdoc # | Topic | Reply LS | Related tdocs: CT1 meeting #; tdoc(s) # | Open issues | Comments
Outgoing liaision statements (LS)
Tdoc # | Topic | Reply LS | Related tdocs: CT1 meeting #; tdoc(s) # | Open issues | Comments