## Cover sheet
3GPP TSG-RAN5 Meeting #104 | [7 empty] | R5-244395
Maastricht, Netherlands, 19-23 Aug 2024
Agenda Item: | 7.5.2
Source: | Nokia
Title: | WP UE Conformance - Introduction of 900 MHz LTE band in the US
Work item code: | LTE_900MHz_US-UEConTest
Release: | Rel-18
Document for: | Information
RAN5 WP template v3.0.0
1. Introduction
At RAN#103, a RAN5 work item for UE Conformance - Introduction of 900 MHz LTE band in the US was approved in [1]. The purpose of the present document is to provide a work plan and status for RAN5 work related to specification of conformance testing for the new LTE FDD band 106. The work plan will be updated after each RAN5 meeting to give the status of the work item until the work is fully completed
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 85% (+85%)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
LTE (FR1) |  | 84.7% (+84.7%)
FR1 |  | 84.7% (+84.7%)
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | LTE
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1
[5 empty] | Completion | Number of new completed test cases | Number of new test cases
LTE
LTE Common
Common test environment | 36.508 | 100% (+100%) |  |  | 100% (+100%)
LTE RF/RRM
RF common parts | 36.521-1 | 100% (+100%) |  |  | 100% (+100%)
RF Rx test cases | 36.521-1 Rx | 100% (+100%) |  |  | 100% (+100%)
RF Tx test cases | 36.521-1 Tx | 100% (+100%) |  |  | 100% (+100%)
Applicability RF. Demod/QSI and RRM test cases | 36.521-2 | 100% (+100%) |  |  | 100% (+100%)
RRM test cases | 36.521-3 | 100% (+100%) |  |  | 100% (+100%)
LTE RAN and CN protocols
Protocol test cases | 36.523-1 | 100% (+100%) |  |  | 100% (+100%)
Applicability Protocol test cases | 36.523-2 | 100% (+100%) |  |  | 100% (+100%)
Test suites (TTCN) | 36.523-3 | 0% |  |  | 0%
5GS
5GS Common
NR RF/RRM
FR1 RF Tx test cases | 38.521-1 Tx | 100% (+100%) |  |  | 100% (+100%)
5 References
[1] RP-240096 | UE Conformance - Introduction of 900 MHz LTE band in the US
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | WP UE Conformance - Introduction of 900 MHz LTE band in the US | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | End of workplan columns. Note! Do not remove this column.
WI code |  | LTE_900MHz_US-UEConTest
WP Scope: |  | Introduce new LTE TDD band 106 to the conformance testing specifications
WP Resp: |  | Tuomo Säynäjäkangas |  |  | tuomo.saynajakangas@nokia.com | [5 empty] | WP item completion |  |  | LTE
TS Resp: |  | <TS responsible if a new TS is involved> |  |  | <Email to TS responsible>
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | LTE |  | FR1
84.7% (+84.7%)
31 (+31)
0.3 (+0.3)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
LTE
LTE Common
TS 36.508: Common test environment
1 |  | 36.508 | 4.3.1.1 | Test frequencies | Addition of test frequencies for B106 | Nokia | RAN5#103 (May-24) | R5-242384 |  | 0.01 | 100% (+100%) | 100% (+100%) |  | 100%
2 |  | 36.508 | 6.2.3 | Test frequencies for signalling test | Addition of 3 MHz channel BW and signaling test frequencies for B106 | Nokia | RAN5#103 (May-24) | R5-242385 |  | 0.01 | 100% (+100%) | 100% (+100%) |  | 100%
LTE RF/RRM
TS 36.521-1: RF test cases - Common parts (general clauses, Annexes)
3 |  | 36.521-1 | 5.2 | Operating bands | Addition of LTE FDD band 106 | Nokia | RAN5#103 (May-24) | R5-242386 |  | 0.01 | 100% (+100%) | 100% (+100%) |  | 100%
4 |  | 36.521-1 | 5,2E | Operating bands for UE category 0, UE category M1, M2 and UE category 1bis | Addition of B106 into UE category M1 and M2 | Nokia | RAN5#103 (May-24) | R5-242386 |  | 0.01 | 100% (+100%) | 100% (+100%) |  | 100%
5 |  | 36.521-1 | 5,2F | Operating bands for UE category NB1 and NB2 | Addition of B106 into UE category NB1 and NB2 | Nokia | RAN5#103 (May-24) | R5-242386 |  | 0.01 | 100% (+100%) | 100% (+100%) |  | 100%
6 |  | 36.521-1 | 5.3 | TX–RX frequency separation | Addition of TX–RX frequency separation for B106 | Nokia | RAN5#103 (May-24) | R5-242386 |  | 0.01 | 100% (+100%) | 100% (+100%) |  | 100%
7 |  | 36.521-1 | 5.4.2.1 | Channel bandwidths per operating band | Addition of channel BWs 1.4 and 3 MHz for FDD B106 | Nokia | RAN5#103 (May-24) | R5-242386 |  | 0.01 | 100% (+100%) | 100% (+100%) |  | 100%
8 |  | 36.521-1 | 5.4.4 | Carrier frequency and EARFCN | Addition of EARFCNs for FDD B106 | Nokia | RAN5#103 (May-24) | R5-242386 |  | 0.01 | 100% (+100%) | 100% (+100%) |  | 100%
TS 36.521-1: RF test cases - Tx
9 |  | 36.521-1 Tx | 6.2.2 | UE Maximum Output Power | Update conformance and test requirements to introduce B106 | Nokia | RAN5#103 (May-24) | R5-242387 |  | 0.01 | 100% (+100%) | 100% (+100%) |  | 100%
10 |  | 36.521-1 Tx | 6.2.2EA | UE Maximum Output Power for UE category M1 | Update conformance and test requirements to introduce B106 | Nokia | RAN5#103 (May-24) | R5-242387 |  | 0.01 | 100% (+100%) | 100% (+100%) |  | 100%
11 |  | 36.521-1 Tx | 6.2.2EC | UE Maximum Output Power for UE category M2 | Update conformance and test requirements to introduce B106 | Nokia | RAN5#103 (May-24) | R5-242387 |  | 0.01 | 100% (+100%) | 100% (+100%) |  | 100%
12 |  | 36.521-1 Tx | 6.2.2F | UE Maximum Output Power for category NB1 and NB2 | Update conformance and test requirements to introduce B106 | Nokia | RAN5#103 (May-24) | R5-242387 |  | 0.01 | 100% (+100%) | 100% (+100%) |  | 100%
13 |  | 36.521-1 Tx | 6.6.3.2 | Spurious emission band UE co-existence | Update conformance and test requirements to introduce B106 | Nokia | RAN5#103 (May-24) | R5-242387 |  | 0.01 | 100% (+100%) | 100% (+100%) |  | 100%
TS 36.521-1: RF test cases - Rx
14 |  | 36.521-1 Rx | 7.3 | Reference sensitivity level | Update conformance and test requirements to introduce B106 | Nokia | RAN5#103 (May-24) | R5-242388 |  | 0.01 | 100% (+100%) | 100% (+100%) |  | 100%
15 |  | 36.521-1 Rx | 7,3EA | Reference sensitivity level for UE category M1 | Update conformance and test requirements to introduce B106 | Nokia | RAN5#103 (May-24) | R5-242388 |  | 0.01 | 100% (+100%) | 100% (+100%) |  | 100%
16 |  | 36.521-1 Rx | 7,3EC | Reference sensitivity level for UE category M2 | Update conformance and test requirements to introduce B106 | Nokia | RAN5#103 (May-24) | R5-242388 |  | 0.01 | 100% (+100%) | 100% (+100%) |  | 100%
17 |  | 36.521-1 Rx | 7.6.1 | In-band blocking | Update conformance and test requirements to introduce B106 | Nokia | RAN5#103 (May-24) | R5-242388 |  | 0.01 | 100% (+100%) | 100% (+100%) |  | 100%
18 |  | 36.521-1 Rx | 7.6.2 | Out-of-band blocking | Update conformance and test requirements to introduce B106 | Nokia | RAN5#103 (May-24) | R5-242388 |  | 0.01 | 100% (+100%) | 100% (+100%) |  | 100%
TS 36.521-2: Applicability for RF, Demod/CSI reporting and RRM test cases
19 |  | 36.521-2 | A.4.3 | Baseline Implementation Capabilities | Add test case applicability statements for B106 introduced for 36.521-1 | Nokia | RAN5#103 (May-24) | R5-242389 |  | 0.01 | 100% (+100%) | 100% (+100%) |  | 100%
20 |  | 36.521-2 | A.4.7 | Category M1 UE Centre Frequency Implementation | Add B106 | Nokia | RAN5#103 (May-24) | R5-242389 |  | 0.01 | 100% (+100%) | 100% (+100%) |  | 100%
TS 36.521-3: RRM test cases
21 |  | 36.521-3 | 3.5.1 | Group of bands | Specify band group for B106 introduced for 36.521-1 | Nokia | RAN5#103 (May-24) | R5-242390 |  | 0.01 | 100% (+100%) | 100% (+100%) |  | 100%
LTE RAN and CN protocols
TS 36.523-1: Protocol test cases
Idle Mode
TBD |  | 36.523-1 |  |  | No changes needed |  |  |  | No changes needed | TBD
Layer 2
TBD |  | 36.523-1 | 7.1.5.1 | Inter-TTI PUSCH hopping by uplink grant | Add less than 5MHz BW into Bandwidth dependent parameters | Nokia | RAN5#103 (May-24) | R5-242392 | Add 3MHz into Table 7.1.5.1.3.2-2. Information in hopping bits as "1", Execution Counter K as "1". | 0.01 | 100% (+100%) | 100% (+100%) |  | 100%
TBD |  | 36.523-1 | 7.1.7.1 | DL-SCH transport block size selection | Add less than 5MHz BW into Bandwidth dependent parameters | Nokia | RAN5#103 (May-24) | R5-242392 | Add 3 MHz into Table 7.1.7.1.1.3.2-2a: Bandwidth Dependent Parameters (+ related tables in sub clauses). | 0.01 | 100% (+100%) | 100% (+100%) |  | 100%
RRC
TBD |  | 36.523-1 | 8.3.4.5 | Inter-frequency E-UTRAN FDD - FDD / CSG Proximity Indication | Add less than 5MHz BW into Cell specific test parameters | Nokia | RAN5#103 (May-24) | R5-242392 | Add 3 MHz into Table A.8.21-3: Cell specific test parameters for E-UTRAN FDD-FDD inter frequency cell proximity detection test case. | 0.01 | 100% (+100%) | 100% (+100%) |  | 100%
NAS
TBD |  | 36.523-1 |  |  | No changes needed |  |  |  | No changes needed | TBD
TS 36.523-2: Applicability for Protocol test cases
TBD |  | 36.523-2 | A.4.3.1 | RF Baseline Implementation Capabilities | Add test case applicability statements for the new test cases introduced in 36.521-1 | Nokia | RAN5#103 (May-24) | R5-242393 |  | 0.01 | 100% (+100%) | 100% (+100%) |  | 100%
TS 36.523-3: Protocol test suites (TTCN)
TBD |  | 36.523-3 | 7.1.1 | FDD candidates selection | Add less than 5MHz BW into PDCCH Candidate Selection. | MCC TF160 | RAN5#105 (Nov-24) |  | Add 3 MHz and new Table 7.1.1.1-5: CCE Start indices (m' & m'') to be used for default C-RNTI (3 MHz). | 0.01 | 0% | 0% |  | 0%
TBD |  | 36.523-3 | 7.3.3 | General DL scheduling scheme | Add less than 5MHz BW as scheduling scheme. | MCC TF160 | RAN5#105 (Nov-24) |  | Add 3 MHz. | 0.01 | 0% | 0% |  | 0%
TBD |  | 36.523-3 | 7.7.2 | Scheduling information | Add less than 5MHz BW scheduling information. | MCC TF160 | RAN5#105 (Nov-24) |  | Add 3 MHz. | 0.01 | 0% | 0% |  | 0%
TBD |  | 36.523-3 | 11.1 | E-UTRA single technology | Add guidelines for test execution for B106 | MCC TF160 | RAN5#105 (Nov-24) |  |  | 0.01 | 0% | 0% |  | 0%
TBD |  | 36.523-3 | 11.2 | E-UTRA - UTRA - GERAN | Add guidelines for test execution for B106 | MCC TF160 | RAN5#105 (Nov-24) |  |  | 0.01 | 0% | 0% |  | 0%
5GS
5GS Common
NR RF/RRM
TS 38.521-1: FR1 RF test cases - Tx
TBD |  | 38.521-1 Tx | 6.5.3.2 | Spurious emission for UE co-existence | Update conformance requirements to protect B106 from spurious emissions of other applicable regional bands | Nokia | RAN5#103 (May-24) | R5-242391 |  | 0.01 | 100% (+100%) | 100% (+100%) |  | 100%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.