3GPP TSG RAN meeting #105										RP-241844

Melbourne, Australia, September 9-12, 2024

## Status Report to TSG

Agenda item:			9.2.4

| WI / SI Name | Study on spatial channel model for demodulation performance requirements for NR |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| included in this status report | Study Item: Yes | Core part: N/A | Performance part: N/A |  | Testing part: N/A |
| Acronym | FS_NR_demod_SCM |  |  |  |  |
| Unique ID | 1040100 |  |  |  |  |
| TSG Tdoc of latest approved WI/SI description (if any) | RP-241610 |  |  |  |  |
| Target Completion Date (indicate if changed) | Study Item: 06/2025 | Core part: N/A | Performance part: N/A | Testing part: N/A |  |
| Overall Completion level | Study Item: 15 % | Core part: N/A | Performance part: N/A | Testing part: N/A |  |

Source:

| Leading WG |  | RAN4 |
| --- | --- | --- |
| Rapporteur | Name | Alexander Hamilton |
|  | Company | Nokia |
|  | Email | Alexander.hamilton@nokia.com |

## 1	Work plan related evaluation

| Do you want to modify the time budget for this WI/SI compared to what was endorsed at the last RAN meeting? | No |
| --- | --- |

## 2.	Detailed progress in RAN WGs since last TSG meeting (for all involved WGs)

## 2.1	RAN1

#### 2.1.1	Agreements

#### 2.1.2	Remaining Open issues

## 2.2	RAN2

#### 2.2.1	Agreements

#### 2.2.2	Remaining Open issues

## 2.3	RAN3

#### 2.3.1	Agreements

#### 2.3.2	Remaining Open issues

## 2.4	RAN4

#### 2.4.1	Agreements

##### 2.4.1.1	Agreements from RAN4#112

Work Plan

Agreement:

As per below

| Meeting No. | Date | Details |
| --- | --- | --- |
| RAN4#112 | August 2024 | Identify Existing Limitations (Phase 1): Scenario Discussed and early Alignment Initial Scenario Configuration Alignment Explore Modelling Approaches (Phase 2): Potential approaches to channel modelling discussed |
| RAN #105 (September 2024) |  |  |
| RAN4#112-bis | October 2024 | Identify Existing Limitations (Phase 1): Scenarios agreed Explore Modelling Approaches (Phase 2): Initial simulation parameter alignment Considered channel model alignment |
| RAN4#113 | November 2024 | Explore Modelling Approaches (Phase 2): Simulation parameters agreed Develop Test Methodology (Phase 3): Testability Discussions Initial simulations Document Conclusions (Phase 4): Draft TR structure agreed Work split agreed |
| RAN #106 (December 2024) |  |  |
| RAN4#114 | Feb 2025 | Develop Test Methodology (Phase 3): Simulation Alignment Document Conclusions (Phase 4): Initial discussion on potential conclusions Draft TPs Draft big pCR |
| RAN #107 (March 2025) |  |  |
| RAN4#114-bis | April 2025 | Develop Test Methodology (Phase 3): Further Simulation Alignment Document Conclusions (Phase 4): Draft conclusions Draft TPs Draft big pCR |
| RAN4#115 | May 2025 | Document Conclusions (Phase 4): big pCR |
| RAN #108 (June 2025) |  |  |

Tap Delay Line Parameters

Agreement:

The following Legacy TDL models for comparison:

- Option 1: TDLC 300-100 ULA Low

- Option 2: TDLA 30-10 ULA Low

- FFS: TDLC 300-100 medA

UE Antenna Configuration

Agreement:

UE Antenna Configuration, for DL, for 38.827 : Cross Pol (1, n/2, 2), i.e. [ + + + +].

Where ‘n’ is number of Rx with half lambda spacing, with omni antenna element radiation pattern.

Comparison Approach

Agreement:

In Priority Order:

- SU-MIMO, with a single receiver implementation (as per test cases for SU-MIMO) – For comparison and alignment

- MU-MIMO, based on the 4x4 existing intra-cell inter-user interference requirements – For comparison

Other cases for comparison not precluded.

#### 2.4.2	Remaining Open issues

##### 2.4.1.1	Open Issues following RAN4#112

Frequency Ranges for Study

Way Forward:

RAN4 shall focus on FR1 conducted test as priority

Test Cases for SU-MIMO

Way Forward:

As a starting point:

- 8Rx:

  - 8 Layer (8T8R)

    - 8 Layer PDSCH TPUT (Options on precoder choice to be presented at next meeting)

    - FFS: 8 Layer PMI Reporting (CB Type 1, single panel)

  - FFS: 4 Layer (4T8R)

    - FFS: 4 Layer PDSCH TPUT

    - FFS: 4 Layer PMI Reporting (CB Type 1, single panel)

- FFS: 4Rx:

  - FFS: 4 Layer (4T4R)

    - FFS: 4 Layer PDSCH TPUT

Interested companies to bring views at the next meeting (for comparison and initial alignment).

Test Cases for MU-MIMO

Way Forward:

Companies to bring proposals at the next meeting.

TDL Model Extensions

Way Forward:

Open issue needs further discussion, 2 contributions provided during RAN4 #112, interested companies to review and provide views at next meeting.

Cluster Delay Model

Way Forward:

Prioritise 38.827 UMa-CDL-C for initial comparison and alignment.

FFS on parameters.

Other options not precluded.

Impact on Testing Duration:

Way Forward:

Open issue needs further discussion.

Definition of New Requirements:

Way Forward:

Open issue needs further discussion.

## 2.5	RAN5

#### 2.5.1	Agreements

#### 2.5.2	Remaining Open issues

#### 2.5.3	Remaining Open issues with cross-WG dependencies

## 2.6	RAN6

#### 2.6.1	Agreements

#### 2.6.2	Remaining Open issues

## 3.	Detailed progress in SA/CT WGs since last TSG meeting

## 3.1	SAx/CTs

#### 3.1.1	Agreements with cross-TSG impacts

#### 3.1.2	Remaining Open issues with cross-TSG impacts

## 4.	References

From RAN4#112

- RP-241610	SID, Study on spatial channel model for demodulation performance requirements	Nokia, BT plc

- R4-2411557	Scenarios and Requirements for Spatial Channel Modelling	BT plc

- R4-2411044	Work Plan for Spatial Channel Model Study Item	Nokia

- R4-2412320	General view on SCM for demodulation	Ericsson

- R4-2412321	Discussion on SCM methodology	Ericsson

- R4-2412322	Simulation results for SCM	Ericsson

- R4-2412328	Discussion on Spatial Channel Modelling	MediaTek inc.

- R4-2413272	On Rel-19 spatial channel model for demodulation performance requirements	Keysight Technologies UK Ltd

- R4-2413056	Initial Considerations on the study on SCM for demodulation performance requirements	Qualcomm Incorporated

- R4-2412793	Discussion on spatial channel model for demodulation performance requirements	ZTE Corporation, Sanechips

- R4-2412762	Overviews on spatial channel model for demodulation requirements	Huawei,HiSilicon

- R4-2411119	Discussion on spatial channel modelling methodology	CATT

- R4-2411300	Discussion on Spatial Channel Model for Demodulation Performance Requirements	Nokia

- R4-2411301	Simulation Results and CDL Implementation for Spatial Channel Model for Demodulation Performance Requirements	Nokia

- R4-2411390	On Spatial Channel Modeling for Demodulation Requirements	Apple

- R4-2412535	Initial view on spatial channel modelling SI	Samsung

- R4-2413427	Topic summary for [112][327] NR_SCM	Moderator (Nokia)

- R4-2413568	Offline meeting minutes for [112][327] NR_SCM	Nokia

- R4-2413606	Way Forward for [112][327] NR_SCM	Nokia