## Cover sheet
3GPP TSG-RAN WG5 Meeting #105 | [7 empty] | R5-246667
Orlando, United States, 18th Nov 2024 - 22nd Nov 2024
Agenda Item: | 7.5.2
Source: | CMCC
Title: | WP UE Conformance - Air-to-ground network for NR
Work item code: | NR_ATG-UEConTest
Release: | Rel-18
Document for: | Information
RAN5 WP template v3.0.0
1. Introduction
At the RAN#102 meeting in December 2023 the Rel-18 RAN5 work item for UE Conformance of Air-to-ground network for NR was approved [1]. The purpose of present document is to provide a work plan for the RAN5 work item to introduce the Rel-18 Air-to-ground network for NR into RAN5 test specifications. The work plan is updated after each RAN5 meeting to give the status of the work item. Section 2 gives an overview of the work item status. The work sheet 'WP' shows the status for each impacted/newly introduced test cases.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 64% (+6%) | 3 (+3) | 35 (+8)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) (FR1) |  | 63.8% (+6.4%) | 3 (+3) | 35 (+8)
FR1 |  | 63.8% (+6.4%) | 3 (+3) | 35 (+8)
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1
[5 empty] | Completion | Number of new completed test cases | Number of new test cases
LTE
LTE Common
Common test environment | 36.508
UE specific test functions | 36.509
LTE RF/RRM
RF common parts | 36.521-1
RF Rx test cases | 36.521-1 Rx
RF Tx test cases | 36.521-1 Tx
RF Demod test cases | 36.521-1 Demod
Applicability RF. Demod/QSI and RRM test cases | 36.521-2
RRM test cases | 36.521-3
Test Tolerances analysis RRM test cases | 36.903
Test Tolerances analysis receiver test cases | 36.904
Test Point analysis receiver and transmitter test cases | 36.905
LTE RAN and CN protocols
Protocol test cases | 36.523-1
Applicability Protocol test cases | 36.523-2
Test suites (TTCN) | 36.523-3
5GS
5GS Common
Common test environment | 38.508-1 | 100% |  |  | 100%
Common ICS | 38.508-2 | 100% |  |  | 100%
UE specific test functions | 38.509
NR RF/RRM
FR1 RF common parts | 38.521-1 | 64.9% (+8.1%) | 3 (+3) | 33 (+8) | 64.9% (+8.1%) | 3 (+3) | 33 (+8)
FR1 RF Tx test cases | 38.521-1 Tx
FR1 RF Rx test cases | 38.521-1 Rx
FR2 RF common parts | 38.521-2
FR2 RF Tx test cases | 38.521-2 Tx
FR2 RF Rx test cases | 38.521-2 Rx
FR1 and FR2 Interworking operation with other radios RF common parts | 38.521-3
FR1 and FR2 Interworking operation with other radios RF Tx test cases | 38.521-3 Tx
FR1 and FR2 Interworking operation with other radios RF Rx test cases | 38.521-3 Rx
RF Demod/QSI test cases | 38.521-4 | 0% | 0 | 1 | 0% | 0 | 1
RRM test cases | 38.533 | 0% | 0 | 1 | 0% | 0 | 1
Applicability RF. Demod/QSI and RRM test cases | 38.522 | 70% (-0%) |  |  | 70% (-0%)
Test Tolerances analysis RRM and RF Rx test cases | 38.903 | 0% |  |  | 0%
Test Point analysis receiver and transmitter test cases | 38.905 | 70% |  |  | 70%
5GS RAN and CN protocols
Protocol test cases | 38.523-1
Applicability Protocol test cases | 38.523-2
Test suites (TTCN) | 38.523-3
UE Positioning
UE Positioning Min. Performance test cases | 37.571-1
UE Positioning Protocol test cases | 37.571-2
Applicability and ICS UE Positioning test cases | 37.571-3
UE Positioning Test sutes (TTCN) | 37.571-4
UE Positioning test scenarios and assistance data | 37.571-5
IMS
IMS over LTE protocol test cases | 34.229-1
IMS over 5GS protocol test cases | 34.229-5
Applicability and ICS IMS test cases | 34.229-2
IMS Test suite (TTCN) | 34.229-3
Mission Critical Services
MC Common test environment | 36.579-1
MCPTT UE test cases | 36.579-2
MC Server Application test cases | 36.579-3
Applicability and ICS MC test cases | 36.579-4
MC Test suite (TTCN) | 36.579-5
MC Video UE test cases | 36.579-6
MC Data UE test cases | 36.579-7
5 References
[1] RP-233412 | New WID on UE Conformance - Air-to-ground network for NR
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | WP UE Conformance - Air-to-ground network for NR | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_ATG-UEConTest
WP Scope: |  | The purpose of this present document is to provide a work plan for the RAN5 work item UE Conformance Test Aspects for Air-to-ground network for NR comprising the necessary updates to existing clauses/test cases and new clauses/test cases as appropriate, with the aim of provision of conformance testing to reflect the relevant core and performance requirement (relevant core spec WIs indicated in the WID).
WP Resp: |  | Dan Song, CMCC |  |  | songdan@chinamobile.com | [5 empty] | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp: |  | n/a |  |  | n/a
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR1
63.8% (+6.4%)
63 (+9)
53.7 (+9)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
1 |  | 38.508-1 | 3.3 | Abbreviations | Introduction of Abbreviations for "ATG" into cl 3.3 | CMCC | RAN5#107 (May-25) | R5-241926 | CMCC Dan Song <songdan@chinamobile.com> A | 0.5 | 100% | 100% |  | 100%
2 |  | 38.508-1 | 4 | Common test environments | Introduction of General Test Environment for Rel-18 NR ATG UE | CMCC | RAN5#107 (May-25) | R5-244488 | CMCC Dan Song <songdan@chinamobile.com> Common test environment for ATG is pending since R18 ASN.1 has not been frozen until Jun 2024. Thus, this part will be updated in RAN5#104 meeting in Aug 2024 | 1 | 100% | 100% |  | 100%
3 |  | 38.508-1 | 5 | Test environments for RF test | Introduction of RF Test Environment for Rel-18 NR ATG UE | CMCC | RAN5#107 (May-25) | R5-241919 R5-244485 | CMCC Dan Song <songdan@chinamobile.com> IE name in SIB22 for ATG has been added with bracket since R18 ASN.1 has not been frozen until Jun 2024. Thus, this part will be updated in RAN5#104 meeting in Aug 2024 | 1 | 100% | 100% |  | 100%
4 |  | 38.508-1 | 7 | Test environments for RRM tests | Introduction of RRM Test Environment for Rel-18 NR ATG UE | CMCC | RAN5#107 (May-25) | R5-241920 R5-244486 | CMCC Dan Song <songdan@chinamobile.com> IE name in SIB22 for ATG has been added with bracket since R18 ASN.1 has not been frozen until Jun 2024. Thus, this part will be updated in RAN5#104 meeting in Aug 2024 | 1 | 100% | 100% |  | 100%
TS 38.508-2: Common ICS
|  | 38.508-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
5 |  | 38.508-2 | A.4.1 | UE Implementation Types | Introduction of common Implementation Conformance Statements for ATG UE into Table A.4.1-1 | CMCC | RAN5#107 (May-25) | R5-241715 | CMCC Dan Song <songdan@chinamobile.com> | 1 | 100% | 100% |  | 100%
NR RF/RRM
TS 38.521-1: FR1 RF test cases - Common parts (general clauses, Annexes)
|  | 38.521-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
6 |  | 38.521-1 | 2 | References | Add "TS 38.104" into the "Reference" Section as per R4-2321919. | CMCC | RAN5#107 (May-25) | R5-240049 | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 100% | 100% |  | 100%
|  | 38.521-1 | 3 | Definitions, symbols and abbreviations | [5 empty] | 0
7 |  | 38.521-1 | 3.1 | Definitions | Add "ATG UE" into "Definitions" as per R4-2321919 | CMCC | RAN5#107 (May-25) | R5-240049 R5-243906 R5-244477 | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 100% | 100% |  | 100%
8 |  | 38.521-1 | 3.2 | Symbols | Add "PMaxOutputPower" into "Definitions" as per R4-2321919 | CMCC | RAN5#107 (May-25) | R5-240049 R5-243906 R5-244477 | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 100% | 100% |  | 100%
9 |  | 38.521-1 | 3.3 | Abbreviations | Add "ATG" and "TAB" into "Abbreviations" as per R4-2321919 | CMCC | RAN5#107 (May-25) | R5-240049 | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 100% | 100% |  | 100%
10 |  | 38.521-1 | 4.3 | Specification suffix information | Update cl."Specification suffix information" for ATG as per R4-2321919 | CMCC | RAN5#107 (May-25) | R5-240049 | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 100% | 100% |  | 100%
11 |  | 38.521-1 | 5.2J | Operating band for ATG | Introduce Operating band for ATG UE | CMCC | RAN5#107 (May-25) | R5-240049 | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 100% | 100% |  | 100%
TS 38.521-1: FR1 RF test cases - Tx
12 |  | 38.521-1 | 6.1J | General | Introduce general description for ATG UE Tx test cases | CMCC | RAN5#107 (May-25) | R5-242030 R5-244478 | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 100% | 100% |  | 100%
|  | 38.521-1 | 6.2J | Transmitter power for ATG | [5 empty] | 0
13 | Y | 38.521-1 | 6.2J.1 | UE maximum output power for ATG | Introduce UE maximum output power test case for ATG UE | CMCC | RAN5#106 (Feb-25) | R5-241751 R5-241764 R5-243037 R5-246055 R5-246061 R5-247941 | CMCC Dan Song <songdan@chinamobile.com> MU/TT are pending for antenna/TAB connectors more than 2. Applicability is incomplete | 1 | 90% | 90% |  | 90%
14 | Y | 38.521-1 | 6.2J.2 | Configured transmitted power for ATG | Introduce Configured transmitted power test case for ATG UE | CMCC | RAN5#106 (Feb-25) | R5-241752 R5-241764 R5-243037 R5-246056 R5-246061 R5-247941 | CMCC Dan Song <songdan@chinamobile.com> MU/TT are pending for antenna/TAB connectors more than 2. Applicability is incomplete | 1 | 90% | 90% |  | 90%
|  | 38.521-1 | 6.3J | Output power dynamics for ATG | [5 empty] | 0
15 | Y | 38.521-1 | 6.3J.1 | Minimum output power for ATG | Introduce Minimum output power test case for ATG UE | CAICT | RAN5#106 (Feb-25) | R5-241756 R5-246058 R5-246062 R5-247941 | CAICT Yufeng Zhang zhangyufeng@caict.ac.cn MU/TT are pending for antenna/TAB connectors more than 2. Applicability is incomplete | 1 | 90% | 90% |  | 90%
16 | Y | 38.521-1 | 6.3J.2 | Transmit OFF power for ATG | Introduce Transmit OFF power test case for ATG UE | CAICT | RAN5#106 (Feb-25) | R5-241755 R5-246058 R5-246062 R5-247939 R5-247941 | CAICT Yufeng Zhang zhangyufeng@caict.ac.cn MU/TT are pending Applicability is incomplete | 1 | 80% | 80% |  | 80%
|  | 38.521-1 | 6.3J.3 | Transmit ON/OFF time mask for ATG | [5 empty] | 0
58 |  | 38.521-1 | 6.3J.3.0 | General | Introduce General description of Transmit ON/OFF time mask for ATG UE | CMCC | RAN5#105 (Nov-24) | R5-247735 | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> | 1 | 100% (+100%) | 100% (+100%) |  | 100%
17 | Y | 38.521-1 | 6.3J.3.1 | General ON/OFF time mask for ATG | Introduce General ON/OFF time mask test case for ATG UE | CMCC | RAN5#106 (Feb-25) |  | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> | 1 | 0% | 0% |  | 0%
52 | Y | 38.521-1 | 6.3J.3.2 | Transmit power time mask for slot and short or subslot boundaries for ATG | Introduce Transmit power time mask for slot and short or subslot boundaries test case for ATG UE | CMCC | RAN5#105 (Nov-24) | R5-247736 | No test case details are specified. CMCC Luyang Zhao <zhaoluyang@chinamobile.com> | 1 | 100% (+100%) | 100% (+100%) |  | 100%
53 | Y | 38.521-1 | 6.3J.3.3 | PRACH time mask for ATG | Introduce PRACH time mask test case for ATG UE | Ericsson | RAN5#106 (Feb-25) | R5-247718 R5-247720 R5-247717 R5-247816 | Ericsson Håkan Grunditz <hakan.grunditz@ericsson.com> | 1 | 90% (+90%) | 90% (+90%) |  | 90%
54 | Y | 38.521-1 | 6.3J.3.4 | SRS time mask for ATG | Introduce SRS time mask test case for ATG UE | Ericsson | RAN5#106 (Feb-25) | R5-247719 R5-247720 R5-247717 R5-247816 | Ericsson Håkan Grunditz <hakan.grunditz@ericsson.com> | 1 | 90% (+90%) | 90% (+90%) |  | 90%
55 | Y | 38.521-1 | 6.3J.3.5 | PUSCH-PUCCH and PUSCH-SRS time masks for ATG | Introduce PUSCH-PUCCH and PUSCH-SRS time masks test case for ATG UE | CMCC | RAN5#106 (Feb-25) |  | No test case details are specified. CMCC Luyang Zhao <zhaoluyang@chinamobile.com> | 1 | 0% | 0% |  | 0%
56 | Y | 38.521-1 | 6.3J.3.6 | Transmit power time mask for consecutive slot or long subslot transmission and short subslot transmission boundaries for ATG | Introduce Transmit power time mask for consecutive slot or long subslot transmission and short subslot transmission boundaries test case for ATG UE | CMCC | RAN5#105 (Nov-24) | R5-247736 | No test case details are specified. CMCC Luyang Zhao <zhaoluyang@chinamobile.com> | 1 | 100% (+100%) | 100% (+100%) |  | 100%
57 | Y | 38.521-1 | 6.3J.3.7 | Transmit power time mask for consecutive short subslot transmissions boundaries for ATG | Introduce Transmit power time mask for consecutive short subslot transmissions boundaries test case for ATG UE | CMCC | RAN5#105 (Nov-24) | R5-247736 | No test case details are specified. CMCC Luyang Zhao <zhaoluyang@chinamobile.com> | 1 | 100% (+100%) | 100% (+100%) |  | 100%
|  | 38.521-1 | 6.3J.4 | Power control for ATG | [5 empty] | 0
18 | Y | 38.521-1 | 6.3J.4.1 | Absolute power tolerance for ATG | Introduce Absolute power tolerance test case for ATG UE | CMCC | RAN5#106 (Feb-25) | R5-247737 R5-247740 R5-247838 | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> | 1 | 90% (+90%) | 90% (+90%) |  | 90%
50 | Y | 38.521-1 | 6.3J.4.2 | Relative power tolerance for ATG | Introduce Relative power tolerance test case for ATG UE | CMCC | RAN5#106 (Feb-25) | R5-247738 R5-247740 R5-247838 | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> | 1 | 90% (+90%) | 90% (+90%) |  | 90%
51 | Y | 38.521-1 | 6.3J.4.3 | Aggregate power tolerance for ATG | Introduce Aggregate power tolerance test case for ATG UE | CMCC | RAN5#106 (Feb-25) | R5-247739 R5-247740 R5-247838 | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> | 1 | 90% (+90%) | 90% (+90%) |  | 90%
|  | 38.521-1 | 6.4J | Transmit signal quality for ATG | [5 empty] | 0
19 | Y | 38.521-1 | 6.4J.1 | Frequency error for ATG | Introduce Frequency error test case for ATG UE | Ericsson | RAN5#106 (Feb-25) |  | Ericsson Hakan Grunditz <hakan.grunditz@ericsson.com> | 1 | 0% | 0% |  | 0%
|  | 38.521-1 | 6.4J.2 | Transmit modulation quality for ATG | [5 empty] | 0
20 |  | 38.521-1 | 6.4J.2.0 | General | Introduce General description of Transmit modulation quality for ATG UE | CMCC | RAN5#106 (Feb-25) |  | CMCC Dan Song <songdan@chinamobile.com> | 1 | 0% | 0% |  | 0%
21 | Y | 38.521-1 | 6.4J.2.1 | Error Vector Magnitude for ATG | Introduce Error Vector Magnitude test case for ATG UE | Ericsson | RAN5#106 (Feb-25) |  | Ericsson Håkan Grunditz <hakan.grunditz@ericsson.com> | 1 | 0% | 0% |  | 0%
22 | Y | 38.521-1 | 6.4J.2.1a | Error Vector Magnitude including symbols with transient period for ATG | Introduce Error Vector Magnitude including symbols with transient period test case for ATG UE | Ericsson | RAN5#106 (Feb-25) |  | Ericsson Håkan Grunditz <hakan.grunditz@ericsson.com> | 1 | 0% | 0% |  | 0%
23 | Y | 38.521-1 | 6.4J.2.2 | Carrier leakage for ATG | Introduce Carrier leakage test case for ATG UE | CMCC | RAN5#106 (Feb-25) |  | CMCC Dan Song <songdan@chinamobile.com> | 1 | 0% | 0% |  | 0%
24 | Y | 38.521-1 | 6.4J.2.3 | In-band emissions for ATG | Introduce In-band emissions test case for ATG UE | CMCC | RAN5#106 (Feb-25) |  | CMCC Dan Song <songdan@chinamobile.com> | 1 | 0% | 0% |  | 0%
25 | Y | 38.521-1 | 6.4J.2.4 | EVM equalizer spectrum flatness for ATG | Introduce EVM equalizer spectrum flatness test case for ATG UE | Ericsson | RAN5#106 (Feb-25) |  | Ericsson Håkan Grunditz <hakan.grunditz@ericsson.com> | 1 | 0% | 0% |  | 0%
26 | Y | 38.521-1 | 6.4J.2.5 | EVM equalizer spectrum flatness for Pi/2 BPSK for ATG | Introduce EVM equalizer spectrum flatness for Pi/2 BPSK test case for ATG UE | Ericsson | RAN5#106 (Feb-25) |  | Ericsson Håkan Grunditz <hakan.grunditz@ericsson.com> | 1 | 0% | 0% |  | 0%
|  | 38.521-1 | 6.5J | Output RF spectrum emissions for ATG | [5 empty] | 0
27 |  | 38.521-1 | 6.5J.0 | General | Introduce general description of Occupied bandwidth for ATG UE | CMCC | RAN5#103 (May-24) | R5-240053 | CMCC Dan Song <songdan@chinamobile.com> | 1 | 100% | 100% |  | 100%
28 | Y | 38.521-1 | 6.5J.1 | Occupied bandwidth for ATG | Introduce Occupied bandwidth test case for ATG UE | CMCC | RAN5#106 (Feb-25) | R5-241753 R5-241764 R5-246057 R5-246061 R5-247939 R5-247941 | CMCC Dan Song <songdan@chinamobile.com> MU/TT are pending for antenna/TAB connectors more than 2 or MOP over than 31dBm. Applicability is incomplete | 1 | 90% | 90% |  | 90%
|  | 38.521-1 | 6.5J.2 | Out of band emission for ATG | [5 empty] | 0
29 |  | 38.521-1 | 6.5J.2.1 | General | Introduce General description of Out of band emission for ATG UE | CMCC | RAN5#105 (Nov-24) | R5-240055 | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 100% | 100% |  | 100%
30 | Y | 38.521-1 | 6.5J.2.2 | Spectrum emission mask for ATG | Introduce Spectrum emission mask test case for ATG UE | Ericsson | RAN5#106 (Feb-25) |  | Ericsson Håkan Grunditz <hakan.grunditz@ericsson.com> | 1 | 0% | 0% |  | 0%
31 | Y | 38.521-1 | 6.5J.2.3 | Adjacent channel leakage ratio for ATG | Introduce Adjacent channel leakage ratio test case for ATG UE | CMCC | RAN5#106 (Feb-25) |  | CMCC Dan Song <songdan@chinamobile.com> | 1 | 0% | 0% |  | 0%
|  | 38.521-1 | 6.5J.3 | Spurious emissions for ATG | [5 empty] | 0
32 |  | 38.521-1 | 6.5J.3.0 | General | Introduce General description of Spurious emissions for ATG UE | CMCC | RAN5#103 (May-24) | R5-240056 | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 100% | 100% |  | 100%
33 | Y | 38.521-1 | 6.5J.3.1 | General spurious emissions for ATG | Introduce General Spurious emissions test case for ATG UE | CMCC | RAN5#106 (Feb-25) | R5-241754, R5-241764, R5-246057 R5-246061 | CMCC Dan Song <songdan@chinamobile.com> MU/TT are pending. Applicability is incomplete | 1 | 80% | 80% |  | 80%
TS 38.521-1: FR1 RF test cases - Rx
34 |  | 38.521-1 | 7.1J | General | Introduce general description for ATG UE Rx test cases | CMCC | RAN5#103 (May-24) | R5-240058 R5-243038 R5-244482 | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 100% | 100% |  | 100%
35 |  | 38.521-1 | 7.2J | Diversity characteristics for ATG | Introduce Diversity characteristics description for ATG UE | CMCC | RAN5#103 (May-24) | R5-240059 | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 100% | 100% |  | 100%
|  | 38.521-1 | 7.3J | Reference sensitivity for ATG | [5 empty] | 0
36 |  | 38.521-1 | 7.3J.1 | General | Introduce General description of Reference sensitivity test case for ATG UE | CMCC | RAN5#103 (May-24) | R5-240060 | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 100% | 100% |  | 100%
37 | Y | 38.521-1 | 7.3J.2 | Reference sensitivity power level for ATG | Introduce Reference sensitivity power level test case for ATG UE |  | RAN5#106 (Feb-25) |  |  | 1 | 0% | 0% |  | 0%
38 | Y | 38.521-1 | 7.4J | Maximum input level for ATG | Introduce Maximum input level test case for ATG UE | CAICT | RAN5#106 (Feb-25) | R5-241760 R5-246060 R5-246062 R5-247941 | CAICT Yufeng Zhang zhangyufeng@caict.ac.cn MU/TT are pending for antenna/TAB connectors more than 2. Applicability is incomplete | 1 | 90% | 90% |  | 90%
39 | Y | 38.521-1 | 7.5J | Adjacent channel selectivity for ATG | Introduce Adjacent channel selectivity test case for ATG UE | CAICT | RAN5#106 (Feb-25) | R5-241761 R5-243038 R5-246060 R5-246062 R5-247941 | CAICT Yufeng Zhang zhangyufeng@caict.ac.cn MU/TT are pending for antenna/TAB connectors more than 2. Applicability is incomplete | 1 | 90% | 90% |  | 90%
|  | 38.521-1 | 7.6J | Blocking characteristics for ATG | [5 empty] | 0
40 |  | 38.521-1 | 7.6J.1 | General | Introduce Blocking characteristics for ATG UE | CMCC | RAN5#103 (May-24) | R5-240061 | CMCC Luyang Zhao <zhaoluyang@chinamobile.com | 0.5 | 100% | 100% |  | 100%
41 | Y | 38.521-1 | 7.6J.2 | In-band blocking for ATG | Introduce In-band blocking test case for ATG UE | CAICT | RAN5#106 (Feb-25) | R5-241762 R5-246060 R5-246062 R5-247940 R5-247941 | CAICT Yufeng Zhang zhangyufeng@caict.ac.cn MU/TT are pending for antenna/TAB connectors more than 2. Applicability is incomplete | 1 | 90% | 90% |  | 90%
42 | Y | 38.521-1 | 7.6J.3 | Out-of-band blocking for ATG | Introduce Out-of-band blocking test case for ATG UE | CAICT | RAN5#106 (Feb-25) | R5-241763 R5-246060 R5-246062 R5-247940 R5-247941 | CAICT Yufeng Zhang zhangyufeng@caict.ac.cn MU/TT are pending Applicability is incomplete | 1 | 80% | 80% |  | 80%
43 | Y | 38.521-1 | 7.7J | Spurious response for ATG | Introduce Spurious response test case for ATG UE | CMCC | RAN5#106 (Feb-25) | R5-241757 R5-241764 R5-246059 R5-246061 R5-247940 R5-247941 | CMCC Dan Song <songdan@chinamobile.com> MU/TT are pending. Applicability is incomplete | 1 | 90% (+10%) | 90% (+10%) |  | 90%
|  | 38.521-1 | 7.8J | Intermodulation characteristics for ATG | [5 empty] | 0
44 |  | 38.521-1 | 7.8J.1 | General | Introduce Intermodulation characteristics for ATG UE | CMCC | RAN5#103 (May-24) | R5-240063 | CMCC Dan Song <songdan@chinamobile.com> | 0.5 | 100% | 100% |  | 100%
45 | Y | 38.521-1 | 7.8J.2 | Wide band intermodulation for ATG | Introduce Wide band intermodulation test case for ATG UE | CMCC | RAN5#106 (Feb-25) | R5-241758 R5-241764 R5-246059 R5-246061 R5-247941 | CMCC Dan Song <songdan@chinamobile.com> MU is pending for antenna/TAB connectors more than 2. Applicability is incomplete | 1 | 90% | 90% |  | 90%
46 | Y | 38.521-1 | 7.9J | Spurious emissions for ATG | Introduce Spurious emissions test case for ATG UE | CMCC | RAN5#106 (Feb-25) | R5-241759, R5-241764 R5-246059 R5-246061 | CMCC Dan Song <songdan@chinamobile.com> MU is are pending for MOP over than 31dBm. Applicability is incomplete | 1 | 90% | 90% |  | 90%
TS 38.521-4: Demod/CSI reporting test cases
|  | 38.521-4 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.521-4 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.521-4 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | 1 | 0% | 0% |  | 0%
TBD | Y | 38.521-4 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1 | 0% | 0% |  | 0%
TS 38.522: Applicability for RF, Demod/CSI reporting and RRM test cases
47 |  | 38.522 | 4 | Test case conditions and selection criteria | Add new ICS statements. | CMCC | RAN5#107 (May-25) | R5-241842 | CMCC Dan Song <songdan@chinamobile.com> | 0.1 | 70% | 70% |  | 70%
48 |  | 38.522 | 4.1.1 | FR1 standalone conformance test cases | Add test case applicability statements for the new test cases introduced for 38.521-x and 38.533. | CMCC | RAN5#107 (May-25) | R5-241842 | CMCC Dan Song <songdan@chinamobile.com> | 0.1 | 70% | 70% |  | 70%
TS 38.533: RRM test cases
|  | 38.533 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.533 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.533 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | 1 | 0% | 0% |  | 0%
TBD | Y | 38.533 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1 | 0% | 0% |  | 0%
TR 38.903: Test Tolerances analysis RRM and RF Rx test cases
|  | 38.903 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.903 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.903 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | 1 | 0% | 0% |  | 0%
TR 38.905: Test Point analysis receiver and transmitter test cases
|  | 38.905 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
49 |  | 38.905 | 4.1.1.8 | FR1 ATG test cases | Add TP analysis for ATG test cases | CAICT | RAN5#107 (May-25) | R5-241765 R5-247717 | CAICT Yufeng Zhang zhangyufeng@caict.ac.cn | 1 | 70% | 70% |  | 70%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.