## Slide 1
Puneet Jain
TSG SA Chair
SA Rel-20 5G-Advanced topics

## Slide 2: Rel-20 5G-Advaced Content Definition Process
TSG #107
TSG #108
TSG #109
TSG #110
TSG #111
TSG #112
TSG #113
TSG #114
TSG #115
TSG #116
TSG #117
TSG #118
TSG #105
2026
2027
Mar.
Sep.
Sep.
Sep.
Dec.
Dec.
Dec.
Mar.
Mar.
Jun.
Jun.
Jun.
Jun.
Stage-3 (CT & SA)
Stage-2 Study/Work Phase
Rel-20 5GA Content Approval
Rel-20 5GA
Workshop
TSG #106
Dec.
2025
Now
100%
SA1 Stage-1 80%
ASN.1 / Open API
Stage-1 Freeze
Selected Rel-20 SID/WID Approval
Rel-20 Final Package Approval
Stage-2 Freeze
Stage-3 Freeze
Rel-20 5GA complete
MED
Moderated Email Discussions
MED
WG starts working on Rel-20 SID/WID approved at SA#107
Rel-20 Scope Discussion / Guidance to WG
2024
ASN.1 / Open API
Stage-2 80% Complete

## Slide 3: SA Rel-20 5GA Content Definition steps
Discussion and Guidance for Rel-20 5GA Scope: The content proposals for Rel-20 5GA will be discussed during the SA Rel-20 5GA Workshop, and overall guidance will be provided to the SA WGs on Rel-20 5GA topics.
  This guidance will include a list of core and miscellaneous topics for Rel-20 5GA. The core topics have garnered significant interest based on numerous presentations, while the miscellaneous topics have been presented in a limited number of instances. The level of detail is yet to be determined.
  The WG's capacity including Max# of SID/WID and TU budget estimates will be taken into account.
Moderated Email Discussions: The Working Group may organize Moderated Email Discussions to develop SID/WID details corresponding to the Rel-20 5GA topics identified in the Core/Miscellaneous list. The focus will be on defining technical objectives, work tasks, and estimated budgets for each task. These discussions can occur in either Q1 or Q2 or both.
Approval of Selected Rel-20 5GA SID/WID: This marks the first step in the approval process for Rel-20 5GA content. The WG may submit the SID/WID to SA#107 for approval. Ideally, the Rel-20 5GA SID/WID for approval at this step should have no dependencies on RAN. SID/WID for approval should follow the guidance on Rapporteurship (see SP-230746). Part of WG capacity will be assigned during the first step approval process.
WG commences Rel-20 5GA SI/WI Work: After the approval of the SID/WID at SA#107, the Working Group can start working on the approved SID/WID during their Q2 meetings.
Final Approval of Rel-20 5GA Package: This represents the second and final step in the approval process for the Rel-20 5GA content definition. The WG can submit the Rel-20 5GA SID/WID to SA#108 for approval. SID/WID for approval should follow the guidance on Rapporteurship (see SP-230746). Further prioritization, if necessary, will be handled based on WG capacity.

## Slide 4
SA2 Rel-20 5G-A candidate topics
See SP-241909 for consolidated list
S.No. | Rel-20 5GA Core Topics | Rel-20 5GA Miscellaneous Topics
1 | Integration of satellite components in the 5G architecture Phase 4 | XR and Media Services (incl. Enhanced Traffic Management)
2 | AI/ML Enhancements | Indirect Network Sharing Phase 2
3 | Ambient IoT | User Identities and Authentication Architecture - Phase 2
4 | Integrated Sensing and Communication | Support for IMS Voice over Wi-Fi in 5GC (incl. Modernized ePDG)
5 | Energy Efficiency Enhancements | Mission Critical Services, Emergency Services and Multimedia Priority Services
6 |  | Industrial network enhancements (incl. de-jittering TSC enhancements)
7 |  | SMS for Emergency

## Slide 5
Guidance to SA2 on Rel-20 5GA work planning
SA2 should limit maximum number of Rel-20 5GA SIDs to 7.
  NOTE: This limit may be revisited at SA#107 after SA2 reaches an agreement on the 5GA and 6G TU split.
SA2 shall allocate the TU budget for TEI20 at a level no less than the TEI19 budget in Release-19.
SA2 should prioritize following “core” topics for Q1 and should aim to submit SIDs at SA#107 for approval (as per normal consensus). Remaining topics may also be discussed if time permits. If SA2 cannot come to an agreement on these items for SA#107 then they can come for approval at SA#108.
    Integration of satellite components in the 5G architecture Phase 4
    AI/ML enhancements
    Integrated Sensing and Communication
    Energy Efficiency Enhancements
The list of work task under “Brief Description and Key Objectives” in SP-2401909 should serves as a starting point for the moderated discussion and can be updated during the process.
The miscellaneous topics will be candidate for moderated discussion during Q2 2024.
The final decision on the complete set of SIDs for Rel-20 5GA (and the work tasks and TU budget of each SID) will be taken in SA#108.

## Slide 6: Thank You !
Puneet Jain
Chair of 3GPP SA
puneet.jain@intel.com
www.3gpp.org