## Slide 1: Exec Report SA5#158 Charging Management (CH)
Gerald Görmer, SA5 Charging Chair, MATRIXX Software

## Slide 2: Administrative aspects
Charging Work progress on Rel-19 (see S5-246328)
  Rel-19 WIDs completion status is good
  Rel-19 SIDs have completion status 75% due to pending work in SA2
  Expected completion of Rel-19 SIDs at SA5#159: additional Rapporteur call planned on 23.January 2025 14:00 – 16:00 UTC
SA5 SWG CH statistics:
  participation to this meeting
  14 delegates participated
  4 delegates followed from remote
  documents to this meeting
  105 total input and 68 output contributions
  4 Rel-19 WIDs (2 completed) and 4 Rel-19 SIDs
  2 liaisons replied (2 in, 3 out)
  4 agreed CRs for Rel-19 WIDs, 44 pCRs for Rel-19 SIDs, 20 CRs for Maintenance

## Slide 3: Incoming LSs
Tdoc | Title | Source | Decision | Reply In
S5-245375 | LS on Ranging/Sidelink Positioning Charging | SA2 | replied | S5-247001
S5-246404 | LS on MBS session charging per Rating Group | CT4 | replied | S5-246932

## Slide 4: Outgoing LSs
Tdoc | Title | To | Cc | Reply To
S5-247001 | LSreply on Ranging/Sidelink Positioning Charging | SA2 | - | S5-245375
S5-246932 | LSreply on MBS session charging per Rating Group | CT4 | - | S5-246404
S5-246956 | LS on Usage of Charging Characteristics and CHF Group ID | SA2, CT4 | - | -

## Slide 5: Charging (CH) WIs/SIs

## Slide 6
New or Revised Charging SIDs/WIDs
Number | Title | Source
- | - | -

## Slide 7: SA5 progress – Summary
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
 | Rel-19 Work Items | ------ | ----- | ------ | ---- | ---- | 
1040012 | WID on CHF Segmentation | CHFSeg | 03/03/2025 | 40 % | SP-241001 | 55 % | 
1040013 | WID on Charging Aspects of Ranging and Sidelink Positioning | Ranging_SL_CH | 03/03/2025 | 50 % | SP-241002 | 100 % | completed
1040018 | WID on charging aspects for energy efficiency of 5G | EnergySys_CH | 13/06/2025 | 45 % | SP-241003 | 45 % | No contribution
1040019 | WID on charging enhancement for indirect network sharing | NetShare_CH | 12/12/2024 | 0 % | SP-241004 | 100 % | completed
1050030 | New WID on Charging for 5G ProSe Ph3 | 5G_ProSe_Ph3_CH | 12/09/2025 | 0 % | SP-241004 | 0 % | No contribution
 | Rel-19 Studies | ------ | ----- | ------ | ----- | ---- | 
1040014 | Study on charging aspects of satellite access Phase 3 | FS_5GSAT_Ph3_CH | 1212/2024 | 55 % | SP-240980 | 75 % | pending work in SA2 on 5GSAT_Ph3-ARC), target delayed to March 2025
1040015 | SID on Charging Aspects of CAPIF | FS_CAPIF_CH | 12/12/2024 | 45 % | SP-240981 | 75 % | additional aspects from GSMA OPG, WID is feasible based on CRs in Rel-19, target delayed to March 2025
1040016 | SID on Charging aspects of next generation real time communication services phase 2 | FS_NG_RTC_Ph2_CH | 12/12/2024 | 55 % | SP-240982 | 75 % | pending work in SA2 on NG_RTC_Ph2, target delayed to March 2025
1040017 | SID on Charging aspects of Uncrewed Aerial Vehicle | FS_UAS_CH | 12/12/2024 | 55 % | SP-240983 | 75 % | pending work in SA2 on UAS_Ph3, target delayed to March 2025
 | Rel-20 Studies | ------ | ----- | ------ | ----- | ----- | 
For more information, see the full Work Plan at: ftp://ftp.3gpp.org/information/WorkPlan

## Slide 8
Charging Exception requests
Number | Title

## Slide 9: Rel-19 WID on CHF Segmentation
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1040012 | WID on CHF Segmentation | CHFSeg | 03/03/2025 | 40 % | SP-241001 | 55 % | 
Progress since SA#105
  1 CR agreed covering:
    CHF Segmentation with Supported Features (TS 32.290)
RAN impacts and dependencies:
  None identified
Next steps:
  Use of CHF Group Id for CHF selection and procedures/message flow, PCF interaction when N107 is used, use of Charging Characteristics for other NF consumer is ffs

## Slide 10: Rel-19 WID on Charging Aspects of Ranging and Sidelink Positioning
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1040013 | WID on Charging Aspects of Ranging and Sidelink Positioning | Ranging_SL_CH | 03/03/2025 | 50 % | SP-241002 | 100 % | completed
Progress since SA#105
  3 CRs agreed covering:
    Introduce OpenAPI extension and charging information to CDR (TS 32.291, TS 32.298)
RAN impacts and dependencies:
  None identified
Next steps:
  None

## Slide 11: Rel-19 WID on charging aspects for energy efficiency of 5G
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1040018 | WID on charging aspects for energy efficiency of 5G | EnergySys_CH | 13/06/2025 | 45 % | SP-241003 | 45 % | 
Progress since SA#105
  No contribution at this meeting
RAN impacts and dependencies:
  None identified
Next steps:
  Message flow and parameter definition

## Slide 12: Rel-19 WID on charging enhancement for indirect network sharing
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1040019 | WID on charging enhancement for indirect network sharing | NetShare_CH | 12/12/2024 | 0 % | SP-241004 | 100 % | completed
Progress since SA#105
  completed
RAN impacts and dependencies:
  None identified
Next steps:
  None

## Slide 13: Rel-19 New WID on Charging Aspects for 5G ProSe Ph3
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
xxx | New WID on Charging Aspects for 5G ProSe Ph3 | 5G_ProSe_Ph3_CH | 12/09/2025 | 0 % | 1050030 | 0 % | 
Progress since SA#105
  No contribution at this meeting
RAN impacts and dependencies:
  None identified
Next steps:
  Start the WID

## Slide 14: Rel-19 Study (FS_5GSAT_CH_Ph3)
Progress since SA#105
  18 pCRs for TR 28.846 were approved covering
    Clarification on the business roles and resolve Editor’s Notes in the satellite roaming charging solution
    Update background for UE-satellite-UE communications and tore and forward satellite operation charging solutions to solve Editor’s Notes
    Add business roles and charging scenarios, requirements and KI for UE-satellite-UE communication, store and forward satellite operation charging solutions for SMS, CP CIoT, UP CIoT
    Add and Update evaluations and conclusions for satellite charging topic 2, for store and forward satellite operation charging and for satellite resource usage charging and for MVNO charging
  Draft TR 28.846 (email approval S5-247040)
  Presentation of TR 28.846 for Information (email approval S5-246952)
RAN impacts and dependencies:
  None identified
Next steps:
  Drafting of solutions, evaluation and conclusion for the study
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1040014 | Study on charging aspects of satellite access Phase 3 | FS_5GSAT_Ph3_CH | 12/12/2024 | 55 % | SP-240980 | 75 % | pending work in SA2 on 5GSAT_Ph3-ARC, target delayed to March 2025

## Slide 15: Rel-19 Study (FS_CAPIF_CH)
Progress since SA#105
  9 pCRs for TR 28.849 were approved covering
    New Use Case: API Invoker Converged Charging
    Solutions/Evaluations: API Service Management, Multiple API Providers, Service API Management, and API Invoker Management
  Draft TR 28.849 (email approval S5-247029)
  Presentation of TR 28.849 for Information (email approval S5-247046)
RAN impacts and dependencies:
  None identified
Next steps:
  CAPIF Topic#4 Solutions, evaluation and study conclusion
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1040015 | SID on Charging Aspects of CAPIF | FS_CAPIF_CH | 12/12/2024 | 45 % | SP-240981 | 75 % | additional aspects from GSMA OPG, WID is feasible based on CRs in Rel-19), target delayed to March 2025

## Slide 16: Rel-19 Study (FS_NG_RTC_Ph2_CH)
Progress since SA#105
  9 pCRs for TR 28.851 were approved covering
    Adding solution and evaluation for standalone IMS Data Channel sessions
    Update the architecture
    Adding solutions and evaluation for DC application download and usage
    Evaluation for IMS DC charging topic 3 and topic 4
  Draft TR 28.851 (email approval S5-247043)
  Presentation of TR 28.851 for Information (email approval S5-247047)
RAN impacts and dependencies:
  None identified
Next steps:
  Add more use cases, key issues and corresponding solutions
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1040016 | SID on Charging aspects of next generation real time communication services phase 2 | FS_NG_RTC_Ph2_CH | 12/12/2024 | 55 % | SP-240982 | 75 % | pending work in SA2 on NG_RTC_Ph2, target delayed to March 2025

## Slide 17: Rel-19 Study (FS_UAS_CH)
Progress since SA#105
  8 pCRs for TR 28.853 were approved covering
    Add evaluation and conclusion for UAS charging topic 3 and topic 4.
    Add use case and solution for C2 Communication charging.
    Clarification of UAV Indication.
  Draft TR 28.853 (email approval S5-247044)
  Presentation of TR 28.853 for Information (email approval S5-247048)
RAN impacts and dependencies:
  None identified
Next steps:
  Add possible solutions, evaluations and overall conclusions.
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1040017 | SID on Charging aspects of Uncrewed Aerial Vehicle | FS_UAS_CH | 12/12/2024 | 55 % | SP-240983 | 75 % | pending work in SA2 on UAS_Ph3, target delayed to March 2025

## Slide 18
Charging TSs & TRs to be sent to SA#106
Number | Title | For
S5-246952 | Presentation of TR 28.846 for Information (for email approval) | Information
S5-247046 | Presentation of TR 28.849 for Information (for email approval) | Information
S5-247047 | Presentation of TR 28.851 for Information (for email approval) | Information
S5-247048 | Presentation of TR 28.853 for Information (for email approval) | Information

## Slide 19: Charging contributions
Maintenance
TEI17
TEI18
CHRACHF
B2B_CH
TEI19
Release 19 Work
CHFSeg
Ranging_SL_CH
Release 19 Study
FS_5GSAT_Ph3_CH
FS_CAPIF_CH
FS_NG_RTC_Ph2_CH
FS_UAS_CH

## Slide 20: Thank you!