## Slide 1: Summary of 2018 Income and Expenditure
Source
3GPP Funding and Finance Group
3GPP/OP#41(19)05

## Slide 2: Contents
Manpower expenditure (MCC staff)
Manpower expenditure (MCC contractors)
Manpower expenditure (IT support)
Manpower expenditure (Additional IT support)
Manpower expenditure (TTCN support)
Manpower expenditure (TTCN STF 160)
Manpower expenditure (TTCN STF 160P, 160G & 160V)
Travel expenditure
Promotion and Marketing Materials
Training
Overheads
Contingency
Income from Partners
Other income sources
Year end prediction
Conclusions

## Slide 3
3GPP Manpower Expenditure (MCC Staff)
Chart: 3GPP Staff expenditure 2018 Budget: 2226 kEUR
| January | February | March | April | May | June | July | August | September | October | November | December | Budget
3GPP staff | 169.454 | 184.891 | 192.402 | 182.115 | 214.955 | 282.153 | 136.321 | 163.747 | 189.782 | 209.582 | 193.92 | 140.309 | 2226
Linear spend to staff budget | 185.5 | 371 | 556.5 | 742 | 927.5 | 1113 | 1298.5 | 1484 | 1669.5 | 1855 | 2040.5 | 2226
3GPP staff cumulative spend | 169.454 | 354.345 | 546.747 | 728.862 | 943.817 | 1225.97 | 1362.291 | 1526.038 | 1715.82 | 1925.402 | 2119.322 | 2259.631

## Slide 4
3GPP Manpower Expenditure (MCC Staff)
End 2018 situation
  Expenditure for MCC Staff is 2 259,631 kEUR out of an annual budget of 2226 kEUR
  Expenditure is not linear because of bonus payments and salary increases which occurred in May and June. The overspend is mainly due to the accumulated annual leave not taken and compensation days incurred (including MCC work between Christmas and the New Year as a result of the December plenary meetings occurring late in the month).

## Slide 5
3GPP Manpower Expenditure (MCC Contractors)
End 2018 situation
  The contractors expenditure during 2018 amounts to 227,652 kEUR from an annual budget 218,800 kEUR. This is mainly due to one contractor changing from 80 to 90% in 2018 to cope with the RAN WG workload.
  It should be noted that the above figure does not include the non-remunerated expert provided by TTA in lieu of payment (whose annual value is 136,200 kEUR).

## Slide 6
3GPP Manpower Expenditure (IT Support)
End 2018 situation
  The cost of the IT support expert was 36,969 kEUR from an annual budget of 39 kEUR (45% of one officer dedicated to this task)

## Slide 7: 3GPP Manpower Expenditure (Additional IT Support)
End 2018 situation
  The cost of providing additional IT support is 79,200 kEUR (132 days) from an annual budget of 66 kEUR. The overspend is due to the increased number of meetings in 2018 and the fact that some “co-located” meetings are in fact in hotels in the same city, but which are some considerable distance apart. This results in the need for more than one IT person being on site.

## Slide 8
3GPP Manpower Expenditure (TTCN Support)
End 2018 situation
  The cost of the TTCN support expert was 124,972 kEUR from an annual budget of 125 kEUR (one officer dedicated full time to this task)

## Slide 9
3GPP Manpower Expenditure (STF 160)
End 2018 situation:
  810,600 kEUR of contracts have been established for STF160 out of the annual budget of 844 kEUR
  There are delays in TTCN development due to the late completion of related base standards and their lack of maturity

## Slide 10
3GPP Manpower Expenditure (160P, 160G and 160V)
End 2018 situation:
  156 kEUR has been spent for TTCN development requested by PTCRB/CTIA corresponding exactly to the funding received from them (STF160P)
  52 kEUR has been spent for TTCN development requested by GCF corresponding exactly to the funding received from them (STF160G)
  In additional to funded work, 394 man days of voluntary effort has been provided by members for TTCN development (STF160V)

## Slide 11: 3GPP Travel Expenditure
End 2018 situation
  The travel and subsistence costs are 579,988 kEUR from an annual budget of 525 kEUR. This includes the cost of 193 travels (130 long haul and 63 short haul)
Chart: 3GPP Travel expenditure 2018 Budget: 525 kEUR
| January | February | March | April | May | June | July | August | September | October | November | December | Budget
Cost per month | 25.974 | 119.443 | 34.085 | 43.691 | 37.475 | 81.875 | 40.42 | 22.77 | 37.588 | 57.59 | 28.392 | 50.679 | 525
Cumulative spend | 25.974 | 145.417 | 179.502 | 223.193 | 260.668 | 342.543 | 382.963 | 405.733 | 443.321 | 500.911 | 529.303 | 579.982

## Slide 12: Promotion and Marketing Materials
End 2018 situation
  The cost of promotion and marketing material was 26,317 kEUR from an annual budget of 60 kEUR
Promotion and Marketing Materials (budget 60 kEUR) | kEUR
5G Brand promotional materials | 3,833
Community Awards | 2,170
Printing | 0,680
Videos | 1,660
Web (webinars and banners) | 10,824
Social event photographer at TSG#82 – 20th Anniv. | 2,150
Miscellaneous | 5,000
TOTAL | 26,317

## Slide 13: Training
End 2018 situation
  Training costs for 2018 (anti-trust training sessions) amounted to 20,933 kEUR from an annual budget of 20 kEUR.

## Slide 14: Overheads
End 2018 situation
  Overheads for 2018 amount to 1402,449 kEUR from an annual budget of 1415 kEUR. The table below shows how this figure is derived.
MCC staff costs in support of 3GPP | 2259,631
Testing staff | 124,972
3GPP contractors for MCC support | 363,852
IT Support | 36,969
3GPP contractors for Specific Task 160 (excl 160V and 160P) | 810,600
TOTAL Workforce | 3596,024
Overhead: 39%*Workforce expenditure (figure based on ETSI overhead calculation) | 1402,449

## Slide 15: Contingency
A contingency of 100 kEUR had been set aside for 2018. 2,600 kEUR have been spent on the non-remunerated contractor’s immigration and work permit fees.

## Slide 16
3GPP Income from Partners
Invoices issued to Partners in 2018 (credit notes and non-remunerated expert taken into account)
Payments received by end of 2018
Partner | 2018 Contribution | Amount invoiced (in kEUR) | Invoice date
ARIB | 373,821 | 380,480 | 04/04/2018
CCSA | 830,714 | 844,184 | 04/04/2018
ETSI | 3248,093 | 3304,697 | 04/04/2018
ATIS | 498,429 | 507,510 | 04/04/2018
TTA | 323,979 | 193,228 | 04/04/2018
TTC | 232,6 | 236,686 | 04/04/2018
TSDSI | 307,364 | 312,661 | 04/04/2018
TOTAL | 5815 | 5779,446 | 

## Slide 17: Other Income Sources
Voluntary resources from Partners:
    136,200 kEUR (value of the voluntary expert provided by TTA in lieu of payment).
Other payments:
  156 kEUR funding from CTIA/PTCRB for STF 160P
  52 kEUR funding from GCF

## Slide 18
Conclusions
Income: all the payments from Partners were received by end of 2018.
Expenditure: most budget lines have been respected with some over expenditure due to more meetings being held during the year than originally estimated and a greater proportion of long haul travels
Summary: taking into account the income and expenditure for 2018, the year has closed with approximately 107 kEUR of funds remaining