## Slide 1: Summary of 2020 H1 Income and Expenditure
Source
3GPP Funding and Finance Group
OP#44(20)05

## Slide 2: Contents
Manpower (MCC staff)
Manpower (MCC contractors)
Manpower (IT support staff)
Manpower (TTCN testing support staff)
Manpower (TTCN STF 160 contractors)
Manpower (TTCN STF 160P, 160G & 160V contractors)
Travel and subsistence
Promotion and marketing materials
Training
Overheads
Contingency
Income from Partners
Other income sources
Conclusions

## Slide 3
Manpower (MCC staff)
At the beginning of 2020, one contractor position (Kimmo Kymalainen) was converted into a staff position. This was not planned for in the budget.
During Q1 2020, a successor was sought to replace the MCC Director (John Meredith) who plans to retire at end September 2020. The approved budget allowed for six months of overlap to enable a smooth handover of responsibilities. The selected successor was already working as a contractor in MCC and so this overlap provision has not been used. The successor (Issam Toufik) is now in post as a staff member. A replacement for Issam Toufik has been appointed but is not expected to be in post until October 2020
Taking the above into account, expenditure at the end of H1 2020 under the MCC staff budget line was 1182 kEUR out of an annual budget of 2170 kEUR.
It is predicted that by the year end the expenditure under this budget line will be 2276 kEUR. This represents an overspend of approximately 106 kEUR.

## Slide 4
Manpower (MCC Contractors)
With the conversion of one contractor position (Kimmo Kymalainen) into a staff position, and the appointment of one contractor (Issam Toufik) to the position of MCC Director, there are no remunerated contractors remaining in MCC at the end of H1 2020.
The expenditure at the end of H1 2020 under the MCC contractor budget line was 60,2 kEUR out of an annual budget of 245,4 kEUR. No further expenditure is expected for the remainder of the year
It should be noted that the H1 expenditure does not include the value of the seconded experts provided in lieu of payment by by CCSA, TSDSI and TTA (having a total value of 408,6 kEUR).

## Slide 5: Manpower (IT support staff)
The pandemic situation had a widespread impact on 3GPP during H1 2020. Only one meeting was held during this period which required onsite IT support.
Taking the above into account, expenditure at the end of H1 2020 under the IT support staff budget line was 5,1kEUR out of an annual budget of 132kEUR.
It is assumed that there will be no further physical meetings held for the remainder of 2020. It is therefore expected that by the year end the expenditure under this budget line will be approximately 10kEUR. This represents an underspend of approximately 122kEUR.

## Slide 6
Manpower (TTCN testing support staff)
One full-time TTCN support expert is provided to manage the development of TTCN within 3GPP.
The cost of that expert at the end of H1 2020 was 68,9 kEUR out of an annual budget of 139 kEUR.
The year-end prediction is that expenditure for this service will close within budget.

## Slide 7
Manpower (TTCN STF 160 contractors)
By the end of H1 2020, 276,9 kEUR of contracts have been established for STF160 out of the annual budget of 884 kEUR.
The year-end prediction is that expenditure for this service will close within budget.

## Slide 8
Manpower (TTCN STF 160P, 160G and 160V contractors)
By the end of H1 2020:
156 kEUR has been allocated for TTCN development requested by PTCRB/CTIA
156 kEUR has been allocated for TTCN development requested by GCF.
In additional to funded work, 18,5 man months voluntary effort have been provided by members for TTCN development (STF160V)
The year-end prediction is that expenditure for these services will close within budget.

## Slide 9: Travel and subsistence
The pandemic situation has led to the cancellation of many meetings during H1 2020. Where flight tickets had been purchased in advance, negotiations led to reimbursement or the issuing of vouchers in the vast majority of cases.
Due to the reimbursement of travel and flight reservations, Expenditure at the end of H1 2020 under the travel and subsistence budget line was -8,705kEUR out of an annual budget of 525kEUR. Further reimbursements are still pending.
It is assumed that there will be no further physical meetings held for the remainder of 2020 and therefore minimal further expenditure under this budget line. It is also assumed that no tickets will be forward purchased during 2020 for use in 2021 It is therefore predicted that this budget line will be underspent by approximately 538 kEUR by the year end.

## Slide 10: Promotion and marketing materials
The expenditure on promotion and marketing materials at the end of H1 2020 amounted to 9,4 kEUR from an annual budget of 60 kEUR. The cancellation of the Mobile World Congress and other events has impacted expenditure under this budget line.
It is predicted that by the year end expenditure will be approximately 30 kEUR, representing an underspent of approximately 30 kEUR .

## Slide 11: Training
The expenditure on training at the end of H1 2020 amounted to 4kEUR from an annual budget of 20 kEUR
Three anti-competition compliance training courses have been planned for H2 2020.
It is predicted that training expenditure will be within budget at the year end.

## Slide 12: Overheads
Changes in manpower expenditure during H1 2020 has led to lower overhead charges than expected. The expenditure at the end of H1 2020 amounted to 699kEUR from an annual budget of 1500 kEUR
It is predicted that by the year end expenditure will be approximately 1469 kEUR, representing an underspent of approximately 31 kEUR.

## Slide 13: Contingency
A contingency of 150 kEUR had been set aside for 2020.
2kEUR have been spent on the seconded expert’s immigration and work permit fees.
One additional expenditure may be incurred during H2 2020 for the registration of an Ethertype with IEEE (approximately 5kEUR)
It is predicted that by the year end expenditure will be approximately 10 kEUR and that approximately 140 kEUR will remain in contingency.

## Slide 14
3GPP Income from Partners
Invoices issued to Partners in 2020 (credit notes and seconded experts taken into account)
Payments received by September 2020

## Slide 15: Other Income Sources
Voluntary resources from Partners:
    136,200 kEUR (value of the voluntary expert provided by CCSA in lieu of payment).
    136,200 kEUR (value of the voluntary expert provided by TSDSI in lieu of payment)
    136,200 kEUR (value of the voluntary expert provided by TTA in lieu of payment)
Other payments:
  156 kEUR funding from CTIA/PTCRB for STF 160P
  156 kEUR funding from GCF for STF 160G

## Slide 16: Year end prediction
Budget Line | Predicted difference (kEUR)
Manpower (MCC staff) | +106
Manpower (MCC contractors) | -185
Manpower (IT support staff) | -122
Manpower (TTCN testing support staff) | -0
Manpower (STF160 TTCN support contractors) | -0
Travel and subsistence | -538
Promotion and marketing materials | -30
Training | -0
Overheads | -31
Contingency | -140
Overall Year end Prediction | -940
RED = Overspend
BLUE = Underspend

## Slide 17
Conclusions
On the expenditure side, the unforeseen pandemic has led to significant underspending as physical meetings have all but ceased and the associated travel cancelled.
On the income side, most Partner payments have been received. All payments are expected to be received by the year end.
It is not possible to predict precisely what will happen during the remainder of 2020, but at this stage it is expected that there will be an overall budget surplus in the order of 940 kEUR.