## Slide 1
3GPP F2F return
Overall plan
F2F DM #2 – 02/March/2022
OPf220011

## Slide 2: Overall plan
Based on the current covid-related travel and quarantine policies it is proposed to target the following general plan for 2022:
  All 3GPP meetings until end of May are to be held as E-meetings
  TSG#96 in June to be held F2F in Budapest/HU
  All July WG meetings to be held as E-meetings
  RAN WGs in August to be held F2F in Toulouse/FR
  SA and CT WGs in August to be held F2F in Gothenburg/Sweden
    Some smaller groups are hosted in Malaga/SP, Wroclaw/PL, Bath/UK
  TSG#97 in September to be held as E-meeting (originally NA)
  All WG meetings in October to be held as E-meetings (originally India and China)
  All WG meetings in November to be held F2F
  TSG#98 in December: proposal to hold this as F2F meeting in Seville/SP
In case return-quarantine restrictions entirely disappear, moving even more meetings to F2F in 2022 can be considered
  A minimum of 6 months lead time is needed for the host to find location, sign contract, etc…
Already confirmed target plan
Proposal to confirm
target plan now

## Slide 3: Detailed considerations
Review the status of June and August meetings – see separate contributions
November WG planning (14-18/Nov)
  Planned to be hosted in North America
  ATIS to seek a suitable location (considering the impact on delegates of all Covid-19 rules and visa issues) and present information at this meeting
  Present F2F_DM#2 to confirm, or re-consider November WG meeting location if suitable North American location is not identified
  To be evaluated and re-checked at F2F_DM#3 10th of May
    ATIS to provide detailed location information and contractual terms to F2F_DM#4
December TSG planning (12-16/Dec)
  EF3 has signed contract (from earlier postponement) for Seville/SP
  Proposal to confirm target as F2F at this F2F_DM#2 meeting
  Formal decision to be taken at F2F_DM#4 on 16th August

## Slide 4: F2F Decision Meeting plan
F2F_DM#2: 2nd March (Wednesday) 13-15h UTC (this meeting)
  Confirm target plan for Sept-Dec/2022
  Make formal decision on June TSGs as F2F
  Make formal decision on September TSGs as Electronic
  Review planning status for August and Nov F2F meetings
[MHSG#28: 3rd March (Thursday) 13-15h UTC
  Update F2F resumption study on key criteria to cover Omicron policies]
F2F_DM#3: 10th May (Tuesday) 13-15h UTC
  Formal decision on August WGs (as F2F)
  Formal decision on Oct WGs (as Electronic)
F2F_DM#4: 16 August (Tuesday) 13-15h UTC
  Formal decision on November WGs and December TSGs (both as F2F)

## Slide 5
Thank You!