## Slide 1: View on IMT-2030 submission timeplan
NTT DOCOMO, INC.
3GPP TSG SA/CT/RAN meeting #103
Maastricht, Netherlands, March 18-21, 2024
SP-240137 / CP-240154 / RP-240071

## Slide 2: Background – TSG#102
RP-233985 - Endorsed​

## Slide 3: DOCOMO proposed timeline
2023 |  |  |  | 2024 | 2023 | 2023 | 2023 | 2025 | 2023 | 2023 | 2023 | 2026 | 2023 | 2023 | 2023 | 2027 | 2023 | 2023 | 2023 | 2028 | 2023 | 2023 | 2023 | 2029 | 2023 | 2023 | 2023 | 2030 | 2023 | 2023 | 2023
Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
6G RAN requirements
3GPP RAN
6G WS (joint SA/CT/RAN)
ITU-R
Technical performance requirements
Evaluation criteria & methodology
Requirements, evaluation criteria and submission templates
Circular Letter
Workshop
Technology proposals for IMT-2030
Evaluation
Consensus building
Outcome & decision
IMT-2030 spec.
Timeline discussion
WS on 6G use cases
3GPP SA/CT
Stage 1 (SA1)
Rel-21 (6G WI)
Rel-21 (6G WI)
Stage 2 (SA2)
Rel-20 (6G SI)
Rel-21 (6G WI)
Stage 3 + ASN.1/Open API (CT)
IMT-2030 submission
Rel-20 (6G SI)
Rel-20 (6G SI)
Rel-21 (6G WI)
ASN.1
Stage3
IMT-2030 submission
Rel-20 (6G SI)
Stage3
SID approval: Sep 24
SID approval: June 25
SID approval: June 25
*TSG#102 Endorsed point

## Slide 4: Discussion points (1/2)
Rel-21 completion
  March 2029 for ASN.1 freeze, aligned among SA/CT/RAN
    Reasonable timing for enough study/work duration (18 + 21 months)
    SA/CT: 9 months b/w stage 2 and stage 3 completions, followed by 3 months for ASN.1 freeze
    → SA2 completion on schedule is quite important
Agenda of TSG-wide 6G workshop
  Useful to discuss/decide cross-TSG aspects, such as
    Which 6G use cases are supported by (enhanced) 5G NR, and which ones are supported by 6G RAT?
    Which 6G use cases identified in SA1 Rel-20 SI(s) should be prioritized for SA2 Rel-20 SI(s)?
    Whether 6G CN architecture is (enhanced) 5GC or brand-new 6GC, and when to decide?
    What should be discussed for tight TSG coordination, such as 6G NW architecture, including RAN-CN interface?

## Slide 5: Discussion points (2/2)
RAN requirements SI
  Controversial in TSG#102: strange to be started before 6G workshop (unlike 5G), while requirements are necessary to start WG-level technical discussion
  DOCOMO proposal: Dec. 2024 – Dec. 2025 for TR approval, considering followings
    5 meetings for TR approval
    At least 2 meetings before WG-level technical discussion
    TR approval before the completion of the discussion on IMT-2030 at ITU-R
  Alternatively, two-phase approach can be considered
    1st phase (Dec’24-): Focus on RAN high-level requirements and high-level deployment scenarios (similar to 5G study)
    2nd phase (Sep’25-): High-level technical topics, such as
      5G-6G migration (including NW architecture)
      6G use case support via eNR vs 6G RAT
      6G day1 priority
From 5G RAN Requirements SI (RP-160811, Dec'15 – Dec'16 for TR approval) This SI is to be completed in March 2017 (RAN #75), to match the ITU-R timeline of technical performance requirement (February 2017). RAN high-level requirements and high-level deployment scenarios need to be completed by March 2016 (RAN #71), to provide guidance to the technical work to be performed in RAN WGs. The TR is to be approved in RAN#73 when the bulk of the requirements is expected to be agreed. When the TR is approved it should be sent to ITU-R so that they can take into account for the discussion on IMT 2020 requirements definition. The SI can then remain open until March 2017 (RAN #75) in the background to further refine the requirements and make sure that they include the IMT 2020 requirements that will be defined by ITU-R by Feb 2017.