3GPP TSG RAN / SA/ CT Meeting #103	RP-240090

Maastricht, Netherlands, March 18-22, 2024	SP-240196

CP-240279

Agenda item:		20.7

Source:		Nokia

Title:	3GPP workplan for 6G

Document for:		Discussion and Decision

# Background

TSG#102 agreed the first set of milestones for 3GPP to undertake 6G work [1]:

To facilitate discussions and decisions on the remaining aspects of 3GPP’s 6G timeplan one can observe how 3GPP dealt with the initial study and normative standardization efforts in light of ITU-R activities and industry commercialization expectations.

The following figure shows a comparison of some of the key milestones in 4G, 5G with the ones in a 6G draft timeplan. Please note that this draft 6G chart shows Nokia’s preferences for the milestones.

We observe some baseline elements from the chart above:

- RAN Plenary Study Item shall well cater for feeding 3GPP input into ITU-R’s performance requirements phase

- Total time from breaking ground in 3GPP to the very first commercialization of the entire new generation system takes 5 years. One can speculate why exactly 5 years, but it is likely the sweet spot between undertaking a thorough enough study whilst catering for the commercialization ambitions of the earliest movers.

- While we don’t see the ITU-R technology submission timeline as the primary driving factor for 3GPP specification readiness, we observe ITU-R’s timeline well aligns with the commercialization timeline we foresee for the earliest of movers.

- The study phase for 5G was reasonably short with a longer normative phase. 
For 6G we see the dynamic of moving towards simplification and hence a shorter normative phase compared to 5G. At the same time a slightly longer study phase caters for feeding more meaningful input into ITU-R in a timely manner and allows streamlining a wide range of emerging technology concepts towards standardization.

# Proposal

As per the considerations above we propose to endorse the remaining 6G timeplan elements as described below:

- RAN Plenary level Study Item

  - Initial set of objectives focusing on ITU-R work to be approved in September/2024, work to start right-away on these objectives.

  - Full set of objectives to be approved in March/2025 following the TSG-wide Workshop, adding objectives e.g. on Architecture Requirements, Migration Scenarios, Interworking & Backward Compatibility, etc…

- Release 20 timeline

  - Package approval (incl. 6G RAN1/2/3 and SA2 Study Item approval) in June/2025 – already agreed.

  - Stage-3 completion in March/2027

  - RAN1 SI completion Dec/2026

  - RAN 2/3/4 and SA2 SI completion March/2027

  - SA1 SI completion September 2025

- Release 21 timeline

  - Package approval (incl. 6G RAN1/2/3 and SA2 Work Item approval) in Dec/2026

  - Stage-3 completion in Dec/2028

  - Frozen and implementable ASN.1: March/2029

# References

[1]		RP-233985 “High-level Considerations for 6G Timeline” (Endorsed)