## WP_3GPP
ID | Unique_ID | Name | Acronym | Outline_Level | Release | Resource_Names | Start_Date | Finish_Date | Percent_Complete | Hyperlink | Status_Report | WI_rapporteur_name | WI_rapporteur_e_mail | Notes | Impacted_TSs_and_TRs | TSG_approved | PCG_approved | TSG_stopped | PCG_stopped | Created | last_modif
15 | 640044 | Co-ordinated packet data network gateway (P-GW) change for SIPTO | CSIPTO | 1 | Rel-13 | S1 | 2014-06-18 08:00 | 2015-06-17 17:00 | 32% | SP-140509
16 | 660012 | Stage 1 for Co-ordinated packet data network gateway (P-GW) change for SIPTO | CSIPTO-ST1 | 2 | Rel-13 | S1 | 2014-06-18 08:00 | 2014-09-16 17:00 | 100% | SP-140509
17 | 660007 | Feasibility Study on Co-ordinated P-GW Change for SIPTO - Stage 2 | FS_CSIPTO_SA2 | 2 | Rel-13 | S2 | 2014-12-03 08:00 | 2015-06-17 17:00 | 0%
18 | 640052 | Application specific Congestion control for Data Communication | ACDC | 1 | Rel-13 | S1 | 2014-06-18 08:00 | 2014-12-04 17:00 | 99% | SP-140234
19 | 660013 | Stage 1 for Application specific Congestion control for Data Communication | ACDC-ST1 | 2 | Rel-13 | S1 | 2014-06-18 08:00 | 2014-09-17 17:00 | 100% | SP-140234
20 | 660039 | Stage 3 for Application specific Congestion control for Data Communication | ACDC-CT | 2 | Rel-13 | C1 | 2014-12-04 08:00 | 2014-12-04 17:00 | 0% | CP-140999
22 | 650019 | Flexible Mobile Service Steering | FMSS | 1 | Rel-13 | S1 | 2014-09-15 08:00 | 2015-06-17 17:00 | 9% | SP-140638
24 | 660002 | Flexible Mobile Service Steering TR Phase | FMSS-SA2TR | 2 | Rel-13 | S2 | 2014-12-12 08:00 | 2015-06-17 17:00 | 15%
25 | 660003 | Flexible Mobile Service Steering - Stage 2 | FMSS-SA2 | 2 | Rel-13 | S2 | 2014-12-12 08:00 | 2015-06-17 17:00 | 0%
92 | 640053 | Double Resource Reuse for Multiple Media Sessions | DRuMS | 1 | Rel-13 | S2 | 2014-03-14 08:00 | 2015-03-13 17:00 | 84% | SP-140393
94 | 660019 | CT aspects of Double Resource Reuse for Multiple Media Sessions | DRuMS-CT | 2 | Rel-13 | C3 | 2014-12-03 08:00 | 2015-03-13 17:00 | 65% | CP-140926
95 | 660047 | CT1 aspects of Double Resource Reuse for Multiple Media Sessions | DRuMS-CT-CT1 | 3 | Rel-13 | C3 | 2014-12-03 08:00 | 2015-03-13 17:00 | 65% | CP-140926
96 | 660048 | CT3 aspects of Double Resource Reuse for Multiple Media Sessions | DRuMS-CT-CT3 | 3 | Rel-13 | C3 | 2014-12-03 08:00 | 2015-03-13 17:00 | 65% | CP-140926
116 | 650032 | QoS End-to-end Multimedia Telephony Service for IMS (MTSI) extensions (Stage 3) | QOSE2EMTSI | 1 | Rel-13 | S4;C3;C1;C4 | 2013-03-06 08:00 | 2015-09-18 17:00 | 17% | SP-140601
123 | 660043 | CT Aspects of QoS End-to-End MTSI Extensions | QOSE2EMTSI-CT | 2 | Rel-13 | C3;C1;C4 | 2014-11-05 08:00 | 2015-09-11 17:00 | 0% | CP-140925
124 | 660044 | CT3 Aspects of QoS End-to-End MTSI Extensions | QOSE2EMTSI-CT3 | 3 | Rel-13 | C3 | 2014-11-05 08:00 | 2015-09-11 17:00 | 0% | CP-140925
125 | 660045 | CT1 Aspects of QoS End-to-End MTSI Extensions | QOSE2EMTSI-CT1 | 3 | Rel-13 | C1 | 2014-11-05 08:00 | 2015-09-11 17:00 | 0% | CP-140925
126 | 660046 | CT4 Aspects of QoS End-to-End MTSI Extensions | QOSE2EMTSI-CT4 | 3 | Rel-13 | C4 | 2014-11-05 08:00 | 2015-09-11 17:00 | 0% | CP-140925
158 | 660001 | Usage Monitoring Control PCC Extension | eUMONC | 1 | Rel-13 | S2 | 2014-12-03 08:00 | 2015-06-16 17:00 | 7%
159 | 660022 | Stage 2 of Usage Monitoring Control PCC Extension | eUMONC-SA2 | 2 | Rel-13 | S2 | 2014-12-03 08:00 | 2015-06-16 17:00 | 6%
160 | 660020 | CT3 Aspect of Usage Monitoring Control extension | eUMONC-CT3 | 2 | Rel-13 | C3 | 2014-12-03 08:00 | 2015-03-13 17:00 | 10% | CP-140927
161 | 660004 | Service Domain Centralization | SeDoC | 1 | Rel-13 | S2 | 2014-12-03 08:00 | 2015-06-16 17:00 | 0%
162 | 660005 | Service Domain Centralization TR Phase | SeDoC-SA2TR | 2 | Rel-13 | S2 | 2014-12-03 08:00 | 2015-06-16 17:00 | 0%
163 | 660006 | Service Domain Centralization - Stage 2 | SeDoC-SA2 | 2 | Rel-13 | S2 | 2014-12-03 08:00 | 2015-06-16 17:00 | 0%
164 | 660009 | MBMS Enhancements | MBMS_enh | 1 | Rel-13 | S2 | 2014-12-03 08:00 | 2015-09-14 17:00 | 0%
165 | 660010 | MBMS Enhancements TR Phase | MBMS_enh-SA2TR | 2 | Rel-13 | S2 | 2014-12-03 08:00 | 2015-09-14 17:00 | 0%
166 | 660011 | MBMS Enhancements - Stage 2 | MBMS_enh-SA2 | 2 | Rel-13 | S2 | 2014-12-03 08:00 | 2015-09-14 17:00 | 0%
167 | 660030 | Enhanced P-CSCF discovery using signalling for access to EPC via WLAN | ePCSCF_WLAN | 1 | Rel-13 | C1 | 2014-10-06 08:00 | 2015-03-13 17:00 | 0% | CP-140813
168 | 660014 | CT1 aspects of Enhanced P-CSCF discovery using signalling for access to EPC via WLAN | ePCSCF_WLAN-CT1 | 2 | Rel-13 | C1 | 2014-12-03 08:00 | 2015-03-13 17:00 | 0% | CP-140813
169 | 660023 | CT4 aspects of Enhanced P-CSCF discovery using signalling for access to EPC via WLAN | ePCSCF_WLAN-CT4 | 2 | Rel-13 | C4 | 2014-10-06 08:00 | 2015-03-13 17:00 | 0% | CP-140813
170 | 660016 | Stage-3 SAE Protocol Development | SAES4, SAES4-CSFB, SAES4-non3GPP | 1 | Rel-13 | C1 | 2014-12-03 08:00 | 2015-12-11 17:00 | 0% | CP-140814
171 | 660017 | IMS Stage-3 IETF Protocol Alignment | IMSProtoc7 | 1 | Rel-13 | C1 | 2014-12-03 08:00 | 2015-12-11 17:00 | 0% | CP-140815
172 | 660034 | Interworking solution for Called IN number and original called IN number ISUP parameters | INNB_IW | 1 | Rel-13 | C1 | 2014-12-03 08:00 | 2015-03-13 17:00 | 53% | CP-140928
173 | 660036 | (IETF) CT1 part of Interworking solution for Called IN number and original called IN number ISUP parameters | INNB_IW-CT1 | 2 | Rel-13 | C1 | 2014-12-03 08:00 | 2015-03-13 17:00 | 25% | CP-140928
174 | 660021 | CT3 aspects of Interworking solution for Called IN number and original called IN number ISUP parameters | INNB_IW-CT3 | 2 | Rel-13 | C3 | 2014-12-03 08:00 | 2015-03-13 17:00 | 80% | CP-140928
175 | 660042 | Warning Status Report in EPS | WSR_EP | 1 | Rel-13 | C4 | 2014-12-03 08:00 | 2015-09-14 17:00 | 0% | CP-140998
176 | 660015 | CT1 aspects of Warning Status Report in EPS | WSR_EP-CT1 | 2 | Rel-13 | C1 | 2014-12-03 08:00 | 2015-09-14 17:00 | 0% | CP-140998
177 | 660029 | CT4 aspects of Warning Status Report in EPS | WSR_EP-CT4 | 2 | Rel-13 | C4 | 2014-12-03 08:00 | 2015-09-14 17:00 | 0% | CP-140998
178 | 660025 | Study on Diameter Load Control Mechanisms | FS_DLoCME | 1 | Rel-13 | C4 | 2014-12-03 08:00 | 2015-09-11 17:00 | 0% | CP-140996
179 | 660026 | Shared Data Update for Multiple Subscriber | SHARED_SubData_UPD | 1 | Rel-13 | C4 | 2014-12-03 08:00 | 2014-12-03 17:00 | 0% | CP-140804
180 | 660027 | Study on EPC Signalling Improvement for Race Scenarios | FS_EPC_SIG_RACE | 1 | Rel-13 | C4 | 2014-12-03 08:00 | 2015-09-11 17:00 | 0% | CP-140997
181 | 660028 | P-CSCF Restoration Enhancements with WLAN | PCSCF_RES_WLAN | 1 | Rel-13 | C4 | 2014-12-03 08:00 | 2015-12-11 17:00 | 0% | CP-140995
182 | 660040 | CT4 aspects of P-CSCF Restoration Enhancements with WLAN | PCSCF_RES_WLAN-CT4 | 2 | Rel-13 | C4 | 2014-12-03 08:00 | 2015-12-11 17:00 | 0% | CP-140995
183 | 660041 | CT1 aspects of P-CSCF Restoration Enhancements with WLAN | PCSCF_RES_WLAN-CT1 | 2 | Rel-13 | C4 | 2014-12-03 08:00 | 2015-12-11 17:00 | 0% | CP-140995
184 | 660035 | ULI and release causes for charging enhancement for VoLTE | new4 | 1 | Rel-13 | S5 | 2014-12-03 08:00 | 2015-09-11 17:00 | 0% | S5-146227
185 | 660033 | Multi-Broadcast Single Frequency Network (MBSFN) Minimization of Drive Tests (MDT) enhancement | new5 | 1 | Rel-13 | S5 | 2014-12-03 08:00 | 2015-06-12 17:00 | 0% | S5-145398
333 | 660008 | Feasibility study on Extended DRX cycle for Power Consumption Optimization | FS_eDRX | 1 | Rel-13 | S2 | 2014-12-03 08:00 | 2015-06-16 17:00 | 0%
334 | 660037 | Study on KQIs for Service Experience |  | 1 | Rel-13 | S5 | 2014-12-03 08:00 | 2015-09-11 17:00 | 0% | S5-146364