## Slide 1: Work Item Management
Lionel Morand
TSG CT Chair, Orange

## Slide 2: Preamble
This presentation aims to reinforce the necessity for good practice in project management and the key role of the rapporteur in this task
Nothing new in this presentation. Most of the information is available on the 3GPP website
This document is destined to WG chairs and new rapporteurs
This is a first version and any comment to improve it is welcome
It is meant to be useful and not an additional constraint.

## Slide 3: Outline
Work Item Description
Types of Work Item
Work Item Rapporteur
Specification Rapporteur
WI/Specification Work Plan update

## Slide 4: Work Item=Project
Development of the 3GPP system is complex and controlled by means of a work plan covering the inclusion of new features (functionality)
the concepts and constraints which apply to an engineering project also apply to the development of the 3GPP system
The primary challenge of project management is to achieve all of the project goals within the given constraints

## Slide 5: Work Item=Project
3GPP system enhancements are possible with:
  new or substantially enhanced services/features/functions
  Technical enhancements or improvements of existing functionality/protocol
Work Items are used to track progress of the work on 3GPP system enhancements
Work Item Description (WID) are used to
  detail the required technical activity
  decide to include the Work item in the 3GPP Work Plan

## Slide 6: Work Item Description
A precise definition of content
  Scope of Work
An estimated schedule
  Clear milestones to track progress
A named person to act as rapporteur
  acting as Project manager
At least four Supporting Member Organizations
  Offering active participation in its realization.
  “Active” means that supporting companies will provide resources to complete the work (i.e. contribution, review/comment, etc.)

## Slide 7: Work Item Classification
“Work Item” is a generic term that encompasses different categories
 | Feature
 | Building Block
 | Work Task
 | Study Item

## Slide 8: Study Item
An initial study, resulting in a Technical Report, which typically performs a feasibility study for additional functionality/protocol enhancements to the existing system.
The conclusion of this study shall allow determining the viability of the introduction of a new feature/solution:
  In some cases, the conclusion can be that it is not be doable
  If the results of the study are positive, one or more subsequent Feature-type Work Items may follow.

## Slide 9: Feature
New or substantially enhanced functionality added to the existing system
self-contained and somehow “optional”
  up to operator/vendor to decide whether to implement it
When complex, broken down into simpler elements:
  building blocks and/or work tasks for specifying precise functionality

## Slide 10: Building Block
A sub-division of a feature
Generally restricted to:
  a single physical
  logical entity
  or a single protocol
For simple features, a single building block may suffice, then feature = building block
Can be further subdividing into smaller tasks, each representing a closely specified and easily comprehended activity.
  divided by technical content and/or by phase.

## Slide 11: Work Task
A sub-division of a building block, representing a self-contained, well-scoped and well-scheduled item of work
lowest hierarchical level of breakdown the scope of work
The output of a work task shall be:
  One or more new Technical Specifications (or Reports); and / or
  Change Requests to existing TSs / TRs.
For simple building blocks, work task = building block

## Slide 12: Work Item Rapporteur
Every Work Item shall have a Rapporteur
Prime contact point
  on technical matters
  for information on progress throughout the drafting phases
  inside or outside 3GPP
Selected
  from regular attendees of the primary responsible Group
  from supporting companies

## Slide 13: Role of Work Item Rapporteur
With the WG, establish and update the Work Plan
Monitor the progress of the work in (all) WG(s)
Schedule offline sessions (drafting session, confcall, etc.) if needed
Report to the responsible WG on the progress of the work
Identify the completion of the WI to update the 3GPP Work Plan
Keep the WI Description up-to-date (when needed)
Help in the identification of rapporteurs for new specifications

## Slide 14: Role of Specification Rapporteur
Serve as Editor until the specification.
  producing the initial draft and subsequent revised versions until approval of the specification.
Oversee the technical quality of the specification.
Explain the specification to any other group (inside or outside 3GPP), where appropriate.
Serve as focal point for technical questions.

## Slide 15: Role of Specification Rapporteur
Deliver a clean specification to the MCC for editorial clean-up before submission for TSG approval to come under change control.
When the specification is approved, the Rapporteur remains the key contact for any proposed modification to the specification
Propose an ordered list of CRs to address (if relevant) to help the WG chairs in the organisation of the meeting
Review all CRs to the approved specification prior to agreement in the Working Group.
  This includes identifying and resolving clashes.

## Slide 16: WI/Specification Rapporteur Report
The Rapporteur should provide a WI/Specification Work Plan status report at each meeting
Status reports are important to:
  know what has been done/ needs to be done
  identify possible issues/risks that need to be solved
Can be done through Discussion Paper updated meeting after meeting
  examples: C1-194188, C1-194364
Status reports should help rapporteurs to indicate the level of completion of the WI when updating the 3GPP Work Plan

## Slide 17: WG Chair duties
WG chairs should help Rapporteurs in their WI management
WG chairs should ensure that Rapporteurs and supporting companies are active
WG chairs should ensure that the outputs of the WI represent the view of the WG (e.g. enough discussion/review, etc.)
WG should ensure that the list of WI/Specification Rapporteurs is up-to-date
Use the Rapporteur reports to:
  prepare WG report to TSG
  update the 3GPP Work Plan

## Slide 18: Summary
Work Item management = Project
Different types of Work Items
  Study
  Feature
  Building Block
  Work Task
The role of the WI/Specification Rapporteur is essential to the overall 3GPP Work Plan management…
  … and remains important after the completion of the WI/specification
Regular Work Plan status report should be used to update chairs and delegates on the project progress

## Slide 19: References
3GPP Working Procedures:
  https://www.3gpp.org/ftp/Information/Working_Procedures/
3GPP TR 21.801 “Specification drafting rules”:
  https://www.3gpp.org/ftp/Specs/archive/21_series/21.801/21801-g10.zip
3GPP TR 21.900 “Technical Specification Group working methods”
  https://www.3gpp.org/ftp/Specs/archive/21_series/21.900/21900-g10.zip

## Slide 20: Thank You!
Lionel Morand
3GPP CT Chairman
mail: lionel.morand@orange.com
phone: +33 6 0775 8936