## Slide 1: CT WG1 Status Report to TSG CT#90
Peter Leis
CT1 Chair, Nokia

## Slide 2: TSG CT WG1 Officials
Peter Leis
TSG CT WG1 Chair
ETSI
peter.leis@nokia.com
Lena Chaponniere
TSG CT WG1 ViceChair
ATIS lguellec@QTI.QUALCOMM.COM
Jörgen Axell
TSG CT WG1 ViceChair
ETSI
jorgen.axell@ericsson.com
Frederic Firmin
Secretary
MCC
frederic.firmin@etsi.org

## Slide 3: Meeting Calendar
Since the last CT plenary
  CT1#126-e (electronic)
  CT1#127-e (electronic)
Upcoming Meetings
  CT1-127-bis-e
    begin January 25th 2021
    end January 29th 2021
  CT1#128-e
    begin February 25th 2021
    end March 5th 2020

## Slide 4: TSG CT WG1 Statistics
Number of handled documents
  CT1#126-e: 961
  CT1#127-e: 770
Agreed CRs
  CT1#126-e: Cat B/C/F 259
  CT1#127-e: Cat B/C/F 198
Agreed pCRs
  CT1#126-e: 13
  CT1#127-e: 14
Attendances
  CT1#126-e: 131 registered
  CT1#121-e: 126 registered
Other information
  Both meetings had all releases in scope

## Slide 5: New agreed Study/Work Items led by CT1
TDoc # | Title | Source | Objectives
CP-203232 | SID - Study on the CT aspects of Support for Minimization of service Interruption | LGE | investigate the stage 2 and the stage 3 aspects for service requirements defined by SA WG1 under their work item MINT
CP-203234 | WID - Reliable Data Service Serialization Indication | Intel | to add support to the Reliable Data Service for indicating the serialization format of the data that will be sent in a NIDD session

## Slide 6: Work Plan Rel-17
Namez | Acronym | Start | End | % | WID
Protocol enhancements of Mission Critical Services | MCProtoc17 | 25.06.2020 | 20.09.2021 | 30% | CP-201164
Mission Critical system migration and interconnection | MCSMI_CT | 13.12.2018 |  | 5% | CP-190143
Stage-3 of MuDe | MuDe | 25.06.2020 | 12.12.2020 | 15% | CP-201162
CT1 aspects of MPS2 | MPS2 | 25.06.2020 | 15.03.2021 | 75% | CP-201207
Stage 3 of eCPSOR_CON | eCPSOR_CON | 25.06.2020 | 20.06.2021 | 10% | CP-201166
Stage-3 5GS NAS protocol development 17 | 5GProtoc17 | 25.06.2020 | 20.09.2021 | 30% | CP-201163
Stage-3 SAE Protocol Development | SAES17 | 25.06.2020 | 20.09.2021 | 30% | CP-201165
Legend Green row – Newly completed
Yellow row – on time for completion Red row – at risk for completion on time, below 70%
98 – no progress since the last plenary
98 - Updated

## Slide 7: Work Plan Rel-17
Name | Acronym | Start | End | % | WID
IMS Stage-3 IETF Protocol Alignment | IMSProtoc17 | 25.06.2020 | 12.09.2021 | 10% | CP-201167
Study on enhanced IMS to 5GC Integration Phase 2 | FS_eIMS5G2 | 25.06.2020 | 20.03.2021 | 10% | CP-201168
CT aspects of Enhancements to Mission Critical Data | eMCData3 | 25.06.2020 | 20.09.2021 | 10% | CP-201177
Enhancements to LMR interworking | eMCCI_CT | 25.09.2020 | 20.09.2021 | 60% | CP-202241
CT aspects of Enhanced Mission Critical Push-to-talk architecture | enh3MCPTT-CT | 25.09.2020 | 20.09.2021 | 45% | CP-202188
CT aspects of 5GC architecture for satellite networks | 5GSAT_ARCH-CT | 16.09.2020 | 12.09.2021 | 20% | CP-202244
Enhancements to Mobile Communication System for Railways (MONASTERY) Phase 2 | eMONASTERY2 | 16.09.2020 | 08.09.2021 | 10% | CP-202256
Legend Green row – Newly completed
Yellow row – on time for completion Red row – at risk for completion on time, below 70%
98 – no progress since the last plenary
98 - Updated

## Slide 8: Work Plan Rel-17
Name | Acronym | Start | End | % | WID
CT1 aspects of PAP/CHAP protocols usage in 5GS | PAP_CHAP | 25.06.2020 | 12.09.2021 | 90% | CP-201167
CT1 aspects of AKMA | FS_eIMS5G2 | 25.06.2020 | 20.03.2021 | 70% | CP-201168
CT1 aspects of SMS_SBI | eMCData3 | 25.06.2020 | 20.09.2021 | 0% | CP-201177
Legend Green row – Newly completed
Yellow row – on time for completion Red row – at risk for completion on time, below 70%
98 – no progress since the last plenary
98 - Updated

## Slide 9: TS sent to CT plenary
TDoc # | Title | Version | Rapporteurs | Sent for
n/a |  |  |  | 

## Slide 10: Status of older releases
Rel-9: 1 CAT F CR on IMS work items was agreed (IANA registration complete)
Rel-12: 1 CAT F CR on IMS work items was agreed (IETF reference update)
Rel-13: 3 CAT F CRs on IMS work items were agreed (IETF reference updates, IANA registration completed)
Rel-13: 1 CAT F CR for Mission Critical work items was agreed
Rel-14: 3 CAT F CRs on IMS work items were agreed (IETF reference updates, IANA registration complete)
Rel-14: 1 CAT F CR for Mission Critical work items was agreed

## Slide 11: Release 15 Status
3 CRs on Mission Critical work items were agreed
2 CRs on IMS work items were agreed (IANA registration related)
4 CRs on 5G_Ph1 were agreed, all are backward compatible
Overall Rel-15 is stable

## Slide 12: Backward Incompatible Changes
In “Frozen” specification, with impact on other TSG WGs
TDoc # | Title | Source | Impacted TS | Impacted TSG WG
n/a |  |  |  | 

## Slide 13: Release 16 Status
All Rel-16 work items are complete.
189 CAT F CRs against Rel-16 agreed , fixing FASMO and aligning with stage-2 (previous quarter had 246 agreed CRs)

## Slide 14: Release 17 Status
161 CRs were agreed for Release 17
  Significant amount of the CRs were related to protocol enhancements
27 pCRs were agreed for Release 17
  5GSAT_ARCH-CT and FS_eIMS5G2
10 tdocs were agreed for agreed Rel 17 study item on FS_MINT-CT
One new work item and one new study item were agreed
Work item proposals with dependency on work items in SA2 and where the SA2 work is still not approved were postponed

## Slide 15: For Information to CT (I)
CT1 has scheduled two electronic meetings in Q1 2021
  CT1#127-bis-e
    Limited scope
    Rel-17 only, excluding Protoc17/SAES17/TEI17
  CT1#128-e
    All releases in scope
CT1 has agreed the updated Terms of Reference, coming to this plenary for approval
CT1 has updated the list of rapporteurs for its specifications
New Rel-17 work item proposals expected in Q1 2021, depending on progress in SA

## Slide 16: For Information to CT (II)
Tight coordination between CT1 and CT3 is needed for the work on „CT aspects for Enabling Edge Applications. CT1, CT3 and CT chairs are planning a CT1-CT3 joint session for that purpose. Details will be provided via email lists after plenary has finished
Hao Jing acted as MCC support for CT1#126-e
Joern Krause acted as MCC support for CT1#127-e
Frederic Firmin still active in the background and in preparation of meetings

## Slide 17: For Action to CT
n/a

## Slide 18: Experience with e-meeting
High number of emails resulted in very busy meetings:
  CT1#126-e roughly 3900 emails
  CT1#127-e roughly 3200 emails
Conference calls
  Used GoTo Meeting, alternating timeslot 13:00 UTC to 15:00 UTC/14:00 to 16:00 UTC
  Useful to find way forward
Decision making over email not always easy
  sometimes slow (different timezones), no f2f offline discussion
  as a consequence, complex topics are more easily shifted out of the meeting

## Slide 19: Some stats, number of tdocs
E-meeting in February and April had limited scope
November e-meeting only 6 days
Chart: Number of tdocs in CT1
| Jan 2018 | Feb 2018 | Apr 2018 | May 2018 | Jul 2018 | Aug 2018 | Oct 2018 | Nov 2018 | Jan 2019 | Feb 2019 | Apr 2019 | May 2019 | Aug 2019 | Oct 2019 | Nov 2019 | Feb 2020 e | April 2020 e | June 2020 e | Aug 2020 e | Oct 2020 e | Nov 2020 e
begin of meeting | 377 | 400 | 422 | 472 | 531 | 404 | 548 | 479 | 350 | 376 | 438 | 450 | 720 | 535 | 525 | 571 | 562 | 765 | 632 | 614 | 448
end of meeting | 710 | 725 | 801 | 812 | 884 | 771 | 969 | 895 | 643 | 703 | 750 | 839 | 1135 | 920 | 940 | 840 | 895 | 1168 | 1006 | 961 | 770

## Slide 20: Some stats, agreed CRs/pCRs
E-meeting in February and April had limited scope
E-meeting in November only 6 days
Chart: CT1 - agreed CR/pCR
| Oct_2019 | Nov_2019 | Feb-e_2020 | April-e_2020 | June-e_2020 | August-e_2020 | October-e_2020 | November-e_2020
agreedCR | 207 | 213 | 194 | 304 | 394 | 325 | 259 | 198
agreedpCR | 95 | 59 | 107 | 42 | 36 | 1 | 14 | 13

## Slide 21: Acknowledgement
The CT1 Chairman wants to thank
Lena Chaponniere for chairing the breakout stream on “Services” topics
Jörgen Axell for chairing the breakout stream on “IMS and MC” topics
Hao Jing, Joern Krause, Frédéric Firmin for their excellent support before, during and after the meetings
Most important the CT1 delegates for their dedication and hard work during very busy and demanding electronic meetings

## Slide 22: Annex

## Slide 23: CRs for conditional approval I
TDoc # | Title | Spec | CR# | Dependancy
C1-207174 | QoS parameter handling for the PDU session transfer between 3GPP and non-3GPP access | 24.501 | 2634 | Core: TS 23.502 CR 2453 (SA2)
C1-207175 | QoS parameter handling for the PDU session transfer between 3GPP and non-3GPP access | 24.501 | 2635 | Core: TS 23.502 CR 2453 (SA2)
C1-206461 | Update RAT selection rule | 24.587 | 127 | Core: TS/TR 24.588 CR 0021
C1-206486 | Update RAT selection rule | 24.588 | 21 | Core: TS/TR 24.587 CR 0127
C1-207478 | Correction in 5GMM cause value #72 | 24.501 | 2816 | Core: TS 23.501 CR 2465 (SA2)
C1-207479 | Correction in 5GMM cause value #72 | 24.501 | 2817 | Core: TS 23.501 CR 2465 (SA2)
C1-206561 | Adding NW-TT port numbers to BMIC | 24.519 | 18 | Core: TS 23.501 CR 2451 (SA2)
C1-207582 | TSi handling when the NW-TT generates the gPTP event messages | 24.535 | 6 | Core: TS 23.501 CR 2466 (SA2)
C1-207634 | The definition of non-CAG cell | 23.122 | 632 | Core: TS 24.501 ... CR#2876...
C1-207642 | Adding handling of the UE configuration parameter "Access_Point_Name_Parameter_Reading_Rule" for the UE to read the APN name parameter from correct input source. | 24.229 | 6476 | Core: TS 24.623 CR 0079

## Slide 24: CRs for conditional approval II
TDoc # | Title | Spec | CR# | Dependancy
C1-207637 | Notification to upper layer upper layer for MMTEL video call when T3346 or T3325 running | 24.301 | 3463 | Core: TS 24.173 CR 0145
C1-207641 | Notification to upper layer upper layer for MMTEL video call when T3346 or T3525 running | 24.501 | 2811 | Core: TS 24.173 CR 0145
C1-207724 | Adding handling of the UE configuration parameter "Access_Point_Name_Parameter_Reading_Rule" for the UE to read the XCAP APN name parameter from correct input source. | 24.623 | 79 | Core: TS 24.229 CR 6476
C1-207596 | CAG support and CAG information are only applicable when MS is in 5GS | 23.122 | 624 | Core: TS/TR 23.501 CR 2486 (SA2)

## Slide 25: Thank You!
Peter Leis
3GPP TSG CT WG1 Chairman
peter.leis@nokia.com