## Slide 1: CT WG3 Status Report to TSG CT#92e
Susana Fernández
TSG CT WG3 Chair
Ericsson

## Slide 2: TSG CT3 Officials
Susana Fernández
CT3 Chair
susana.fernandez@ericsson
Yoshihiro Inoue
CT3 Vicechair yoshihiro.inoue@ntt-at.co.jp
Huang Zhenning
CT3 Vicechair
huangzhenning@chinamobile.com
Hao Jing
Secretary
MCC
Hao.Jing@3gpp.org

## Slide 3: Meeting Calendar
Since the last CT plenary
  Ordinary (complete Agenda):
    CT3#115E (April 14th – 23rd)
    CT3#116E (May 19th – 28th)
Upcoming Meetings
  Ordinary (complete Agenda):
    CT3#117E (August 18th- 27th)

## Slide 4: TSG WG CT3 Statistics
CT3#115e:
Number of handled documents
  607 documents allocated
Agreed CRs
  Cat B/C/F : 67/0/114
Agreed pCRs
  25
Attendances
  93 registered/ 93 attendants
CT3#116e:
Number of handled documents
  565 documents allocated
Agreed CRs
  Cat B/C/F: 99/0/88
    (13/0/6 revised from CT3#115e)
Agreed pCRs
  7
Attendances
  85 registered/ 85 attendants

## Slide 5: New/Revised agreed Study/Work Items led by CT3
TDoc # | Title | Source | Objectives | Release
CP-211xxx | CT aspects on Dynamically Changing AM Policies in the 5GC (rev) | Ericsson | The objective of this work item is to develop the Stage 3 specifications to enable the dynamic change of AM policies as specified by Stage 2. Revised to align with latest stage 2 status and terminology. | Release 17
CP-211xxx | N7 Interfaces Enhancements to Support GERAN and UTRAN (rev) | China Mobile | The objective is to study and then extend the interface on N7 reference point to support 2G/3G. Revised to correct terminology and add missing impacted TS. | Release 17
CP-211xxx | CT aspects on Dynamic Management of Group-based Event Monitoring (rev) | Ericsson | The objective of this work item is to develop the Stage 3 specifications to enable the Dynamic management of group-based event monitoring as specified by Stage 2. Revised to correct WI code. | Release 17
CP-211xxx | Enablers for Network Automation for 5G - phase 2 (rev) | China Mobile | The objective is to specify the protocols and specifications required in order to fulfil system enhancements for NWDAF. Revised to align with Stage 2 and to introduce three new TSs. | Release 17

## Slide 6: New/Revised agreed Study/Work Items led by CT3
TDoc # | Title | Source | Objectives | Release
CP-211xxx | Enhancements of 3GPP Northbound and Application Layer APIs (new) | Huawei | The objective of this work item is to specify the technical enhancements and necessary changes to the 3GPP Northbound Interfaces and Application Layer APIs, following the principles in 3GPP TS 29.500 and 3GPP TS 29.501 when possible, which are not covered by other dedicated WIs. | Release 17
CP-211xxx | Enhancement of 5G PCC related services in Rel-17 (new) | Huawei | The objective of this work item is to specify the stage 3 procedures related to EPS functionality not completely covered in en5GPccSer. | Release 17
CP-211xxx | CT aspects for enabling Edge Applications (rev) | Samsung | The objective of this work item is to define the protocol aspects and related APIs for enabling edge applications based upon the normative Stage 2 technical specifications developed by SA6, SA5 and SA3 WGs. | Release 17

## Slide 7: Work Plan – CT3 Driven – Release 17 (i)
Name | Acronym | Start | End | % | WID
Stage 3 of Multimedia Priority Service (MPS) Phase 2 | MPS2 | 2020-06 | 2021-03 | 70 | CP-201207
PFD management enhancement | pfdManEnh | 2020-06 | 2021-06 | 100 | CP-210183
CT aspects on PAP/CHAP protocols usage in 5GS | PAP_CHAP | 2020-09 | 2021-03 | 100 | CP-210188
Authentication and key management for applications based on 3GPP credential in 5G | AKMA-CT | 2020-09 | 2021-06 | 97 | CP-203107
CT aspects for Enabling Edge Applications | EDGEAPP | 2020-12 | 2021-12 | 40 | CP-21xxxx
Legend Green row – Newly completed
Yellow row – for completion on time Red row – at risk for completion on time
98 – no progress since the last plenary
98 - Updated

## Slide 8: Work Plan – CT3 Driven – Release 17 (ii)
Name | Acronym | Start | End | % | WID
CT aspects on Dynamically Changing AM Policies in the 5GC | TEI17_DCAMP | 2021-03 | 2022-03 | 30 | CP-21xxxx
N7 Interfaces Enhancements to Support GERAN and UTRAN | TEI17_NIESGU | 2021-03 | 2021-09 | 90 | CP-21xxxx
CT aspects on Dynamic Management of Group-based Event Monitoring | TEI17_GEM | 2021-03 | 2022-03 | 35 | CP-21xxxx
Enablers for Network Automation for 5G - phase 2 | eNA_Ph2 | 2021-03 | 2022-03 | 20 | CP-21xxxx
Legend Green row – Newly completed
Yellow row – for completion on time Red row – at risk for completion on time
98 – no progress since the last plenary
98 - Updated

## Slide 9: Work Plan – CT3 Driven – Release 17 (iii)
Name | Acronym | Start | End | % | WID
Enhancements of 3GPP Northbound Interfaces and Application Layer APIs | NBI17 | 2021-03 | 2022-03 | 35 | CP-21xxxx
Enhancement of 5G PCC related services in Rel-17 | en5GPccSer17 | 2021-03 | 2022-03 | 20 | CP-21xxxx
Legend Green row – Newly completed
Yellow row – for completion on time Red row – at risk for completion on time
98 – no progress since the last plenary
98 - Updated

## Slide 10: Work Plan – Non-CT3 Driven – Rel-17 (i)
Name | Acrony | Start | End | % | WID
Study on enhanced IMS to 5GC Integration Phase 2 | FS_eIMS5G2 | 2020-06 | 2021-03 | 5 | CP-201168
IMS Stage-3 IETF Protocol Alignment | IMSProtoc17 | 2020-06 | 2021-09 | 60 | CP-201167
Service Based Interface Protocol Improvements Release 17 | SBIProtoc17 | 2020-06 | 2021-09 | 65 | CP-211088
Reliable Data Service Serialization Indication | RDSSI | 2020-12 | 2021-12 | 100 | CP-203234
CT aspects of Access Traffic Steering, Switch and Splitting support in the 5G system architecture; Phase 2 | ATSSS_Ph2-CT | 2021-03 | 2022-03 | 50 | CP-210136
Legend Green row – Newly completed
Yellow row – for completion on time Red row – at risk for completion on time
98 – no progress since the last plenary
98 - Updated

## Slide 11: Work Plan – Non-CT3 Driven – Rel-17 (ii)
Name | Acrony | Start | End | % | WID
CT aspects of enhanced support of industrial IoT | IIoT | 2021-03 | 2022-03 | 45 | CP-211114
CT aspects on Same PCF Selection For AMF and SMF | TEI17_SPSFAS | 2021-03 | 2021-09 | 98 | CP-211184
CT aspects of Enhanced support of Non-Public Networks | eNPN-CT | 2021-03 | 2022-03 | 0 | CP-210139
CT Aspects of 5G eEDGE | eEDGE_5GC | 2021-03 | 2022-03 | 40 | CP-211092
Enhancement of Network Slicing Phase 2 | eNS_Ph2 | 2021-03 | 2022-03 | 30 | CP-210070
CT aspects for Support of Unmanned Aerial Systems Connectivity, Identification, and Tracking | ID_UAS | 2021-03 | 2022-03 | 0 | CP-211112
Legend Green row – Newly completed
Yellow row – for completion on time Red row – at risk for completion on time
98 – no progress since the last plenary
98 - Updated

## Slide 12: Work Plan – Non-CT3 Driven – Rel-17 (ii)
Name | Acrony | Start | End | % | WID
Enhancement to the 5GC Location Services - Phase 2 | 5G_eLCS_ph2 | 2021-03 | 2022-03 | 0 | CP-211090
CT aspects of Enhancement for Proximity based Services in 5GS | 5G_ProSe | 2021-03 | 2022-03 | 35 | CP-211110
BEst Practice of PFCP | BEPoP | 2021-03 | 2021-09 | 60 | CP-210074
CT aspects of 5GC architecture for satellite networks | 5GSAT_ARCH-CT | 2021-03 | 2021-09 | 60 | CP-210149
CT aspects of Enhanced application layer support for V2X services | eV2XAPP | 2021-03 | 2022-03 | 50 | CP-211109
CT aspects on support for Signed Attestation for Priority and Emergency Sessions | TEI17_SAPES | 2021-03 | 2021-09 | 100 | CP-210143
Legend Green row – Newly completed
Yellow row – for completion on time Red row – at risk for completion on time
98 – no progress since the last plenary
98 - Updated

## Slide 13: Work Plan – Non-CT3 Driven – Rel-17 (iii)
Name | Acrony | Start | End | % | WID
CT Aspects of Application Layer Support for Uncrewed Aerial Systems (UAS) | UASAPP | 2021-06 | 2022-03 | 5 | CP-211111
CT aspects of the architectural enhancements for 5G multicast-broadcast services | 5MBS | 2021-06 | 2022-03 | 0 | CP-211093
Enhanced Service Enabler Architecture Layer for Verticals | eSEAL | 2021-06 | 2022-03 | 0 | CP-211117
CT aspects of Architecture enhancements for 3GPP support of advanced V2X services - Phase 2 | eV2XARC_Ph2 | 2021-06 | 2022-03 | 0 | CP-211116
Legend Green row – Newly completed
Yellow row – for completion on time Red row – at risk for completion on time
98 – no progress since the last plenary
98 - Updated

## Slide 14: TS/TR sent to CT plenary
None

## Slide 15: Pre-Release 16 Status
There were no submitted pre-Release 15 CRs
For Release 15, 19 CRs were agreed
  Most contributions were for 5GS_Ph1-CT & NAPS-CT.
  eSPECTRE and CAPIF-CT got one contribution each.
  Most of the topics correct overlooked issues
    Wrong attribute names or data types, missing response codes, wrong Request URI, etc.
    Corrections on applicability and conditional use of attributes
    Corrections to mandate information in non-roaming II-NNI (TS 29.165)
  Corrections not considered as FASMO were moved to further releases

## Slide 16: Release 16 Status
49 agreed CRs (cat F) in Release 16 (24 in CT3#115e & 28 in CT3#116e, 3 revised)
Significant less contributions than in previous meetings.
Main areas of activity have been:
  5G_eSBA WI: 13 agreed CRs
    Support of Redirect Responses with “application/json” media types in every API.
  V2XAPP WI: 8 agreed CRs
    Corrections on data types, resource URIs, Service names, etc.
  eNA WI: 8 agreed CRs
  en5GPccSer WI: 5 agreed CRs
    Corrections on the handling of ExtendedSamePcf feature, several corrections to TS 29.594, etc.
  Other corrections for ATSSS, Vertical_LAN, 5G_CIoT, 5G_eLCS

## Slide 17: Release 17 Status (I) - General
2 new agreed WIDs, 4 new endorsed WIDs
2 revised agreed WIDs, 5 revised endorsed WIDs
Significant work for the already agreed/endorsed WIDs
Dependencies with ongoing Stage 2 work: Dependent CRs and several LSs submitted.
A lot of work expected in the upcoming meetings
Work plans presented by companies for several WIs to describe impacts and plans for completion of the work
277 agreed CRs, 32 agreed pCRs
Handling of Inclusive Language
  Checking up to date for the existing Release 17 TSs.

## Slide 18: Release 17 Status (II) – CT3-driven WIs
MPS2 WI reported as 60% complete
  CRs to both EPC & 5G PCC TSs to introduce MPS for DTS support.
pfdManEnh WI reported as 100%
  One CR for partial pull handling agreed in this cycle.
AKMA-CT WI reported as 97%
  Most work related to API corrections in TS 29.535.
PAP_CHAP WI reported as 100%
  No contributions submitted in this period.

## Slide 19: Release 17 Status (III)- CT3 Owned WIs
EDGEAPP WI reported as 40%
  TS 29.558 progressing according to plans.
  Specification of Eees_UELocation, Eees_UEIdentifier, Eees_SessionWithQoS, Eees_AppClientInformation and Eees_TargetEASDiscovery service descriptions and API definitions has started.
  Discussions on API design basics – CT4 contacted to agree on the principles.
  Many Editor’s Notes introduced for several design aspects.
TEI17_DCAMP WI reported as 30%
  Companies contributing to the WI according to Work Plan.
  New TS 29.534 on track.
  Impacts on N5, N7, N15 and Northbound APIs agreed.

## Slide 20: Release 17 Status (III)- CT3 Owned WIs
TEI17_NIESGU WI reported as 90%
  Support of event trigger for GERAN and UTRAN access over N7 interface agreed.
TEI17_GEM WI reported as 35%
  Progress on the support of GEM partial cancellation
eNA_Ph2 WI reported as 20%
  Four new TSs have been initiated as part of this WI (DCCF services, ADRF services, MFAF services, network data analytics signalling flows)
  Work started for the specification of Nnwdaf_MLModelProvision API & Nnwdaf_DataManagement API in TS 29.520
  Functionality such as like User Data Congestion Analytics, Partitioning criteria for applying sampling in UE partitions, Mute Reporting incorporated in the relevant TSs.

## Slide 21: Release 17 Status (IV)- CT3 Owned WIs
NBI17 WI reported as 35% (New WID)
  Agreement on how to split the work between SBIProtoc17 & NBI17: The new WI would cover all the protocol enhancement aspects related to Northbound APIs & Application Layer APIs and SBIProtoc17 would be limited to 5GC APIs.
en5GPccSer17 WI reported as 20 % (New WID)
  WI agreed to cover PCC enhancements not covered under any other WI.
  Contributions related to interworking, offline charging, requests that have timed out, etc. handled.

## Slide 22: Release 17 Status (IV)- CT3 Non-driven WIs
SBIProtoc17 WI reported as 65%
  Focused on alignment CT3 SBI-based TSs with TS 29.500 & TS 29.501.
  WID updated after agreeing on the split with the new WI NBI17: SBIProtoc 17 focused on 5G APIs.
  Progressive increase of the percentage of completion in every meeting.
IMSProtoc17 WI reported as 60%
  No contributions during this Plenary cycle.
  Progressive increase of the percentage of completion in every meeting.

## Slide 23: Release 17 Status (V)- CT3 Non-driven WIs
TEI17_SPSFAS WI reported as 95%
  Agreed contribution to TS 29.513 to select the same PCF from AMF & SMF.
ATSSS_Ph2 WI reported as 50%
  Agreed contributions to support threshold condition and steering mode indicators in Npcf_PolicyControl Service.
IIoT WI reported as 45%
  Work started for the specification of Time Sensitive Communication other than TSN, Survival Time, Time Synchronization Exposure, TSCAI Time Domain in the relevant TSs.
  Big dependency with ongoing stage 2 work.

## Slide 24: Release 17 Status (VI)- CT3 Non-driven WIs
eNS_Ph2 WI reported as 30%
  Work started with the specification of Network Slice Status reporting events for MonitoringEvent API & Serving PLMN UE Slice-MBR control.
eEDGE_5GC WI reported as 40%
  Support of User Plane Latency requirements in AF-influence of traffic routing control introduced in relevant services.
  ECS Address Provisioning support added.
  Support of Network Exposure to EAS via Local NEF
  Updates related to AF influence on URSP introduced.
BEPoP WI reported as 60%
  Agreed updates to support L2TP for CUPS

## Slide 25: Release 17 Status (VII)- CT3 Non-driven WIs
5GSAT_ARCH WI reported as 60%
  Handling of Satellite backhaul change event as been specified in TS 29.512, TS 29.513 & TS 29.523.
eV2XAPP WI reported as 50%
  Work focused on the specification of VAE_HDMapDynamicInfo service, the support of Local MBMS & eCAPIF.
TEI17_SAPES WI reported as 100%
  With the support for signed attestation for emergency and priority IMS sessions the WI was considered complete.

## Slide 26: Release 17 Status (VIII)-CT3 Non-driven WIs
UASAPP WI reported as 5%
  Skeleton and scope for the new UASAPP TS have been agreed.
WIDs for 5MBS, ESEAL & EV2XARC_Ph2 agreed. Work not initiated.
Quite a few contributions to enhance functionality & descriptions for different WIs (TEI17 + WI code CRs).
Non-reported WIs had no progress during this Plenary Cycle.

## Slide 27: Backward Incompatible Changes
None

## Slide 28: For Information to CT
CT3 work focused on:
  Agreeing/endorsing a big list of Release 17 Work Items.
  Starting or progressing work for the agreed/endorsed WIDs.
  Introducing corrections for Release 16 & Release 15.
Plenty of work expected during the coming meetings to progress the Work Items.
  Still a strong dependency with the stage 2 progress:
    CR dependencies and LSs to SA2 required.
  Work for pre-Release 17 contributions is being reduced, especially for Release 15.
CT3-CT4 coordination required for some topics
  Functionality that affect both WGs, API design principles or work split for Work Items that impact both groups.
CT3 is committed to the handling of Inclusive language in our TR/TSs.
  All existing Release 17 TSs handle Inclusive Language.
E-meeting experience improves in each meeting
  Still the process is quite time consuming and reaching agreements is more difficult than in f2f meetings.

## Slide 29: For Action to CT
No identified action

## Slide 30: Acknowledgement
The Chair wants to thank
  Vice Chairmen Yoshihiro and Huang Zhenning for helping in the CT3 management.
  MCC Hao Jing for his big effort and good work to support CT3 before, during and after the meeting.
  ETSI support for IT facilities.
  All CT3 delegates, and specially TS rapporteurs, for their hard work, professionalism and commitment for the success of this challenging meeting.
  CT WG Chairs, CT Chair and MCCs for helping with the good practices in the handling of e-meetings and coordination activities.

## Slide 31: Annex

## Slide 32: CRs for conditional approval
TDoc # | Title | Spec | CR# | Dependency
C3-212541 |  | TS 29.513 | #0261 | TS 23.503 CR #6484
C3-211018 | Reference update: RFC 8841 | TS 29.165 | #1019 | TS 24.229 CR #6485
C3-211019 | Reference update: RFC 8841 | TS 29.165 | #1020 | TS 24.229 CR #6486
C3-211020 | Reference update: RFC 8841 | TS 29.165 | #1021 | TS 24.229 CR #6487
C3-211021 | Reference update: RFC 8841 | TS 29.165 | #1022 | TS 24.229 CR #6488
C3-211022 | Reference update: RFC 8841 | TS 29.165 | #1023 | TS 24.229 CR #6489
C3-211618 | 5GS interworking with EPS for EAP based secondary AUTH in RADIUS message flow | TS 29.561 | #0088 | TS 23.502 CR 2475
C3-211619 | 5GS interworking with EPS for EAP based secondary AUTH in Diameter message flow | TS 29.561 | #0089 | TS 23.502 CR 2475

## Slide 33: Thank You!
Susana Fernández
3GPP TSG CT WG3 Chair
Susana.fernandez@ericsson.com