## Slide 1: CT WG1 Status Report to TSG CT#92e
Peter Leis
CT1 Chair, Nokia

## Slide 2: TSG CT WG1 Officials
Peter Leis
TSG CT WG1 Chair
ETSI
peter.leis@nokia.com
Lena Chaponniere
TSG CT WG1 ViceChair
ATIS lguellec@QTI.QUALCOMM.COM
Jörgen Axell
TSG CT WG1 ViceChair
ETSI
jorgen.axell@ericsson.com
Frederic Firmin
Secretary
MCC
frederic.firmin@etsi.org
Andrijana Brekalo
Secretary
MCC
Andrijana.Brekalo@etsi.org

## Slide 3: Meeting Calendar
Since the last CT plenary
  CT1#129-e (electronic)
  CT1#130-e (electronic)
Upcoming Meetings
  CT1#131-e
    begin August 19th 2021
    end August 27th 2021

## Slide 4: TSG CT WG1 Statistics
Number of handled documents
  CT1#129bis-e: 602
  CT1#130-e: 1169
Agreed CRs
  CT1#129-e: Cat B/C/F 84
  CT1#130-e: Cat B/C/F 262
Agreed pCRs
  CT1#129-e: 74
  CT1#130-e: 69
Attendances
  CT1#129-e: 177 registered
  CT1#130-e: 168 registered
Other information
  CT1#129-e had reduced scope, only Rel-17 (no xyzProtoc17, no TEI17)
  CT1#130-e had full scope

## Slide 5: New agreed Study/Work Items led by CT1
TDoc # | Title | Source | Objectives
CP-211111 | New WID on CT Aspects of Application Layer Support for Uncrewed Aerial Systems (UAS) | Huawei | specify the CT aspects and update the CT WGs specifications to support the stage 2 requirements on Application layer support for Uncrewed Aerial System (UAS) defined in 3GPP TS 23.255
CP-211116 | New WID on CT aspects of architecture enhancements for 3GPP support of advanced V2X services - Phase 2 | Huawei | Specify CT aspects of advanced V2X services Phase 2 in order to enhance the CT WGs specifications based on the stage 2 requirements developed by SA2
CP-211117 | New WID on enhanced Service Enabler Architecture Layer for Verticals | Samsung | Define the protocol aspects of enhanced SEAL based upon the normative Stage 2 technical specifications developed by SA6
CP-211118 | New WID on CT aspects of Mission Critical Services over 5GS | Nokia | Define the stage 3 aspects of Mission Critical Services over 5GS based on stage 2 technical specifications developed by SA6

## Slide 6: Work Plan Rel-17
Namez | Acronym | Start | End | % | WID
Protocol enhancements of Mission Critical Services | MCProtoc17 | June 2020 | Sept 2021 | 50% | CP-202193
Mission Critical system migration and interconnection | MCSMI_CT | Dec 2018 |  | 5% | CP-190143
Stage-3 of MuDe | MuDe | June 2020 | June 2021 | 100% | CP-211162
CT1 aspects of MPS2 | MPS2 | June 2020 | March 2021 | 80% | CP-201207
Stage 3 of eCPSOR_CON | eCPSOR_CON | June 2020 | March.2022 | 50% | CP-210148
Stage-3 5GS NAS protocol development 17 | 5GProtoc17 | June 2020 | March 2022 | 50% | CP-201163
Stage-3 SAE Protocol Development | SAES17 | June 2020 | Sept 2021 | 50% | CP-201165
Legend Green row – Newly completed
Yellow row – on time for completion Red row – at risk for completion on time, below 70%
98 – no progress since the last plenary
98 - Updated

## Slide 7: Work Plan Rel-17
Name | Acronym | Start | End | % | WID
IMS Stage-3 IETF Protocol Alignment | IMSProtoc17 | June 2020 | Sept 2021 | 40% | CP-201167
Study on enhanced IMS to 5GC Integration Phase 2 | FS_eIMS5G2 | June .020 | Sept 2021 | 15% | CP-201168
CT aspects of Enhancements to Mission Critical Data | eMCData3 | June 2020 | Sept 2021 | 45% | CP-201177
Enhancements to LMR interworking | eMCCI_CT | Sept 2020 | Sept 2021 | 60% | CP-202241
CT aspects of Enhanced Mission Critical Push-to-talk architecture | enh3MCPTT-CT | Sept 2020 | Sept 2021 | 48% | CP-202188
CT aspects of 5GC architecture for satellite networks | 5GSAT_ARCH-CT | Sept 2020 | Sept 2021 | 50% | CP-210149
Enhancements to Mobile Communication System for Railways (MONASTERY) Phase 2 | eMONASTERY2 | Sept 2020 | March 2022 | 50% | CP-210145
Legend Green row – Newly completed
Yellow row – on time for completion Red row – at risk for completion on time, below 70%
98 – no progress since the last plenary
98 - Updated

## Slide 8: Work Plan Rel-17
Name | Acronym | Start | End | % | WID
CT1 aspects of PAP/CHAP protocols usage in 5GS | PAP_CHAP | June 2020 | Sept 2021 | 100% | CP-201167
CT1 aspects of AKMA | AKMA-CT | June 2020 | March 2021 | 95% | CP-201168
CT1 aspects of SMS_SBI | SMS_SBI | June 2020 | Sept 2021 | 0% | CP-201177
CT aspects for Enabling Edge Applications | EDGEAPP | Dec 2020 | Sept 2021 | 30% | CP-203106
SID - Study on the CT aspects of Support for Minimization of service Interruption | FS_MINT-CT | Dec 2020 | June 2021 | 95% | CP-210144
Reliable Data Service Serialization Indication | RDSSI_CT | Dec 2020 | Sept 2021 | 100% | CP-203234
New WID on CT aspects of Access Traffic Steering, Switch and Splitting support in the 5G system architecture; Phase 2 | ATSSS_Ph2 | March 2021 | March 2022 | 60% | CP-210136
Legend Green row – Newly completed
Yellow row – on time for completion Red row – at risk for completion on time, below 70%
98 – no progress since the last plenary
98 - Updated

## Slide 9: Work Plan Rel-17
Name | Acronym | Start | End | % | WID
CT aspects of enhanced support of industrial IoT | IIoT | March 2021 | March 2022 | 65% | CP-210279
Enabling Multi-USIM devices | MUSIM | March 2021 | March 2022 | 40% | CP-210280
CT aspects of Enhanced support of Non-Public Networks | eNPN | March 2021 | March 2022 | 20% | CP-210139
CT aspects for Support of Unmanned Aerial Systems Connectivity, Identification, and Tracking | ID_UAS | March 2021 | March 2022 | 20% | CP-210287
CT aspects of Enhancement for Proximity based Services in 5GS | 5G_ProSe | March 2021 | March 2022 | 50% | CP-210292
CT aspects of Enhanced application layer support for V2X services | eV2XAPP | March 2021 | March 2022 | 35% | CP-210273
CT aspects on support for Signed Attestation for Priority and Emergency Sessions | TEI17_SAPES | March 2021 | Sept 2021 | 100% | CP-210272
Legend Green row – Newly completed
Yellow row – on time for completion Red row – at risk for completion on time, below 70%
98 – no progress since the last plenary
98 - Updated

## Slide 10: Work Plan Rel-17
Name | Acronym | Start | End | % | WID
CT1 aspects of eNS_Ph2 | eNS_Ph2 | March 2021 | March 2022 | 30% | CP-210288
CT1 aspects of 5G_eLCS_ph2 | 5G_eLCS_ph2 | March 2021 | March 2022 | 0% | CP-210075
CT1 aspects of 5G eEDGE | eEDGE_5GC | March 2021 | March 2022 | 40% | CP-210284
Legend Green row – Newly completed
Yellow row – on time for completion Red row – at risk for completion on time, below 70%
98 – no progress since the last plenary
98 - Updated

## Slide 11: TS/TR sent to CT plenary
TDoc # | Title | Version | Rapporteurs | Sent for
CP-211122 | 24.811 - Study on the CT aspects of Support for Minimization of service Interruption | 2.0.0 | LG Electronics | approval

## Slide 12: Status of older releases
Rel-14: 5 CAT F CRs for Mission Critical work items agreed
Rel-15: 2 CAT F CRs for Mission Critical work items agreed

## Slide 13: Release 16 Status
All Rel-16 work items are complete.
15 CAT F CRs against Rel-16 agreed , fixing FASMO and aligning with stage-2 (previous quarter had 43 agreed CRs)

## Slide 14: Backward Incompatible Changes
In “Frozen” specification, with impact on other TSG WGs
TDoc # | Title | Source | Impacted TS | Impacted TSG WG
C1-213917 | Addition of ATSSS Rule ID and individual rule modification | Ericsson, Nokia, Nokia Shanghai Bell | 24.193 (Rel-16) | RAN5

## Slide 15: Release 17 Status - Statistics
253 CRs were agreed for Release 17
69 pCRs were agreed for Release 17
2 CRs on "inclusive language review" were agreed
4 new work items under CT1 lead were agreed

## Slide 16: Release 17 Status - Studies
Study on enhanced IMS to 5GC Integration Phase 2
  CT wide study with TR in CT1, CT3, CT4
  CT1 aspects did not progress in Q2, still at 15%
CT1 aspects for Enabling Edge Applications
  Two potential candidate solutions have been discussed for EDGE4
  TS 24.558 contains an Annex B that is supposed to contain potential protocol candidates
  Potential candidates are
    API based solution
    NAS based solution
  So far very slow progress for pCRs on EDGE-4 due to lack of consensus
  Conclusion to be made in upcoming CT1 meetings
CT aspects of 5GC architecture for satellite networks
  CT1 has study phase, documented in TR 24.821
  TR not sent to June plenary for approval, plan is to sent it for approval to September plenary

## Slide 17: Release 17 Status - Studies
Study on the support for minimization of service interruption
  TR 24.811 sent for approval to CT#92e
  TR 24.811 is seen 95% complete
  Conclusion on a network-based solution for key issue #6 is outstanding, will be completed during normative phase (TR contains a UE based solution for KI#6)

## Slide 18: For Information to CT
CT1 had elections for Chair and one ViceChair
  CT1#129-e
    Peter got re-elected as CT1 Chair
  CT1#130-e
    Jörgen got re-elected as CT1 VC
CT1 will have elections for
  one ViceChair during CT1#131e
CT1 has a new MCC
  Andrijana started in CT1#130e

## Slide 19: For Action to CT
Scope of 24.519 “5G System (5GS); Time-Sensitive Networking (TSN) Application Function (AF) to Device-Side TSN Translator (DS-TT) and Network-Side TSN Translator (NW-TT) protocol aspects; Stage ” changes in Rel-17
  Change of scope required by work item “Support of Enhanced Industrial IIoT” (CP-211114), also requires change of title of the TS
  change of title is not possible, as there is a Rel-16 version of the spec, and the new title / scope would not be ok for this release
  solution is to create a new spec in Rel-17, which contains the existing content of 24.519
  CP-211174 coming to CT#92e deletes the content of 24.519 and adds a pointer to the new spec TS 24.XXX
  apart from this CR, all other approved CRs to 24.519 are implemented, this will be saved as 24.XXX v17.1.0
  implement the deletion CR to 24.519, there will be no upgrade to Rel-18
  same process as for some mission critical specifications in Rel-14, e.g. TS 24.483
-> CT is asked to approve the creation of new TS using the process described on this slide

## Slide 20: Experience with e-meeting
High number of emails resulted in very busy meetings:
  CT1#129-e roughly 3100 emails
  CT1#130-e roughly 4200 emails
Conference calls
  Used GoTo Meeting, alternating timeslot 13:00 UTC to 15:00 UTC
  Useful to find way forward
Decision making over email not always easy
  sometimes slow (different timezones), no f2f offline discussion
  as a consequence, complex topics are more easily shifted out of the meeting

## Slide 21: Some stats, number of tdocs
January 2020 meetings not shown
E-meetings in February 2020 and April 2020 had limited scope
E-meeting in November 2020 only 6 days
January/ April 2021 with limited scope
Chart: Number of tdocs in CT1
| Jan 2018 | Feb 2018 | Apr 2018 | May 2018 | Jul 2018 | Aug 2018 | Oct 2018 | Nov 2018 | Jan 2019 | Feb 2019 | Apr 2019 | May 2019 | Aug 2019 | Oct 2019 | Nov 2019 | Feb 2020 e | April 2020 e | June 2020 e | Aug 2020 e | Oct 2020 e | Nov 2020 e | Jan 2021 e | Feb 2021 e | April 2021 e | May 2021 e
begin of meeting | 377 | 400 | 422 | 472 | 531 | 404 | 548 | 479 | 350 | 376 | 438 | 450 | 720 | 535 | 525 | 571 | 562 | 765 | 632 | 614 | 448 | 270 | 650 | 377 | 658
end of meeting | 710 | 725 | 801 | 812 | 884 | 771 | 969 | 895 | 643 | 703 | 750 | 839 | 1135 | 920 | 940 | 840 | 895 | 1168 | 1006 | 961 | 770 | 441 | 991 | 583 | 1169

## Slide 22: Some stats, agreed CRs/pCRs
January 2020 meetings not shown
E-meetings in February 2020 and April 2020 had limited scope
E-meeting in November 2020 only 6 days
January/ April 2021 with limited scope
Chart: CT1 - agreed CR/pCR
| Aug_2019 | Oct_2019 | Nov_2019 | Feb-e_2020 | April-e_2020 | June-e_2020 | August-e_2020 | October-e_2020 | November-e_2020 | January-e_2021 | February-e_2021 | April-e_2021 | May-e_2021
agreedCR | 244 | 207 | 213 | 194 | 304 | 394 | 325 | 259 | 198 | 30 | 237 | 84 | 262
agreedpCR | 92 | 95 | 59 | 107 | 42 | 36 | 1 | 14 | 13 | 75 | 63 | 74 | 69

## Slide 23: Acknowledgement
The CT1 Chairman wants to thank
Lena Chaponniere for chairing the breakout stream on “Services” topics
Jörgen Axell for chairing the breakout stream on “IMS and MC” topics
Andrijana Brekalo for excellent support before, during and after the meetings
Frédéric Firmin for excellent support before, during and after the meetings
Most important the CT1 delegates for their dedication and hard work during very busy and demanding electronic meetings

## Slide 24: Annex

## Slide 25: CRs for conditional approval (I)
TDoc # | Title | Spec | CR# | Dependancy
C1-213629 | Correct MCVideo MOs R14 | 24.483 | 0100 | 24.484-0178
C1-213631 | Correct MCVideo user profile R15 | 24.483 | 0101 | 24.484-0179
C1-213633 | Correct MCVideo user profile R16 | 24.483 | 0102 | 24.484-0180
C1-213635 | Correct MCVideo user profile R17 | 24.483 | 0103 | 24.484-0181
C1-213750 | Correction to AT Commands for NR V2X | 27.007 | 0731 | 38.509-0035 38.509-0035
C1-213751 | Correction to AT Commands for NR V2X | 27.007 | 0732 | 38.509-0035 38.509-0036
C1-213611 | S-CSCF reselection in eIMS | 24.229 | 6526 | 23.380-0115
C1-213612 | S-CSCF reselection in eIMS | 24.229 | 6527 | 23.380-0115
C1-212925 | Control of PTP functionality in DS-TT and NW-TT | 24.519 | 0024 | 23.501-2690
C1-213735 | Correction on DS-TT/NW-TT Ethernet port and replacement of "bridge" with "user plane node" | 24.519 | 0027 | 29.244-0548

## Slide 26: CRs for conditional approval (II)
TDoc # | Title | Spec | CR# | Dependancy
C1-212445 | Emergency services in an SNPN | 24.501 | 3144 | 23.501-2649
C1-213016 | Emergency service fallback and SNPN | 24.501 | 3205 | 23.501-2649
C1-213027 | Inter-network mobility | 24.501 | 3206 | 23.501-2815 23.501-2826
C1-213772 | Emergency registration to an SNPN by a UE in the limited service state or no SIM state | 23.122 | 0703 | 23.501-2649 23.167-0360
C1-213854 | Update of registration procedure for SNPN case | 24.501 | 3258 | 23.502-2641
C1-213875 | Onboarding in SNPN - initial registration | 24.501 | 3203 | 23.501-2562
C1-213877 | Onboarding in SNPN - slicing in initial registration | 24.501 | 3204 | 23.501-2562
C1-213881 | Reject handling of registration for SNPN onboarding | 24.501 | 3319 | 23.501-2562
C1-213882 | Slice handling in registration for SNPN onboarding | 24.501 | 3320 | 23.501-2562 23.501-2709
C1-213883 | De-registration for SNPN onboarding registered UE | 24.501 | 3321 | 23.501-2755

## Slide 27: CRs for conditional approval (III)
TDoc # | Title | Spec | CR# | Dependancy
C1-213884 | DNN/S-NSSAI providing in PDU session establishment for SNPN onboarding | 24.501 | 3322 | 23.501-2562 23.501-2709
C1-213885 | PVS information providing in PDU session establishment for onboarding | 24.501 | 3323 | 23.501-2832 23.501-2802
C1-213886 | PVS information providing in PDU session establishment for onboarding | 24.501 | 3268 | 23.501-2832 23.501-2802
C1-213902 | Mobility registration update upon entering a new SNPN | 23.122 | 0710 | 23.501-2815
C1-213918 | Onboarding in SNPN - mobility registration update | 24.501 | 3211 | 23.501-2562
C1-213929 | Selection for onboarding in SNPN | 23.122 | 0711 | 23.501-2562
C1-213748 | Indication of UE supporting 3GPP access leg in EPC during MA PDU session establishment procedure | 24.501 | 3194 | 23.502-2719
C1-213749 | EPS interworking if UE supporting 3GPP access leg in EPC of an MA PDU session | 24.193 | 0038 | 23.502-2719
C1-213773 | Introduction of performance measurement for a certain target QoS flow and UE assistance data provisioning | 24.193 | 0029 | 24.193-0030
C1-213776 | Support of UE assistance data in PMFP | 24.193 | 0036 | 23.501-2647

## Slide 28: CRs for conditional approval (IV)
TDoc # | Title | Spec | CR# | Dependancy
C1-213778 | PMFP message transport associated with QoS flow | 24.193 | 0037 | 23.501-2721
C1-213791 | Support of packet loss rate measurement | 24.193 | 0030 | 23.501-2840
C1-213813 | Add target QoS flow capability for access performance measurement | 24.501 | 3248 | 23.501-2720
C1-213606 | Remove paging restriction via Registration | 24.501 | 3166 | 23.501-2553
C1-213607 | Remove paging restriction via TAU | 24.301 | 3522 | 23.401-3622
C1-213657 | Considering paging restrictions while paging the UE that is MUSIM capable in 5GS | 24.501 | 3224 | 23.502-2558
C1-213660 | Using Service Request procedure for removing paging restrictions in 5GS for a Multi-USIM UE | 24.501 | 3226 | 23.502-2724
C1-213805 | Leaving procedure and Reject Paging Indication for Multi-USIM UEs in EPS | 24.301 | 3534 | 23.401-3622
C1-213806 | Updates to Registration procedure for MUSIM Leaving in 5GS | 24.501 | 3267 | 24.301-3534 23.502-2724 24.501-3268
C1-213809 | Updates to Service Request for MUSIM Leaving and Reject Paging in 5GS | 24.501 | 3268 | 23.401-3534 23.502-2724 23.502-2558

## Slide 29: CRs for conditional approval (V)
TDoc # | Title | Spec | CR# | Dependancy
C1-213847 | Introducing IMSI Offset to Attach and TAU procedures for MUSIM handling in EPS | 24.301 | 3527 | 23.401-3618
C1-213956 | Multi-USIM UE support indications in EPS | 24.301 | 3514 | 23.401-3622 23.401-3630
C1-213957 | Multi-USIM UE support indications in 5GS | 24.501 | 3121 | 23.501-2553
C1-213958 | Maximum number of established PDU sessions already reached for a NW slice | 24.501 | 3213 | 23.502-2591
C1-213744 | Send REGISTRATION COMPLETE message only if the SOR information is received | 23.122 | 0724 | 24.501-3303
C1-213745 | Send REGISTRATION COMPLETE message only if the SOR information is received | 24.501 | 3303 | 23.122-0724
C1-213737 | MMTEL Voice and MMTEL Video in non-3GPP | 24.501 | 3050 | 24.502-0186 24.173-0146
C1-213738 | MMTEL Voice and MMTEL Video in non-3GPP | 24.502 | 0186 | 24.501-3050 24.173-0146
C1-213740 | MMTEL Voice and MMTEL Video in non-3GPP | 24.173 | 0146 | 24.501-3050 24.502-0186
C1-213850 | PDU session establishment for NR satellite access | 24.501 | 3348 | 23.502-2623

## Slide 30: CRs for conditional approval (VI)
TDoc # | Title | Spec | CR# | Dependancy
C1-213638 | Location information; mid-call access change | 24.229 | 6411 | 32.260-0423

## Slide 31: Thank You!
Peter Leis
3GPP TSG CT WG1 Chairman
peter.leis@nokia.com