## Slide 1: CT WG3 Status Report to TSG CT#93e
Susana Fernández
TSG CT WG3 Outgoing Chair
Ericsson

## Slide 2: TSG CT3 Officials in CT3#117e meeting
Susana Fernández
CT3 Chair
susana.fernandez@ericsson
Yoshihiro Inoue
CT3 Vicechair yoshihiro.inoue@ntt-at.co.jp
Huang Zhenning
CT3 Vicechair
huangzhenning@chinamobile.com
Achraf Khsiba
Secretary
MCC
Achraf.KHSIBA@3gpp.org

## Slide 3: New TSG CT3 Officials
Yali Yan
CT3 Chair
yanyali@huawei.com
Narendranath Durga Tangudu
CT3 Vice Chair n.tangudu@samsung.com
Susana Fernández
CT3 Vice Chair
susana.fernandez@ericsson.com
Achraf Khsiba
Secretary
MCC
Achraf.KHSIBA@3gpp.org

## Slide 4: Meeting Calendar
Since the last CT plenary
  Ordinary (complete Agenda):
    CT3#117E (August 18th – 27th)
Upcoming Meetings
  Ordinary (Agenda TBA):
    CT3#118E (October 11th- 15th)
    CT3#119E (November 11th- 19th)

## Slide 5: TSG WG CT3 Statistics
CT3#117e:
Number of handled documents
  621 documents allocated
Agreed CRs
  Cat B/C/F : 79/0/106
Agreed pCRs
  62
Attendances
  176 registered/ 176 attendants

## Slide 6: New/Revised agreed Study/Work Items led by CT3
TDoc # | Title | Source | Objectives | Release
CP-212163 | CT aspects on Dynamically Changing AM Policies in the 5GC (rev) | Ericsson | The objective of this work item is to develop the Stage 3 specifications to enable the dynamic change of AM policies as specified by Stage 2. Revised to add Huawei as supporting company. | Release 17
CP-212165 | CT aspects on Dynamic Management of Group-based Event Monitoring (rev) | Ericsson | The objective of this work item is to develop the Stage 3 specifications to enable the Dynamic management of group-based event monitoring as specified by Stage 2. Revised to add 5GS scope based on the Stage 2 revised WID SP-210364. | Release 17

## Slide 7: Work Plan – CT3 Driven – Release 17 (i)
Name | Acronym | Start | End | % | WID
Stage 3 of Multimedia Priority Service (MPS) Phase 2 | MPS2 | 2020-06 | 2021-03 | 95 | CP-201207
PFD management enhancement | pfdManEnh | 2020-06 | 2021-06 | 100 | CP-210183
CT aspects on PAP/CHAP protocols usage in 5GS | PAP_CHAP | 2020-09 | 2021-03 | 100 | CP-210188
Authentication and key management for applications based on 3GPP credential in 5G | AKMA-CT | 2020-09 | 2022-03 | 98 | CP-203107
CT aspects for Enabling Edge Applications | EDGEAPP | 2020-12 | 2021-12 | 60 | CP-211196
Legend Green row – Newly completed
Yellow row – for completion on time Red row – at risk for completion on time
98 – no progress since the last plenary
98 - Updated

## Slide 8: Work Plan – CT3 Driven – Release 17 (ii)
Name | Acronym | Start | End | % | WID
CT aspects on Dynamically Changing AM Policies in the 5GC | TEI17_DCAMP | 2021-03 | 2022-03 | 50 | CP-212163
N7 Interfaces Enhancements to Support GERAN and UTRAN | TEI17_NIESGU | 2021-03 | 2021-09 | 100 | CP-211194
CT aspects on Dynamic Management of Group-based Event Monitoring | TEI17_GEM | 2021-03 | 2022-03 | 80 | CP-212165
Enablers for Network Automation for 5G - phase 2 | eNA_Ph2 | 2021-03 | 2022-03 | 30 | CP-211191
Legend Green row – Newly completed
Yellow row – for completion on time Red row – at risk for completion on time
98 – no progress since the last plenary
98 - Updated

## Slide 9: Work Plan – CT3 Driven – Release 17 (iii)
Name | Acronym | Start | End | % | WID
Enhancements of 3GPP Northbound Interfaces and Application Layer APIs | NBI17 | 2021-03 | 2022-03 | 65 | CP-211197
Enhancement of 5G PCC related services in Rel-17 | en5GPccSer17 | 2021-03 | 2022-03 | 35 | CP-211193
Legend Green row – Newly completed
Yellow row – for completion on time Red row – at risk for completion on time
98 – no progress since the last plenary
98 - Updated

## Slide 10: Work Plan – Non-CT3 Driven – Rel-17 (i)
Name | Acrony | Start | End | % | WID
Study on enhanced IMS to 5GC Integration Phase 2 | FS_eIMS5G2 | 2020-06 | 2021-03 | 5 | CP-201168
IMS Stage-3 IETF Protocol Alignment | IMSProtoc17 | 2020-06 | 2021-09 | 70 | CP-201167
Service Based Interface Protocol Improvements Release 17 | SBIProtoc17 | 2020-06 | 2021-09 | 75 | CP-211088
Reliable Data Service Serialization Indication | RDSSI | 2020-12 | 2021-12 | 100 | CP-203234
CT aspects of Access Traffic Steering, Switch and Splitting support in the 5G system architecture; Phase 2 | ATSSS_Ph2-CT | 2021-03 | 2022-03 | 80 | CP-210136
Legend Green row – Newly completed
Yellow row – for completion on time Red row – at risk for completion on time
98 – no progress since the last plenary
98 - Updated

## Slide 11: Work Plan – Non-CT3 Driven – Rel-17 (ii)
Name | Acrony | Start | End | % | WID
CT aspects of enhanced support of industrial IoT | IIoT | 2021-03 | 2022-03 | 65 | CP-212100
CT aspects on Same PCF Selection For AMF and SMF | TEI17_SPSFAS | 2021-03 | 2021-09 | 100 | CP-211184
CT aspects of Enhanced support of Non-Public Networks | eNPN | 2021-03 | 2022-03 | 45 | CP-212103
CT Aspects of 5G eEDGE | eEDGE_5GC | 2021-03 | 2022-03 | 65 | CP-212021
Enhancement of Network Slicing Phase 2 | eNS_Ph2 | 2021-03 | 2022-03 | 40 | CP-210070
CT aspects for Support of Unmanned Aerial Systems Connectivity, Identification, and Tracking | ID_UAS | 2021-03 | 2022-03 | 20 | CP-211112
Legend Green row – Newly completed
Yellow row – for completion on time Red row – at risk for completion on time
98 – no progress since the last plenary
98 - Updated

## Slide 12: Work Plan – Non-CT3 Driven – Rel-17 (ii)
Name | Acrony | Start | End | % | WID
Enhancement to the 5GC Location Services - Phase 2 | 5G_eLCS_ph2 | 2021-03 | 2022-03 | 10 | CP-211090
CT aspects of Enhancement for Proximity based Services in 5GS | 5G_ProSe | 2021-03 | 2022-03 | 65 | CP-212105
BEst Practice of PFCP | BEPoP | 2021-03 | 2022-03 | 85 | CP-212024
CT aspects of 5GC architecture for satellite networks | 5GSAT_ARCH-CT | 2021-03 | 2021-09 | 80 | CP-210149
CT aspects of Enhanced application layer support for V2X services | eV2XAPP | 2021-03 | 2022-03 | 50 | CP-211109
CT aspects on support for Signed Attestation for Priority and Emergency Sessions | TEI17_SAPES | 2021-03 | 2021-09 | 100 | CP-210143
Legend Green row – Newly completed
Yellow row – for completion on time Red row – at risk for completion on time
98 – no progress since the last plenary
98 - Updated

## Slide 13: Work Plan – Non-CT3 Driven – Rel-17 (iii)
Name | Acrony | Start | End | % | WID
CT Aspects of Application Layer Support for Uncrewed Aerial Systems (UAS) | UASAPP | 2021-06 | 2022-03 | 30 | CP-211111
CT aspects of the architectural enhancements for 5G multicast-broadcast services | 5MBS | 2021-06 | 2022-03 | 0 | CP-212022
Enhanced Service Enabler Architecture Layer for Verticals | eSEAL | 2021-06 | 2022-03 | 10 | CP-212098
CT aspects of Architecture enhancements for 3GPP support of advanced V2X services - Phase 2 | eV2XARC_Ph2 | 2021-06 | 2022-03 | 0 | CP-211116
System enhancement for redundant PDU session | TEI17_SE_RPS | 2021-08 | 2022-03 | 0 | CP-212099
CT aspects for enabling MSGin5G Service | 5GMCRCH | 2021-08 | 2022-03 | 0 | CP-212106
Legend Green row – Newly completed
Yellow row – for completion on time Red row – at risk for completion on time
98 – no progress since the last plenary
98 - Updated

## Slide 14: TS/TR sent to CT plenary
TDoc # | Title | Version | Rapporteur | Sent for
CP-212164 | 3GPP TS 29.558 | 1.0.0 | Samsung | Information

## Slide 15: Pre-Release 16 Status
There were no submitted pre-Release 15 CRs
For Release 15, 8 CRs were agreed
  There were only contributions for 5GS_Ph1-CT (7) & NAPS-CT (1).
  Most of the topics correct overlooked issues
    Wrong resource names or data types, misalignment between OpenAPI specification and main body of the TS, etc.
    Corrections on applicability and conditional use of attributes
  Corrections not considered as FASMO were moved to further releases

## Slide 16: Release 16 Status
18 agreed CRs (cat F) in Release 16
Contributions handled for en5GPccSer, eNA, Vertical_LAN, 5WWC, 5G_eLCS, RACS, eV2XARC, 5G_URLLC, eNAPIs, xBDT, eIMS5G_SBA and TEI16 for PC.
  Most relevant discussions related to:
    Handling of PDU session id in N7 interface (5GPccSer WI)
    Support of TCP/UDP ports as part of Non-3GPP location (5GPccSer WI)
    Correction in the Policy Provisioning request procedures (eV2XARC WI)
    report of user location/time in N5 interface (eIMS5G_SBA WI) and
    applicability of User Location Info values in RADIUS interworking (TEI16 for PC).
  Handling of corrections related to wrong resource URIs, attribute names, description of attributes, cardinality, etc.

## Slide 17: Release 17 Status (I) - General
2 new endorsed WIDs
2 revised agreed WIDs, 7 revised endorsed WIDs
Significant work for the already agreed/endorsed WIDs
Dependencies with ongoing Stage 2 work: potential work to be confirmed and several LSs submitted.
A lot of work expected in the upcoming meetings
Work plans presented by companies for several WIs to describe impacts and plans for completion of the work
189 agreed CRs, 62 agreed pCRs

## Slide 18: Release 17 Status (II) – CT3-driven WIs
MPS2 WI reported as 95% complete
  CRs to both EPC & 5G PCC TSs to align MPS for DTS support with stage 2.
pfdManEnh WI already reported as 100%
  Two CR agreed in this cycle.
AKMA-CT WI reported as 98%
  Discussions open about the handling of error cases for error case in AKMA Application Key Retrieval
PAP_CHAP WI reported as 100%
  One CR to correct PAP_CHAP description for legacy DN-AAA was agreed.

## Slide 19: Release 17 Status (III)- CT3 Owned WIs
EDGEAPP WI reported as 60%
  Some progress on registration, service continuity and capability exposure aspects (several services for EES APIs & ECS APIs).
  TS 29.558 sent to the CT Plenary for Information.
TEI17_DCAMP WI reported as 50%
  Significant work going beyond the planned work plan.
  New TS 29.534 on track.
  Impacts on Npcf, Nbsf, Nnef & Nudr services agreed.
  Introduction of the impacts in the related/new flows in TS 29.513.

## Slide 20: Release 17 Status (III)- CT3 Owned WIs
TEI17_NIESGU WI reported as 100%
  No CRs in this Plenary cycle.
TEI17_GEM WI reported as 80%
  Updates on the support of GEM partial cancellation.
eNA_Ph2 WI reported as 30%
  Smooth progress for the 4 new TSs (DCCF services, ADRF services, MFAF services, network data analytics signalling flows).
  Progress on the impacts for Naf & Nnef services (e.g. collective behaviour analytics, performance data event) and Nwdaf services (e.g. User data congestion analytics, aggregation support).

## Slide 21: Release 17 Status (IV)- CT3 Owned WIs
NBI17 WI reported as 65%
  Resource root structure updated in NB APIs as per discussions with CT4
  Optional support of load/overload control in NB APIs
  Other miscellaneous corrections (e.g. missing 204 No Content, removing unbreakable spaces, etc.)
en5GPccSer17 WI reported as 35 %
  Contributions related to alignment with EPC functionality (UE initiated resource modification procedure, PCC rule authorization with preliminary Service info)
  Support of 5G level UE identities in Rx

## Slide 22: Release 17 Status (IV)- CT3 Non-driven WIs
SBIProtoc17 WI reported as 75%
  Most CRs related to correct the URI structure as discussed and agreed in CT4.
  Progressive increase of the percentage of completion in every meeting.
IMSProtoc17 WI reported as 70%
  No contributions during this Plenary cycle.
  Progressive increase of the percentage of completion in every meeting.

## Slide 23: Release 17 Status (V)- CT3 Non-driven WIs
TEI17_SPSFAS WI reported as 100%
  No contributions submitted in this CT3 meeting.
ATSSS_Ph2 WI reported as 80%
  Minor agreed contributions to complete/correct TS 29.512.
IIoT WI reported as 65%
  Work focused on the introduction of TSCTSF support in existing TSs and in the new dedicated TS for the definition of Ntsctsf Service.

## Slide 24: Release 17 Status (VI)- CT3 Non-driven WIs
eNS_Ph2 WI reported as 40%
  Work focused on the support of UE-Slice-MBR & Slice-MBR. LS to SA2 for the support of Nnef_SliceStatus.
eEDGE_5GC WI reported as 65%
  Support of Uplink buffering indication for application relocation
  Completion and correction for ECS Address Provisioning.
  Support of duplicated notifications (PCF & AF) from the SMF.
BEPoP WI reported as 85%
  Completion and correction of L2TP procedures.

## Slide 25: Release 17 Status (VII)- CT3 Non-driven WIs
5GSAT_ARCH WI reported as 80%
  Clarification of Satellite backhaul procedures in TS 29.512 and 5QI values in TS 29.513.
TEI17_SAPES WI reported as 100%
  Support of IBCF RPH signing for MPS
UASAPP WI reported as 30%
  TS 29.257 smoothly progressing.
  Introduction of UAE_C2Operation ModeManagement API

## Slide 26: Release 17 Status (VIII)- CT3 Non-driven WIs
ID_UAS WI reported as 20%
  Introduction of UAV presence monitoring. First version of new TS 29.255.
eNPN WI reported as 45%
  Work focused on the introduction of IMS emergency services for SNPN in PCC interfaces.
5G_eLCS_ph2 WI reported as 10%
  Support for Multiple QoS Class in deferred location request in NB APIs.
5G_ProSe WI reported as 65%
  Progress on the new TS 29.557, introduced impacts on DCAMP TS 29.534. Corrections on ProSe Policy Provisioning procedures.

## Slide 27: Release 17 Status (VIII)-CT3 Non-driven WIs
eSEAL WI reported as 10%
  Handling of SEAL groups.
Quite a few contributions to enhance functionality & descriptions for different WIs (TEI17 + WI code CRs).
Remaining WIs had no progress during this Plenary Cycle.

## Slide 28: Backward Incompatible Changes
None

## Slide 29: For Information to CT
CT3 election process took place with the following outcome:
  Chair position:
    Dr. Yali Yan HuaWei Technologies Co., Ltd / CCSA.
  Vice Chair positions
    Mr. Narendranath Durga Tangudu Samsung Electronics Co. Ltd. / TTA
    Mrs. Susana Fernandez Ericsson GmbH, Eurolab / ETSI
CT3 work focused on:
  Agreeing/endorsing quite a few new/revised Release 17 Work Items.
  Starting or progressing work for the agreed/endorsed WIDs.
  Introducing corrections for Release 16 & Release 15.
Plenty of work expected during the coming meetings to progress the Work Items.
  Still a strong dependency with the stage 2 progress:
    4 LSs to SA2 and 1 LS to SA4 sent.
  Work for pre-Release 17 contributions is being reduced.
Work estimated to be completed on time.
  Work plans estimations for existing Work Items do not show any risk.
E-meeting experience improves in each meeting
  Still the process is quite time consuming and reaching agreements is more difficult than in f2f meetings.

## Slide 30: For Action to CT
No identified action

## Slide 31: Acknowledgement
The Outgoing Chair wants to thank
  Outgoing Vice Chairmen Yoshihiro and Huang Zhenning for helping in the CT3 management.
  MCC Achraf Khsiba for his big effort and good work in his first CT3 meeting, working hard to support CT3 before, during and after the meeting.
  ETSI support for IT facilities.
  All CT3 delegates, and specially TS rapporteurs, for their hard work, professionalism and commitment for the success of this challenging meeting.
  CT WG Chairs, CT Chair and MCCs for helping with the good practices in the handling of e-meetings and coordination activities.
The Outgoing Chair wants to congratulate the new CT3 Officials (welcome Yali & Naren!)

## Slide 32: Annex

## Slide 33: CRs for conditional approval (I)
TDoc # | Title | Spec | CR# | Dependency
C3-214491 | PDU session policy data extension for UE-Slice-MBR | TS 29.519 | #0261 | TS 29.504 CR #0148
C3-214485 | Support for Multiple QoS Class in deferred location request | TS 29.122 | #0491 | TS 29.572 CR#0114
C3-214411 | IBCF RPH signing for MPS | TS 29.165 | #1030 | TS 24.229 CR#6528
C3-214594 | Support of TCP and UDP ports in non-3GPP UE location | TS 29.214 | #1662 | TS 29.571 CR#0294
C3-214595 | Support of TCP and UDP ports in non-3GPP UE location | TS 29.214 | #1663 | TS 29.571 CR#0295
C3-214596 | Support of TCP and UDP ports in non-3GPP UE location | TS 29.512 | #0816 | TS 29.571 CR#0294
C3-214597 | Support of TCP and UDP ports in non-3GPP UE location | TS 29.512 | #0817 | TS 29.571 CR#0295

## Slide 34: CRs for conditional approval (II)
TDoc # | Title | Spec | CR# | Dependency
C3-214598 | Support of TCP and UDP ports in non-3GPP UE location | TS 29.514 | #0332 | TS 29.571 CR#0294
C3-214599 | Support of TCP and UDP ports in non-3GPP UE location | TS 29.514 | #0333 | TS 29.571 CR#0295
C3-214530 | Correction to V2X Policy Provisioning Request | TS 29.513 | #0285 | TS 23.503 CR#0613
C3-214531 | Correction to V2X Policy Provisioning Request | TS 29.513 | #0286 | TS 23.503 CR#0614
C3-214532 | Correction to V2X Policy Provisioning Request | TS 29.525 | #0162 | TS 23.503 CR#0613
C3-214533 | Correction to V2X Policy Provisioning Request | TS 29.525 | #0163 | TS 23.503 CR#0614

## Slide 35: Thank You!
Susana Fernández
3GPP TSG CT WG3 Outgoing Chair
Susana.fernandez@ericsson.com