## Slide 1: CT view on Rel-19 Planning
Mr Lionel Morand
CT Chair, Orange

## Slide 2: Release 18 Planning
Discussion on Release 18 stage 2 extension at SA#98
  CT Hardline:
    Ensure 9 months between stage 2 freeze and the stage 3 freeze
    Ensure 3 months between stage 3 freeze and ASN.1/OpenAPI freeze
    Common CT stage 3/RAN functional freeze date and ASN.1/OpenAPI freeze date
Approved freeze dates
  Stage 2: June 2023 (TSG#99)
  Stage 3: March 2024 (TSG#102)
  ASN.1/OpenAPI: June 2024 (TSG#103)

## Slide 3: CT view on Rel-19 timeline (1/3)
Hardline (still enforced):
Ensure 9 months between stage 2 freeze and the stage 3 freeze
  To grant enough time for TSG cross-coordination.
  For CT, Stage 2 requirements coming from SA2 but also from SA3, SA4, SA5, SA6
Ensure 3 months between stage 3 freeze and ASN.1/OpenAPI freeze
  To avoid protocol backward incompatible change and provide some buffer protocol consolidation
Common CT stage 3/RAN functional freeze date and ASN.1/OpenAPI freeze date

## Slide 4: CT view on Rel-19 timeline (2/3)
Taking into account:
  Rel-18 planning shift (+3 months):
    Stage 3 freeze: March 2024
    OpenAPI/ANS.1 freeze: June 2024
  Working assumptions:
    Completed Rel-19 functional scope: December 23
    RAN position regarding ASN.1 freeze: December 2025
  SA responsible for the decision on stage 2 freeze date but will impact the stage 3 freeze and the OpenAPI/ASN.1 freeze dates.
  SA/RAN/CT must remain in sync. TSG coordination required for final decision on the Rel-19

## Slide 5: CT view on Rel-19 timeline (3/3)
This would mean for CT:
  OpenAPI/ASN.1 freeze: December 2025
    To keep in sync RAN and CT
  Stage 3 freeze: September 2025
    3-month gap between Stage 3 and coding freeze dates
    18-month release timeframe from Rel-18 Stage 3 freeze
      including enough time for Rel-18 consolidation
  (expected) Stage 2 freeze: December 2024
    With 9-month gap between stage 2 and the stage 3 freeze dates
    Stage 2 freeze date under the responsibility of SA

## Slide 6: Thank You!
Lionel Morand
3GPP TSG CT Chair
ETSI
lionel.morand@orange.com