## Sheet1
Subclause number in 23.282 | Subclause title | Affected TS handled by CT1 on MC | TS Rapporteur (company) | Expected affected subclause in 24.xyz | Assigned to | status (%) #102 | status (%) #103 | Notes | Issues / Comments
7.1 | MCData Service Configuration | 24.483, 24.484 | 24.483 (LG) 24.484 (Blackberry) |  | ? Samsung | 0 | 25% |  | no one is working on 24.483
7.2 | Affiliation and de-affiliation to/from MCData group(s) | 24.282 | 24.282 (Samsung) | 8 | Samsung | 0 | 0% |  | will be reused from 24.379
7.3 | Use of MBMS transmission | 24.282, 24.582 | 24.282 (Samsung) 24.582 (MSI tmp.) | 10.2.7.2 in 24.282 11 in 24.582 |  | 0 |  | Signaling plane messaging in 24.282, media plane control messaging and usage in 24.582 See also 10.7 of 23.280 | Is MBMS applicable for SDS?
7.4.2.2 | One-to-one standalone short data service using signalling control plane | 24.282 | 24.282 (Samsung) | 9.2.2 | Samsung | 70 | 90% |  | one-to-one and group procedures are written in the same framework
7.4.2.3 | One-to-one standalone short data service using media plane | 24.282, 24.582 | 24.282 (Samsung) 24.582 (MSI tmp.) | 9.2.3 6.1.1, 6.2.1, 6.3.1 | Samsung MSI | 20 | 90% 70% | 24.282 except for media plane control and delivery in 24.582 | one-to-one and group procedures are written in the same framework
7.4.2.4 | One-to-one short data service session | 24.282, 24.582 | 24.282 (Samsung) 24.582 (MSI tmp.) | 9.2.4 6.1.2, 6.2.2, 6.3.2 | Samsung MSI | 20 | 20% 0% | 24.282 except for media plane control and delivery in 24.582
7.4.2.5 | Group standalone short data service using signalling control plane | 24.282 | 24.282 (Samsung) | 9.2.5 | Samsung | 70 | 90% |  | one-to-one and group procedures are written in the same framework
7.4.2.6 | Group standalone short data service using media plane | 24.282, 24.582 | 24.282 (Samsung) 24.582 (MSI tmp.) | 9.2.6 6.1.1, 6.2.1, 6.3.1 | Samsung MSI | 20 | 90% 70% | 24.282 except for media plane control and delivery in 24.582 | one-to-one and group procedures are written in the same framework
7.4.2.7 | Group short data service session | 24.282, 24.582 | 24.282 (Samsung) 24.582 (MSI tmp.) | 9.2.7 6.1.2, 6.2.2, 6.3.2 | Samsung MSI | 20 | 0% 0% | 24.282 except for media plane control and delivery in 24.582
7.4.3.3 | One-to-one standalone short data service using signalling control plane | 24.282 | 24.282 (Samsung) | 9.3.2 | Samsung | 0 | 80% | Off-network | one-to-one and group procedures are written in the same framework
7.4.3.4 | Group short data service using signalling control plane | 24.282 | 24.282 (Samsung) | 9.3.2 | Samsung | 0 | 80% | Off-network | one-to-one and group procedures are written in the same framework
7.5.2.2 | File upload using HTTP | 24.282 | 24.282 (Samsung) | 10.2.2 | Samsung | 0 | 0%
7.5.2.3 | File download using HTTP | 24.282 | 24.282 (Samsung) | 10.2.3 | Samsung | 0 | 0%
7.5.2.4 | One-to-one file distribution using HTTP | 24.282 | 24.282 (Samsung) | 10.2.4 |  | 0
7.5.2.5 | One-to-one file distribution using media plane | 24.282, 24.582 | 24.282 (Samsung) 24.582 (MSI tmp.) | 10.2.5 subclause under 7 in 24.582 |  | 0 |  | 24.282 except for media plane control and delivery in 24.582
7.5.2.6 | Group standalone file distribution using HTTP | 24.282 | 24.282 (Samsung) | 10.2.6 |  | 0
7.5.2.7 | Group standalone file distribution using media plane | 24.282, 24.582 | 24.282 (Samsung) 24.582 (MSI tmp.) | 10.2.7 subclause under 6 in 24.582 |  | 0 |  | 24.282 except for media plane control and delivery in 24.582 | reliable delivery in case of MBMS very probably not to be handled in Rel-14. Does this affect the whole subject of MBMS delivery?
7.6.2.2 | Auto-send data | 24.483, 24.484, 24.282, 24.582 | 24.483 (LG) 24.484 (Blackberry) 24.282 (Samsung) 24.582 (MSI tmp.) | ? ? 11 6.1.2, 6.2.2, 6.3.2 | ? Samsung Samsung MSI | 10 | ? ? 50% 0% | Configuration in 24.483, 24.484, the use of configured parameters and decision making in 24.282 and/or 24.582. | based on the discussions in CT1#103 inconsistencies have been found between stage-1 requrements and stage-2 implemenation. Possible solutions under discussion for way forward. Auto-send procedures in the signalling plane will be reused for SDS session.
7.6.2.3 | Send data with mandatory download | 24.282, 24.582 | 24.282 (Samsung) 24.582 (MSI tmp.) |  |  | 0 |  | No configuration parameters are identified. It may affect both 24.282 and 24.582 for FD
7.6.2.4 | Send data without mandatory download | 24.282, 24.582 | 24.282 (Samsung) 24.582 (MSI tmp.) |  |  | 0 |  | No configuration parameters are identified. It may affect both 24.282 and 24.582 for FD
7.6.2.5 | Accessing list of deferred data group communications | 24.282, 24.582 | 24.282 (Samsung) 24.582 (MSI tmp.) |  |  | 0 |  | This procedure involves only one client and the MCData server | It may be implemented either in the signallig plane or media plane. Preferrably only in one of them
7.7.2.2.2 | Release of MCData communication using media plane | 24.282, 24.582 | 24.282 (Samsung) 24.582 (MSI tmp.) | 13.2.2 subclause under 8 in 24.582 |  | 0 |  | (Initiated by the originating MCData user.) 24.282 except for media plane termination control in 24.582
7.7.2.2.3 | Release of MCData communication using HTTP | 24.282 | 24.282 (Samsung) | 13.2.2 |  | 0 |  | (Initiated by the originating MCData user.)
7.7.2.3.2 | Release of MCData communication using media plane | 24.282, 24.582 | 24.282 (Samsung) 24.582 (MSI tmp.) | 13.2.3 subclause under 8 in 24.582 |  | 0 |  | (Initiated by the MCData server w/o prior indication.) 24.282 except for media plane termination control in 24.582
7.7.2.3.3 | Release of MCData communication using HTTP. | 24.282 | 24.282 (Samsung) | 13.2.3 |  | 0 |  | (Initiated by the MCData server w/o prior indication.)
7.7.2.4 | MCData server initiated communication release with prior indication | 24.282 | 24.282 (Samsung) | 13.2.5 |  | 0
7.7.2.5 | Authorized MCData user initiated communication release without prior indication | 24.282, 24.582 | 24.282 (Samsung) 24.582 (MSI tmp.) | 13.2.4 subclause under 8 in 24.582 |  | 0 |  | 24.282 except for media plane termination control in 24.582
7.7.2.6 | Authorized MCData user initiated communication release with prior indication | 24.282 | 24.282 (Samsung) | 13.2.4 |  | 0
7.8.2.2 | One-to-one conversation management | 24.282 | 24.282 (Samsung) | 6.2.2 |  | 5 | 90% |  | Conversation ID assignment and the use of this ID has been defined. How a conversation is terminated?
7.8.2.3 | Group conversation management | 24.282 | 24.282 (Samsung) | 6.2.2 |  | 5 | 90% |  | Conversation ID assignment and the use of this ID has been defined. How a conversation is terminated?
7.9.3 | Enhanced status for on-network | 24.282 | 24.282 (Samsung) | 14.2 | Samsung | 0 | 0%
7.9.4 | Enhanced status for off-network | 24.282 | 24.282 (Samsung) | 14.3 |  | 0
| Registration to MCData Service | 24.482, 24.282 | 24.482 (MSI) 24.282 (Samsung) | ? 7 in 24.282 | MSI Samsung | 0 | 90% 0% | (see clause 10.6 in the table for 23.280)
| Security Aspects | 24.282, 24.582 | 24.482 (MSI) 24.282 (Samsung) |  |  | 0 | 90% 0% | Security management in 24.282, signalling and madia plane security specifations in 24.282 and 24.582 respectively | Identity management in 24.482 90% completed. The security aspect deepends on the stage-2 outcome from SA3
Subclause number in 23.280 | Subclause title | Affected TS handled by CT1 on MC | TS Rapporteur (company) | Expected affected subclause in 24.xyz | Assigned to | status (%) #102 | status (%) #103 | Notes | Issues / Comments
8 | Identities | 24.482, 24.282. | 24.482 (MSI) 24.282 (Samsung) | ? 7 in 24.282 |  | 0 | 90% 0% | Follow the identity management and relationship between signaling plane and application plane identities as in 24.482 and 24.379 by transforming from MCPTT to MCData. Additions for MCData will go into 24.482 and transforming the material in 24.379 will go into 24.282. | Identity management in 24.482 90% completed. In 24.282 this will be reused from 24.379
10.1 | MC Service configuration | 24.483, 24.484, 24.282 | 24.483 (LG) 24.484 (Blackberry) 24.282 (Samsung) | ? ? All over | Samsung | 0 | 0% 25% 50% | Follow the configuration management as in 24.483, 24.484 and 24.379 by transforming from MCPTT to MCData. Additions for MCData will go into 24.483 and 24.484 and transforming the material in 24.379 will go into 24.282. | no one is working on 24.483
10.2 | Group management (on-network) | 24.481 | 24.481 (Ericsson) |  |  | 0 | 80% | Follow the group management as in 24.481 by adding to MCData (check if MCData specific novelties). Additions for MCData will go into 24.481. | Framework for extending to general MC services implemented by the rapporteur. MCData related material introduced by Samsung
10.3 | Pre-established session (on-network) | 24.282 | 24.282 (Samsung) | 4.3 | Samsung | 0 | 0% | NOTE: Stage-2 does not talk about pre-established sessions for MCData Follow the pre-established session management as in 24.379 by transforming from MCPTT to MCData. Additions for material in 24.379 will go into 24.282. | Normative specification is missing in 24.282 Medi plane control (connect and disconnect messages as in MCPTT) is not well defined
10.4 | Simultaneous session (on-network) | 24.282 | 24.282 (Samsung) |  |  | 0 |  | Session management in 24.282 should cover this | No current allocation in stage-3
10.5 | Use of UE-to-network relay | TBD |  |  |  | 0 |  | TBD | Is this applicable in stage-2
10.6 | General user authentication and authorization for MC Services | 24.482, 24.282 | 24.482 (MSI) 24.282 (Samsung) | 7 in 24.282 | Samsung (for 24.282) | 0 | 90% 0% | The registration and service authorization (clause 7 in 24.379) should be reflected to 24.282 | Identity management in 24.482 90% completed. In 24.282 this will be reused from 24.379
10.7 | Use of MBMS transmission | 24.282, 24.582 | 24.282 (Samsung) 24.582 (MSI tmp.) | 10.2.7.2 under 11 in 24.582 |  | 0 |  | Transform the material in 24.379 into 24.282 and the material in 24.380 into 24.582 (FFS). (Also as stated for subclause (7.3) of 23.282) | No explicit allocation in stage-3 reliable delivery in case of MBMS very probably not to be handled in Rel-14. Does this affect the whole subject of MBMS delivery?
10.8 | Affiliation and de-affiliation to/from MC Service Groups | 24.282 | 24.282 (Samsung) | 8 | Samsung | 0 | 0% | as stated for subclause (7.2) of 23.282 | in 24.282 this will be reused from 24.379
10.9 | Location Management | 24.282 | 24.282 (Samsung) |  |  | 0 |  | should be the same as in 24.379 but not mentioned in 23.282 | No explicit allocation in stage-3
10.10 | Emergency Alert | 24.282 | 24.282 (Samsung) |  |  | 0 |  | should be the same as in 24.379 but not mentioned in 23.282 | No explicit allocation in stage-3
Color-code legend: Topic R14 status | Description
Indicates that no company(s) is assigned to do the work. -Unlikely to make the R14 time frame.
Stage-3 implemenation under risk
Company assigned to do the work -Highly likely to be completed in R14 time frame