## Tdoc cover sheet
3GPP TSG CT WG1 Meeting #123-e Electronic meeting; 16-24 April 2020 |  | C1-202205
Source: | Huawei, HiSilicon
Title: | Work plan for the CT1 part of eV2XARC
Agenda item: | 16.2.13
Document for: | Discussion

## Contributions plan
Contribution Plan
Spec | Topic | Related LS or other WG tdoc(s) # | CT1 meeting #; tdoc(s) # | Comments | Open issues
24.587
| TS skeleton |  | #117; C1-193204
| TS scope |  | #117; C1-193205
| General clause under provisioning of parameters for V2X configuration |  | #120; C1-196377
| V2X Application Server discovery (over Uu communication) | S2-1903308 | #119; C1-194856 | Adds general description on V2X communication over Uu
| Unicast mode communication over PC5 reference point | S2-1904441, S2-1904443 | #119; C1-194855 | Adds general description on V2X communication over PC5
| V2X communication over PC5 reference point | S2-1903020 |  |  | If the UE has an ongoing emergency session via IMS, it shall not trigger any PLMN selection due to V2X communication over PC5 reference point. If the UE has an ongoing emergency session via IMS, the ongoing emergency session via IMS shall be prioritized over V2X communication over PC5 reference point
| PC5 QoS handling for unicast, groupcast and broadcast | S2-1906302 |  | No impact
| V2X Policy and parameters | S2-1906303 | #119; C1-194852 | Adds the configuration parameters for V2X communication over PC5
| V2X communication over Uu Reference Point | S2-1906311 | #119; C1-194856, C1-195048 | Adds general description on V2X communication over Uu and general description of V2X services in 5GS
| Unicast mode communication over PC5 reference point & Identifiers for unicast mode V2X communication over PC5 reference point | S2-1906326, S2-1908200 | #119; C1-194855, C1-195048 | Adds general description on V2X communication over PC5 and general description of V2X services in 5GS
| PC5 unicast; Layer-2 link modification for a unicast linkLayer-2 link establishment over PC5 reference point & Layer-2 link modification for a unicast link | S2-1906327, S2-1908196 | #120; C1-196862, C1-196853, C1-196854
| NR PC5 QoS | S2-1906328 |  | No impact
| Add QoS operation into PC5 procedures | S2-1906330 |  | No impact
| QoS Handling for V2X communication over PC5 Reference Point | S2-1906334
| QoS handling for V2X communication over Uu reference point | S2-1906818
| Groupcast mode communication over PC5 reference point | S2-1907466
| Application Layer ID | S2-1908189 |  | No impact
| Mobility between EPS and 5GS over Uu | S2-1908198
| PC5 unicast link | S2-1908200, S2-1908626 (LS)
| NR PC5 QoS handling | S2-1908214 |  | No impact
| References, definitions and abbreviations |  | #119; C1-194857
| Configuration parameters for V2X communication over Uu |  | #119; C1-195057 | Adds configuration parameters for V2X communication over Uu
| Configuration parameters for V2X communication over PC5 |  | #120; C1-196621, C1-196762 | C1-196621 makes possible that one mapping rule includes one or more V2X service identifiers C1-196762 adds configuration parameters for V2X communication over PC5 related to privacy (see TS 23.287; clause 6.3.3.2)
| Resolution of editor's note under clause 6.1 of TS 24.587 |  | #120; C1-196379
| Handling of PC5 unicast link establishment procedure |  | #121; C1-198632 | Updates the PC5 unicast link establishment procedure
| PC5 unicast link release procedure |  | #121; C1-198634 | Adds the PC5 unicast link release procedure | This needs to be re-submitted as it fails to be incorporated in the latest version of TS 24.587
24.588
| TS skeleton |  | #117; C1-193256
| TS scope |  | #117; C1-193257
| Overview of UE policies for V2X |  | #119; C1-194847 | Overview of UE polocies for V2X and likage to TS 24.501 for the UE policy delivery service (Annex D)
| Descriptions of UE policies for V2X |  | #119; C1-194850 | Adding linkage to TS 24.587 for specification of V2X policy for V2X communication over PC5 and for V2X communication over Uu
| Overall clean-up for TS 24.588 |  | #120; C1-196493
24.301
| NR PC5 QoS modelling and operations in EPC | S2-1908219
| Interworking between EPS V2X and 5GS V2X | S2-1906341 |  | V2X Policy and parameters provisioning
24.501
| UE Configuration Update procedure | S2-1906316
| Service Authorization and Provisioning to UE | S2-1906331, S2-1906342 | #119; C1-194848 | Adding the V2X policy as a code point for the UE policy section management list so that V2X policy(ies) can be transferred from the PCF to the UE
| New UE Policy Control Request Trigger for V2X | S2-1906335 |  |  | “change of PLMN” is not yet defined as a PCRT applied to UE policy
| PCF discovery and selection | S2-1906343 |  | Registration Request message
| Registration and N2 Handover procedure | S2-1906817 |  | No impact
| IP Address Configurations for unicast link establishment procedure | S2-1908195
| V2X Application Server could provide the 5QIs as input based | S2-1908209
| Clarification on PC5 QoS rule | S2-1908215
| PC5 QoS parameters clarifications | S2-1908216
| No NAS signalling release for V2X UE authorized to use PC5 communication | S2-1908217 | #119; C1-194305 (postponed) #120; C1-196626 | Registration procedure and N1 NAS signalling connection release | The issue is to control the release of the N1 NAS signalling connection in the UE so that the UE does not start T3540 for the case when the UE requests resources for V2X communications over PC5 reference point, and for the AMF to not release the N1 NAS signalling connection immediately in that case. Revision of C1-194305 expected at CT1#120. Revision was not provided but a new p-CR in C1-196626 C1-196626 was agreed at CT1#120
| Enhancements to QoS Handling for V2X Communication Over Uu Reference Point | S2-1908223, S2-1908607, S2-1908627 (LS)
| QoS Handling for V2X Communication Over Uu Reference Point | S2-1908225 |  | Registration procedure
| PC5 QoS rule handling and filter definitions | S2-1908227
| V2X capability and V2X PC5 capability |  | #119; C1-195049 | Adds V2X capability and V2X PC5 capability into the 5GMM capability IE
| Annex D update because of V2X |  | #121; C1-198628 | Adds the necessary updates because of V2X for the policy delivery service
| 5QI 86 introduction |  | #121; C1-198629 | Adds a new 5QI for V2X
| Access control for UE triggered V2X policy provisioning procedure |  | #121; C1-198635 | Access control for MO policy request is made enabled
| Expiration time of configuration parameters for V2X communication |  | #121; C1-198636 | Updates the specification to keep compatibility to EPS and allow interworking with EPS for V2X services in 5GS
| Handling of PC5 unicast link modification procedure |  | #121; C1-198817 | Corrects some wording mistakes and adds an abnormal case
| Completion of UE-requested V2X policy provisioning procedure |  | #121; C1-198821 | Updates the UE-requested V2X policy provisioning procedure
| Encoding of direct link establishment messages and parameters |  | #121; C1-198823 | Adds encoding details for the direct link establishment messages
24.526
| UE Configuration Update procedure | S2-1906316
| Specifying and adding reference for V2X Policy |  | #119; C1-194846 |  | Adding linkage to TS 24.588 for the specification of V2X policies
27.007

## Expected contributions
Expected Contributions for future meetings
Spec | Topic | Related LS or other WG tdoc(s) # or TS # | Volunteered company/delegate | Contribution(s) | Open issues
24.587
| To add text for the General clause under provisioning of parameters for V2X configuration |  | Huawei (Christian) | #120; C1-196377
| UE-requested V2X policy provisioning procedure | TS 23.287 | Huawei (Christian) | #120; C1-196861 | The procedure should rely on the UE policy delivery service defined in TS 24.501
| To resolve the editor's note under clause 6.1 |  | Huawei (Christian) | #120; C1-196379
| Resolution of the editor's note on precedence of V2X configuration parameters |  | Huawei (Christian) | #120; C1-198346
| Resolution of editor's note on V2X communication over Uu |  | Huawei (Christian) | #120; C1-198358
| Expiration time of configuration parameters for V2X communication |  | Huawei (Christian) | #120; C1-198475
| V2X communication over PC5 reference point | S2-1903020 | Huawei (Christian) |  | If the UE has an ongoing emergency session via IMS, it shall not trigger any PLMN selection due to V2X communication over PC5 reference point. If the UE has an ongoing emergency session via IMS, the ongoing emergency session via IMS shall be prioritized over V2X communication over PC5 reference point
| V2X communication over Uu reference point | TS 23.287 | Ericsson (Ivo) |  | V2X messages carried over Uu are exchanged using user plane and they can be sent or received over broadcast, unicast or groupcast depending so there may be need to have separate sub-clauses under the transmission of V2X communication over PC5
| PC5 unicast link handling regarding RLF and Update of PC5 Link Identifier description | S2-2000345, related LS in S2-2000976, S2-2000975 | <No volunteer yet> |  | Upon receiving an indication from the AS layer that the PC5-RRC connection was released due to RLF, the V2X layer in the UE locally releases the PC5 unicast link associated with this PC5-RRC connection. The AS layer uses PC5 Link Identifier to indicate the PC5 unicast link whose PC5-RRC connection was released. Add description about using Layer 2 IDs for unicast.
| Clarification on unicast link release | S2-2000347 | <No volunteer yet> |  | When the PC5 unicast link has been released as specified in clause 6.3.3.3, the V2X layer of each UE for the PC5 unicast link informs the AS layer that the PC5 unicast link has been released. The V2X layer uses PC5 Link Identifier to indicate the released unicast link
| Security for V2X communication | S2-2000572, S2-2000953. Related LS in S2-2000971 | Huawei (Christian) |  | Add clarification regarding the use of L2 IDs for security establishment procedure in clause 6.3.3.1. The Link identifier update for unicast link procedure is updated to allow the change of L2 IDs for both UEs at the same time.
| Correction of "set of configuration parameters" in the precedence of the V2X configuration parameters | S2-2000952, related LS in S2-2000970 | Huawei (Christian); #122e; C1-200525 |  | As pointed out in S2-2000019/C1-198822, in TS 24.386 (Stage 3 on V2X protocol for EPS) the "set of configuration parameters" is not considered in the precedence of the V2X configuration parameters. On the contrary, Stage 2 for 5GS V2X includes it in the precedence list. This could lead to interworking issues with EPS V2X.
| QoS | S2-2000346, S2-2000959, S2-2000961, S2-2000979, S2-2000981 | <No volunteer yet> |  | Add description for unicast which information is provided by the V2X layer to the AS layer for per-flow QoS operations, and remove NOTE. In particular, the PC5 Link Identifier for unicast is provided to the AS layer instead of source/destination Layer-2 IDs because it is observed from the following RAN2 agreement@RAN2#108 (R2-1916288: Report from session on LTE V2X and NR V2X) that the AS layer also uses the PC5 Link Identifier for unicast. Clarify to support the non-standardized PC5 QoS characteristics. Add text about PC5 QoS handling for network scheduled operation mode. A new sentence has been introduced to describe the handling of IP/Non-IP packets before they are passed to the AS layer.
| Keep-alive signalling (i.e. Layer-2 link maintenance procedure) in the V2X layer | S2-2000792, related LS in S2-2000973 | OPPO (Rae); #122e; C1-200327
| Updates to the PC5 unicast link modification | S2-2000978 | <No volunteer yet> |  | The PFI is used to identify V2X service, which means the PFI is associated with V2X service(e.g. PSID(s) or ITS-AID(s)). So, for the case of adding new PC5 QoS flows for the existing V2X service(s), initiating UE shall provide the V2X service info and QoS info in the modifacation request message. if not, the target UE can’t make this association. For removing the existing PC5 QoS flows in an existing PC5 unicast link, PFI(s) is enough in the modifacation request message.
24.588
UE policies for V2X communication over Uu for 5GS
| UE policies for V2X communication over PC5 for 5GS |  | Ericsson (Ivo)
24.301
| NR PC5 QoS modelling and operations in EPC | S2-1908219 | <No volunteer yet>
| Interworking between EPS V2X and 5GS V2X | S2-1906341 | <No volunteer yet> | V2X Policy and parameters provisioning
24.501
| UE Configuration Update procedure | S2-1906316 | Huawei (Christian)
| No NAS signalling release for V2X UE authorized to use PC5 communication | S2-1908217 | vivo (Yang) and LG (SangMin) | #119; C1-194305 (postponed) and #120; C1-196494 | The issue is to control the release of the N1 NAS signalling connection in the UE so that the UE does not start T3540 for the case when the UE requests resources for V2X communications over PC5 reference point, and for the AMF to not release the N1 NAS signalling connection immediately in that case. Revision of C1-194305 expected at CT1#120
| Updates to the UE policy delivery service to support the UE-requested V2X policy provisioning procedure | TS 23.287 | OPPO (Rae) | #120; C1-196074
| New UE Policy Control Request Trigger for V2X | S2-1906335 | <No volunteer yet> |  | “change of PLMN” is not yet defined as a PCRT applied to UE policy
| PCF discovery and selection | S2-1906343 | <No volunteer yet> | Registration Request message
| Registration and N2 Handover procedure | S2-1906817 | <No volunteer yet> | No impact
| IP Address Configurations for unicast link establishment procedure | S2-1908195 | <No volunteer yet>
| V2X Application Server could provide the 5QIs as input based | S2-1908209 | <No volunteer yet>
| Clarification on PC5 QoS rule | S2-1908215 | <No volunteer yet>
| PC5 QoS parameters clarifications | S2-1908216 | <No volunteer yet>
| Enhancements to QoS Handling for V2X Communication Over Uu Reference Point | S2-1908223, S2-1908607, S2-1908627 (LS) | <No volunteer yet>
| QoS Handling for V2X Communication Over Uu Reference Point | S2-1908225 | <No volunteer yet> | Registration procedure
| PC5 QoS rule handling and filter definitions | S2-1908227 | <No volunteer yet>
24.526
| UE Configuration Update procedure | S2-1906316
27.007
| Need to add a update or add AT commands to support eV2XARC |  | <No volunteer yet>

## Incoming LSs
Incoming liaision statements (LS)
Tdoc # | Topic | Reply LS | Related tdocs: CT1 meeting #; tdoc(s) # | Open issues | Comments