## Tdoc cover sheet
3GPP TSG CT WG1 Meeting #127e |  | C1-207429
Source: | Nokia, Nokia Shanghai Bell
Title: | Work plan for the CT1 part of eMONASTERY2
Agenda item: | 17.3.10
Document for: | Discussion

## Contributions plan
|  | Topic | Responsible company in stage-3 | is done? | Impacted Specs | CT1 meeting #; tdoc(s) # | Open issues | Related stage2 tdoc(s) # | Comments
1 | Extensions to other services | Solution 1 on restricting incoming private communications | Nokia CT1 #127bis | 1 | 24.484 configuration management 24.379 call control MCPTT 24.281 call control MCVideo 24.282 call control MCData 24.483 | MCPTT CT1#119; C1-194820,C1-194821,C1-1950610, C1-195062 MCData CT1#124-e:C1-204183-C1-204185 |  | S6-190698 (CR 0119r1, Cat B, Rel-16, 23.281)
2 |  | Solution 2 on implicit activation and deactivation of functional alias(es) | Samsung, Nokia CT1 #127e | 1 | 24.379 | CT1#121; C1-198801; CT1 #127e: C1-207705, C1-207652 | The MCVideo control part has been implemented in C1-205325 similar to the MCPTT FA control | S6-190815 (CR 0122r2, Cat B, Rel-16, 23.281)
3 |  | Solution 3 on client performs automatic group affiliation/de-affiliation | Samsung, Nokia CT1 #127e | 1 | 24.483, 24.379, 24.484 | CT1#122: C1-200409; C1-200410; C1-200886, CT1 #127e: C1-207705, C1-207652 | The MCVideo control part has been implemented in C1-205325 similar to the MCPTT FA control | S6-190859 (CR 0123r3, Cat B, Rel-16, 23.281)
4 |  | Extension of Solution 9 on allowed FA checks for first-to-answer call (config data for allowed FAs+server checks) | Nokia CT1 #128e | 1 | 24.483, 24.379, 24.484 |  |  | S6-191556 (CR0226r2, Cat B, Rel-17, 23.379)
5 |  | Solution 14 on MC service server limits the number of simultaneous successful service authorisations | Nokia CT1 #127e | 1 | 24.379, 24.484, 24.281, 24.282 | CT1#122: C1-201056, CT1#124 C1-203722, C1-204182; CT1#125 C1-204691 CT1 #127e: C1-207752, C1-207425, C1-207422 |  | S6-190934 (CR 0131, Cat B, Rel-16, 23.281)
6 |  | Extension of Solution 14 on per user MC service server limits the number of simultaneous successful service authorisations | Nokia CT1 #128e | 1
7 |  | Solution 31 on client activation and deactivation functional aliases based on location | Samsung, Nokia CT1 #127e | 1 | 24.281 24.484,24.483 | CT1#120; C1-196814,C1-196815, C1-196816 CT1 #127e: C1-207705, C1-207652 |  | S6-190939 (CR 0132, Cat B, Rel-16, 23.281)
8 |  | Solution 33 on communication priority for functional aliases | Samsung, Nokia CT1 #126e | 1 | 24.281, 24.282, 24.484 configuration management 24.379 call control MCPTT | CT1#121; C1-198659; CT1 #127e: C1-207652 (merged C1-206407) |  | S6-191444 (CR0134r1, Cat B, Rel-17, 23.281) S6-191445 (CR0166r1, Cat B, Rel-17, 23.282)
9 | FA support in MCVideo | Solution 18 on support of functional aliases for video emergency group calls, solution 20 on support of functional aliases for video group calls together with solution 23 on support functional alias controlling for MCVideo services | Samsung CT1#125e | 1 | 24.281, 24.581 | CT1#125e: C1-205325, C1-205324 |  | S6-190721 (CR 0124r1, Cat B, Rel-16, 23.281), S6-190878 (CR 0127r4, Cat B, Rel-16, 23.281)
10 |  | Solution 21 on support of functional aliases for private and emergency video calls together with solution 23 on support functional alias controlling for MCVideo services | Samsung CT1#125e | 1 | 24.281, 24.581 | CT1#125e: C1-205325, C1-205324 |  | S6-190865 (CR 0125r3, Cat B, Rel-16, 23.281), S6-190866 (CR 0126r3, Cat B, Rel-16, 23.281)
11 | Partially addressed in Rel-16 in stage 2 | Solution 10 on location information for a specific functional alias |  | 0 |  |  |  | S6-191182 (CR 0203r3, Cat B, Rel-16, 23.280)
12 |  | Solution 26 on user requests application layer priorities |  | 0 |  |  | MCPTT stage 2 part not concluded within Rel-16 | S6-190710 (CR 0196r1, Cat B, Rel-16, 23.379), S6-190711 (CR 0121r1, Cat B, Rel-16, 23.281), S6-190712 (CR 0141r1, Cat B, Rel-16, 23.282)
13 |  | Solution 29 on call forwarding/transfer for private calls +media security for private call forwarding |  | 0 |  |  | MCPTT stage 2 part not concluded within Rel-16 | S6-191185 (CR 0210r2, Cat B, Rel-16, 23.379) S6-191230 (CR 0211r3, Cat B, Rel-16, 23.379) S6-191990 (CR 0229r7, Cat B, Rel-17, 23.379) S6-200332 (CR 0246r5, Cat B, Rel-17, 23.379) S6-200573 (CR 0253r1, Cat F, Rel-16, 23.379) S6-200574 (CR 0254r1, Cat A, Rel-17, 23.379) S6-200821 (CR 0253r3, Cat F, Rel-16, 23.379) S6-200822 (CR 0254r3, Cat A, Rel-17, 23.379) S6-201208 (CR 0262r1, Cat B, Rel-17, 23.379) S6-201209 (CR 0263r1, Cat B, Rel-17, 23.379)
14 |  | IP connectivity extensions:P2P using FA to address the target MC service user, P2P remote establishment, withdrawal a connection by an authorized user, control of QoS based on per packet priority, MCData Group communication |  | 0 | 24.282 | CT1#122:C1-201022; CT1#123: C1-202883, C1-202884,C1-202885 |  | CRs that have already been addressed in Rel-16 S6-190864 (CR 0148r3, Cat B, Rel-16, 23.282), S6-190727 (CR 0149r1, Cat B, Rel-16, 23.282), S6-191231 (CR 0159r3, Cat B, Rel-16, 23.282) S6-191508 (CR0162r2, Cat B, Rel-17, 23.282) S6-191615 (CR0164r4, Cat B, Rel-17, 23.282) S6-191616 (CR0165r4, Cat B, Rel-17, 23.282) S6-191850 (CR 0189r3, Cat B, Rel-17, 23.282) S6-191849 (CR 0182r2, Cat B, Rel-17, 23.282)
15 |  | FA to Group binding | [5 empty] | S6-191606 (CR0207r3, Cat B, Rel-17, 23.280) S6-192085 (CR 0224, Cat C, Rel-17, 23.280) S6-192206 (CR 0238r1, Cat B, Rel-17, 23.379)
16 |  | Solution 11 on MC service server prevents de-affiliation when using a specific functional alias(es) (subclause 7.11) | [5 empty] | S6-191450 (CR 0209r1, Cat B, Rel-17, 23.280)
17 |  | Solution 12 on list of functional aliases used by affiliated group members (subclause 7.12) | [5 empty] | S6-191555 (CR 0208r2, Cat B, Rel-17, 23.280)
18 | FA as target | Use of functional alias as target address used for establishing MCData, especially SDS, FD | Nokia |  |  |  |  | S6-191557 (CR 0163r2, Cat B, Rel-17, 23.282) S6-191991 (CR 0181r3, Cat B, Rel-17, 23.282)
19 |  | MCVideo communications using functional alias to address target user | Nokia |  |  |  |  | S6-200936 (CR 0257r1, Cat B, Rel-17, 23.280 S6-200897 (CR 0142r6, Cat B, Rel-17, 23.281) S6-201191 (CR 0145r1, Cat F, Rel-17, 23.281)
20 |  | MCPTT communications using functional alias to address target user – security aspects. Impacts also on call forwarding und call transfer procedures. | Nokia |  |  |  |  | S6-200553 (CR 0251r3, Cat F, Rel-16, 23.379) S6-200554 (CR 0252r3, Cat A, Rel-17, 23.379) S6-200898 (CR 0256r3, Cat F, Rel-17, 23.379) S6-201190 (CR 0261r1, Cat F, Rel-17, 23.379) S6-201225 (CR 0269r1, Cat B, Rel-17, 23.379)
21 |  | MCData communications using functional alias to address target user – security aspects | Nokia |  |  |  |  | S6-201188 (CR 0230r1, Cat F, Rel-17, 23.282) S6-201187 (CR 0229r1, Cat F, Rel-17, 23.282) S6-201186 (CR 0228r1, Cat F, Rel-17, 23.282) S6-201189 (CR 0231r1, Cat F, Rel-17, 23.282)
22 |  | Use of functional alias as target address used for establishing an MCPTT emergency private call | Nokia |  |  |  |  | S6-191846 (CR 0225r3, Cat B, Rel-17, 23.379)
23 | Missing requirements | Call deflection from requirements TS 22.179 [R-5.6.3-015] and [R-6.7.4-016] | [5 empty] | S6-191446 (CR 0228r1, Cat F, Rel-16, 23.379)S6-200333 (CR 0247r5, Cat B, Rel-17, 23.379)
24 |  | Requirements [R-6.8.7.2-007], [R-6.8.7.2-008], [R-6.8.7.2-009], [R-6.8.7.2-010] | [5 empty] | S6-190710, S6-190711 and S6-190712 S6-192345 (CR 0221r4, Cat F, Rel-17, 23.280) S6-192225 (CR 0190r2, Cat F, Rel-17, 23.282) S6-192212 (CR 0191r1, Cat B, Rel-17, 23.282) S6-192346 (CR 0193r2, Cat B, Rel-17, 23.282) S6-192347 (CR 0240r2, Cat B, Rel-17, 23.379) S6-192348 (CR 0137r2, Cat B, Rel-17, 23.281)
25 | Posponed to Rel-18 (for now) | Solution 32 on functional alias and alternative addressing scheme for interworking with GSM-R |  | 0 |  |  | MCPTT stage 2 part not concluded within Rel-16, Rel-17 considered also incomplete | S6-191187 (CR 0035r2, Cat B, Rel-16, 23.283), (only management aspects covered) S6-191457 (CR0036r2, Cat B, Rel-17, 23.283) S6-191561 (CR0048r2, Cat B, Rel-17, 23.283) S6-192208 (CR 0049r3, Cat B, Rel-17, 23.283) S6-191458 (CR0037r2, Cat B, Rel-17, 23.283) S6-191460 (CR 0050r1, Cat B, Rel-17, 23.283)
26 |  | Interconnection-MCPTT (private, group) | [5 empty] | S6-192207 (CR 0239r1, Cat B, Rel-17, 23.379)
27 |  | Interconnection - MCVideo (private, group) | [5 empty] | S6-200182 (CR 0143r1, Cat F, Rel-17, 23.281) S6-200183 (CR 0144r1, Cat F, Rel-17, 23.281)
0.41667

## Incoming LSs
Incoming liaision statements (LS)
Tdoc # | Topic | Reply LS | Related tdocs: CT1 meeting #; tdoc(s) # | Open issues | Comments