## General
Latest update: 06/10/2020
Rel-17 - WI: Enhancement for the 5G Control Plane Steering of Roaming for UE in CONNECTED mode (eCPSOR_CON)
Latest WID: CP-202186
Completion Status: CT#89: 5% (CT1-5%) CT#90: CT#91:

## CT1 issues
Latest update: 06/11/2020
CT-1 Issues
Issue number | Description | Contributor to the next meeting? | DP /CR- Spec | Status | Notes
1 | Do we need to provide the SOR-CMCI info to the UE at initial registration, as no PDU session exists at that point when SOR is performed (SOR info received by the Reg. Accept message)? |  |  | closed | Contribution to CT1#126e see C1-204780.
2 | The SOR-CMCI is dynamically generated similar to SOR info. Or is there some information that can be statically configured in the UE? |  |  | closed | Contribution to CT1#126e see C1-206529
3 | What are the Static and dynamic info to be configured in the UE?
4 | Should SOR info and SOR-CMCI arrive at the UE at the same time? The procedure where SOR is checked should also check the SOR-CMCI. How to handle the UE behaviour when receiving the information (SOR info+SOR-CMCI) at the same time or with a delay (received in different messages). |  |  | ongoing | Contribution to CT1#126e See C1-206065, C1-205950 SOR-CMCI shall be received in the same container with other SOR related info. Procedure part is still open.
5 | Define the UE behaviour upon receiving the new SOR information while in connected mode. This includes consideration towards the newly requested sessions or re-established sessions. Editor's note: How the UE determines that the SOR-CMCI requires that the UE shall move to the idle mode is FFS. |  |  | ongoing
6 | Editor's note: it is FFS whether the SOR-CMCI is (a) configured in the UE using the UE parameters update via UDM control plane procedure, (b) included in a SOR transparent container, (c) transported in a new transparent container, or (d) other means. |  |  | ongoing | related with issue 19
7 | Editor's Note: The exact structure and detailed parameters of SOR-CMCI is FFS. | NTT DOCOMO Ericsson, Thales /Ban | CR/23.122 revision of C1-205954 | ongoing | Contribution to CT1#126e see C1-205954 related to issue 9
8 | Possible solutions for considering SOR-CMCI for Rel-15 onwards and what are the impacts. |  |  | ongoing | Contribution to CT1#126e see C1-206065
9 | Define the services that are exempted from eCPSOR-CON New clause in Annex-c. - use of DNN, S-NSSAI or 5QI to identify the services - 5GMM/5GSM procedures (exempted or not) | NTT DOCOMO Ericsson, Thales /Ban | CR/23.122 revision of C1-205954 | ongoing | Contribution to CT1#126e see C1-205954
10 | High priority service exempt from release due to SOR. |  |  |  | Wait for SA1 response.
11 | SOR-CMCI, do we need another definition for secured new SOR info?
12 | Editor's note: If the UE has an established emergency PDU session, it is FFS whether the UE shall attempt to perform the PLMN selection immediately after the emergency PDU session is released or after some time to enable PSAP callback.
13 | Editor's note: it is FFS whether the UE performs local NAS signalling connection release or de-registration procedure when the SOR-CMCI requires that the UE shall move to the idle mode. | NTT DOCOMO Ericsson, Thales /Ban | CR/23.122 proposed in the revision of C1-205954 | ongoing | Contribution to CT1#126e see C1-206329
14 | Identify when to provide the new SOR information to the UE, while the UE is in the HPLMN, or only when in the VPLMN?
15 | If UPU is used; solve the issue of reserved values for UPU to allow indicating a new code point for SOR-CMCI. |  |  | closed | Contribution to CT1#126e see C1-206065 the intention is that UPU will not be used for transporting SOR-CMCI.
16 | Whether to store the SOR-CMCI in the UE's ME or USIM, or both and the priority order needs to be clarified. | NTT DOCOMO /Ban | DP
17 | it is FFS whether the UDM can provide the SOR-CMCI to a UE not supporting SOR-CMCI.
18 | it is FFS how the SOR-AF knows that it should provide the SOR-CMCI for the UE.
19 | How would the home operator configure the SOR-CMCI in the UE? It is FFS whether subclause C.3 is to describe configuring the UE with SOR-CMCI or whether a new subclause will be specified to describe configuring the UE with SOR-CMCI.
20 | How to specify if the SOR-CMCI is part of the secured packet is FFS | Thales /Ly Thanh | CR/23.122 part of the revision of C1-205954
21 | The need for the UE to provide its capability for SOR-CMCI. This may be needed to ensure the AMF has provided the HPLMN with the UE capability or not. | NTT DOCOMO /Ban | DP and CR/23.122

## CT1 contributions
Latest update: 06/11/2020
CT-1 Contributions
meeting /Item No | Item | Contributor | Spec-CR/DP/LS | Tdoc Number | Notes
CT1#125e /1 | Kick-off – Stage-2 required work and project planning for the WI eCPSOR_CON | NTT DOCOMO /Ban | DP | C1-204618
CT1#125e /2 | Rel-17 SOR enhancement – Identifying the session type | NTT DOCOMO /Ban | DP | C1-204619 | Qualcomm/Lena: do not use OSid + APP id, use of DNN, S-NSSAI or 5QI is fine. Ericsson/Ivo: benefit in interrupting ongoing NAS (5GMM or 5GSM) procedures is not clear. Those procedures are very quick.
CT1#125e /3 | Discussion to providing the SOR connected mode information | Ericsson /Ivo | DP | C1-204780 | DOCOMO/Ban: not clear what are the configurations in the UE. The information should be dynamically provided to the UE. Apple/Robert: Backward compatibility issue with configuring the SOR connected mode information in the UE using the UE parameters update via UDM control plane procedure. As the UDM initiating UE parameters update procedure it currently is not aware of the release of the UE.TS 24.501, in figure 9.11.3.53A code points are defined as “reserved" in UPU. Orange/Marius: sees some information change dynamically and others are can be static and configured in the UE.
CT1#125e /4 | Enhancement for CP-SOR for UE in connected mode | Ericsson /Ivo | Spec: 23.122 CR 0566 | Provided in C1-204781 Agreed in C1-205289 | Editor's note: it is FFS whether the SOR-CMCI is (a) configured in the UE using the UE parameters update via UDM control plane procedure, (b) included in a SOR transparent container, (c) transported in a new transparent container, or (d) other means. Editor's note: Exact structure of the SOR-CMCI is FFS.ditor's note: If the UE has an established emergency PDU session, it is FFS whether the UE shall attempt to perform the PLMN selection immediately after the emergency PDU session is released or after some time to enable PSAP callback. Editor's note: it is FFS whether the UE performs local NAS signalling connection release or de-registration procedure when the SOR-CMCI requires that the UE shall move to the idle mode.Editor's note: How the UE determines that the SOR-CMCI requires that the UE shall move to the idle mode is FFS.
CT1#125e /5 | Introducing the definition "Steering of roaming connected mode control information" | NTT DOCOMO /Ban | Spec: 23.122 CR 0572 | Provided in C1-204805 Agreed in C1-205244 | Editor's Note: The detailed parameters of SOR-CMCI is FFS.
CT1#125e /6 | LS on providing the SOR connected mode information | Ericsson /Ivo | LS to SA2 | C1-204782 | Postponed
CT1#125e /7 | LS on high priority service exempt from release due to SOR | Nokia /Sung | LS to SA1 | C1-204941 | Agreed
CT1#125e /8 | LS on VPLMN release version for Rel-17 enhancement for CP-SOR in connected mode | NTT DOCOMO /Ban | LS to SA1 | Provided in C1-205055 Revised to C1-205224 | Postponed
CT1#126e /1 | Discussion – main requirements for achieving CP-SOR in connected mode | NTT DOCOMO /Ban | DP | C1-205950 | Ivo provided some comments. some of the requirements are implemented in C1-205952.
CT1#126e /2 | Enhanced CP-SOR in connected mode- UE behaviour during initial registration | NTT DOCOMO /Ban | DP | C1-205951 | Lena and Ivo disagree with the conclusions. Ban: The only one condition that is not covered in 24.501 subclause 4.2 and is required for SOR is the handling of the Uplink data status that indicates to the network the preserved PDU sessions which have uplink data pending. The NW then may re-establish the PDU sessions. then we solved the issue by agreeing to C1-206753/C1-206754 (Rel-16/17 respectively)
CT1#126e /3 | Introducing new requirements for CP-SOR in connected mode | NTT DOCOMO /Ban | Spec: 23.122 CR0591 | Provided in C1-205952 agreed in C1-206529 | Requirements for using SOR-CMCI
CT1#126e /3 | Updating the requirements for CP-SOR in 5GS | NTT DOCOMO /Ban | Spec: 23.122 CR0592 | Provided in C1-205953 agreed in C1-206542 | adding reference to 22.261
CT1#126e /5 | SOR-CMCI configuration and session handling for enhanced control plane SOR in connected mode | NTT DOCOMO /Ban | Spec: 23.122 CR0593 | C1-205954 | Postponed. Reason: Nokia does not see defining a criteria for the SOR-CMCI is required, and sending only one timer to the UE is sufficient. This timer is used to release any PDU session, independent of the communication type.
CT1#126e /6 | Delivery mechanism for Connected-Mode SoR Information | Samsung | DP | C1-206065 | Good proposal for including the SOR-CMCI as part of the SOR information. Also requires the UE to indicate its support for such IE.
CT1#126e /7 | Editor's note on de-registration or NAS signalling connection release | Ericsson /Ivo | Spec: 23.122 CR0612 | C1-206329 | Postponed. Reason: Ban indicated that releasing the PDU sessions, by UE deregistration, will help having clear charging records among operators.
CT1#126e /8 | Discussion on UE parameters update transparent container with an unsupported UE parameters update data set type | Ericsson /Ivo | DP | C1-206330 | eventually may not be needed for eCPSOR_CON. Proposed solution in C1-206065.
CT1#126e /9 | UE parameters update data set types supported by the UE | Ericsson /Ivo | Spec: 24.501 CR05xx | C1-206331 | eventually may not be needed for eCPSOR_CON. Proposed solution in C1-206065.
CT1#126e /10 | No need to release NAS signalling connection when the selected VPLMN is the highest priority PLMN | Ericsson /Ivo | Spec: 23.122 CR0613 | Provided in C1-206332 revised to C1-206737 | postponed. Different companies had different views on usage of the "list of available and allowable PLMNs in the area" in 23.122 annex C. NTT Docomo and Apple wanted to remove usage of the list where Qualcomm wanted to preserve using the list.
CT1#126e /11 | No need to release NAS signalling connection when the selected VPLMN is the highest priority PLMN | Ericsson /Ivo | Spec: 23.122 CR0614 | C1-206333 | withdrawn - double reserved number
CT1#126e /12 | Obtaining SOR-CMCI | Ericsson /Ivo | Spec: 23.122 CR0615 | Provided in C1-206336 Agreed in C1-206735 | describing how the UDM obtains the SOR-CMCI (from the UDR or the SOR-AF).
CT1#126e /13 | SOR-CMCI configuration data | Thales /Ly Thanh | DP | C1-206380 | Identifying new open issues related to configuration of SOR-CMCI in the ME/USIM
CT1#127e /14 | SOR-CMCI configuration and session handling for enhanced control plane SOR in connected mode | NTT DOCOMO /Ban | Spec: 23.122 CR0593 | C1-207036 | revision of C1-205954
CT1#127e /15 | LS – Providing the UE support for SOR-CMCI to the HPLMN UDM | NTT DOCOMO /Ban | LS out | C1-207040
CT1#127e /16 | Provisioning and handling of SOR-CMCI | NTT DOCOMO /Ban | DP | C1-207038
CT1#127e /17 | Support of SOR-CMCI in UE and CN | NTT DOCOMO /Ban | Spec: 23.122 CR0622 | C1-207039
CT1#127e /18 | No need to release NAS signalling connection when the selected VPLMN is the highest priority PLMN | Ericsson, Qualcomm Incorporated / Ivo | Spec: 23.122 CR0615 | C1-207071 | revision of C1-206735
CT1#127e /19 | UE indication of SOR-CMCI capability 24.501 | Orange / Mariusz | Spec: 24.501 CR2943 | C1-207469
CT1#127e /20 | UE-initiated de-registration after SOR-CMCI | Orange / Mariusz | Spec: 23.122 CR0642 | C1-207470

## CT4 issues
Latest update: 28/10/2020
CT-4 Issues
Issue number | Description | Contributor to the next meeting? | DP /CR - Spec | Status | Notes

## CT4 contributions
Latest update: 29/10/2020
CT-4 Contributions
meeting /Item No | Item | Contributor | Spec-CR/DP/LS | Tdoc Number | Notes
CT4#101 /1 | Evolution of SoR delivery mechanism | Samsung | DP | C4-205111
CT4#101 /2 | Evolution of SoR delivery mechanism – UDM API Changes | Samsung | Spec: 29.503 CR0500 | C4-205112
CT4#101 /3 | Evolution of SoR delivery mechanism – AUSF API Changes | Samsung | Spec: 29.509 CR0108 | C4-205113
CT4#101 /4 | Evolution of SoR delivery mechanism – SoR-AF API Changes | Samsung | Spec: 29.550 CR0014 | C4-205114