## Tdoc cover sheet
3GPP TSG-CT WG1 Meeting #130-e E-meeting, 20-28 May 2021 |  | C1-213467
Source: | Samsung Electronics
Title: | Work plan for CT1 aspects of EDGEAPP
Agenda item: | 17.2.16
Document for: | Information

## Contributions plan
Contribution Plan
Spec | Topic | % | Related LS or other WG tdoc(s) # | Volunteered company | CT1 meeting #; tdoc(s) # | Comments | Open issues
24.558 | Enabling Edge Applications (Rel-17)
-- | TS - Skeleton | 3 |  |  | CT1#128-e
clause 1 | Scope | 2 |  | Samsung | CT1#129-e; C1-202454
clause 2 | References | 2 |  | Samsung | CT1#129-e; C1-202454
clause 3 | Definition of Terms and Abbreviation | 2
clause 4 | Overview | 1 |  | Samsung | CT1#130-e
clause 5 | Services offered by the Edge Enabler Server
| EEC registration (Service Description, Service Operation) | 6 |  | Samsung | CT1#130-e
| EAS discovery (Service Description, Service Operation) | 8
| Application context relocation (Service Description, Service Operation) | 4
| Application context relocation Events (Service Description, Service Operation) | 8
clause 6 | Edge Enabler Server API Definitions
| Information applicable to several EES APIs | 2
| Eees_EECRegistration API Definition | 6 |  | Huawei / Samsung | CT1#129-e; C1-202546
| Eees_EASDiscovery API Definition | 8 |  | InterDigital | CT1#129-e; C1-202547 (Subscribe-Notify model resource structure and methods) | Following points are yet to be specified: - Subscribe notify model - Data structure needs to be specified. - Request response model - Operations, Data structures needs to be specified. Need to define following based on skeleton (as applicable): - API URI - Resources - Custom Operations without associated resources - Notifications - Data Model - Error Handling - Feature negotiation
| Eees_AppContextRelocation API Definition | 4 |  | InterDigital |  | Following needs to be defined based on skeleton (as applicable): - API URI - Resources - Custom Operations without associated resources - Notifications - Data Model - Error Handling - Feature negotiation
| Eees_ACREvents | 8 |  |  |  | Following needs to be defined based on skeleton (as applicable): - API URI - Resources - Custom Operations without associated resources - Notifications - Data Model - Error Handling - Feature negotiation
clause 7 | Security | 4
Annex A | Edge Enabler Server OpenAPI specification
Data Types applicable to several APIs
| EEC Registration API | 4
| EAS Discovery API | 4
| Application context relocation API | 4
| Application context relocation Events API | 4
Annex B | Protocol options considered for EDGE-4 reference point | 16
API Option
| Service Provisioning (Service Description, Service Operation) |  |  | Samsung
| Eecs_ServiceProvisioning API Definition |  |  | Samsung | CT1#129-e; C1-202155 (request-response model resource URI and methods) | Following points are yet to be specified: - Subscribe notify model - Data structure needs to be specified. - Request response model - Operations, Data structures needs to be specified. Need to define following based on skeleton (as applicable): - API URI - Resources - Custom Operations without associated resources - Notifications - Data Model - Error Handling - Feature negotiation
Service Provisioning (OpenAPI Specification)
Solution evaluation
Conclusion
NAS Option
Elementary procedures between ECS and EEC
Handling of unknown, unforeseen, and erroneous service data
Message functional definition and contents
Information elements coding
Timers
Solution evaluation
Conclusion
Annex Updates (if needed)
TS cleanup - Editorials
| TS (for Info) |  |  |  | CT#92e
| TS (For approval) |  |  |  | CT#93e
100

## Incoming LSs
Incoming liaision statements (LS)
Tdoc # | Topic | Reply LS | Related tdocs: CT1 meeting #; tdoc(s) # | Open issues | Comments
C1-207064 | LS on APIs in EDGEAPP (S6-202009) |  | CT1#127-e;C1-207123 |  | Merged into a revision of C1-207340
|  |  | CT1#127-e;C1-207285 |  | Merged into a revision of C1-207340
|  |  | CT1#127-e;C1-207721 | There is no concensus in CT1 about usage of NAS for EDGE-4 reference point. Discussion on types of APIs. | Postponed Revsion of C1-207340
|  |  | CT1#127-e;C1-207122 |  | Proposal 1: 3GPP CT1 can make use of the NAS as an appropriate mean of supporting the EDGE-4 reference point. Proposal 2: 3GPP CT1 could make use of API(s) or the NAS for supporting the EDGE-1 reference point. Proposal 3: CT1 should wait for stable stage 2 work and analysis from all impacted working groups before considering unifying any potential API.
C1-210050 | LS on APIs in EDGEAPP (S6-202009) | C1-210441
C1-210028 | Reply to LS on APIs in EDGEAPP (C3-205439)
C1-212808 | LS on Clarification on the API design principles (C3-212554)

## Outgoing LSs
Outgoing liaision statements (LS)
Tdoc # | Topic | Related tdocs: CT1 meeting #; tdoc(s) # | Open issues | Comments
C1-210441 | Reply LS on APIs in EDGEAPP | C1-210050; C1-210028 | Protocol selection for EDGE-4 reference point is under discussion