## Tdoc cover sheet
3GPP TSG CT WG1 Meeting #133bis-e Electronic meeting; 17-21 January 2022 |  | C1-220428
Source: | CATT, OPPO
Title: | Work plan for the CT1 part of 5G_ProSe-CT
Agenda item: | 17.2.18
Document for: | Discussion

## Contributions plan
Contribution Plan
Contribution Plan
Spec | Topic | Related LS or other WG tdoc(s) # | CT1 meeting #; tdoc(s) # | Comments | Open issues
24.554
| TS skeleton |  | #128e; C1-211183
| TS scope |  | #128e; C1-211184
| Types of discovery procedures |  | #129e; C1-212046
| Match report procedure for restricted ProSe direct discovery model A |  | #129e; C1-212274
| Match report procedure for restricted ProSe direct discovery model B |  | #129e; C1-212275
| Match Report procedure for open ProSe direct discovery |  | #129e; C1-212276
| Discovery overview |  | #129e; C1-212383
| Overview of TS 24.554 |  | #129e; C1-212384
| Add EN for U2U |  | #129e; C1-212385
| Announce request procedure for open ProSe direct discovery |  | #129e; C1-212468 |  | Overlapping description on PROSE PC5 DISCOVERY in clause 6.2.2, 6.2.3, 6.2.6 and 6.2.7 with clause 6.2.14
| Monitor request procedure for open ProSe direct discovery |  | #129e; C1-212469
| Announce request procedure for restricted ProSe direct discovery model A |  | #129e; C1-212470 |  | Overlapping description on PROSE PC5 DISCOVERY in clause 6.2.2, 6.2.3, 6.2.6 and 6.2.7 with clause 6.2.14
| Monitor request procedure for restricted ProSe direct discovery model A |  | #129e; C1-212472
| Announcing Alert procedure |  | #129e; C1-212474
| Direct discovery update procedure for open discovery |  | #129e; C1-212475
| Precedence of ProSe configuration parameters |  | #129e; C1-212477
| Configuration parameters for 5G ProSe Direct Discovery |  | #129e; C1-212488
| Direct Discovery update procedure for restricted discovery |  | #129e; C1-212495
| Discoverer request procedure for restricted ProSe Direct Discovery Model B |  | #129e; C1-212498 |  | Overlapping description on PROSE PC5 DISCOVERY in clause 6.2.2, 6.2.3, 6.2.6 and 6.2.7 with clause 6.2.14
| TS 24.554: Overview of 5G ProSe direct communications. |  | #129e; C1-212505
| Discoveree request procedure for restricted ProSe Direct Discovery Model B |  | #129e; C1-212507 |  | Overlapping description on PROSE PC5 DISCOVERY in clause 6.2.2, 6.2.3, 6.2.6 and 6.2.7 with clause 6.2.14
| UE-requested 5G ProSe policy provisioning procedure |  | #129e; C1-212531
| 5G ProSe Direct Link Establishment Procedure |  | #129e; C1-212572
| 5G ProSe PC5 QoS flow establishment |  | #129e; C1-212574
| 5G ProSe Data transmission mechanism over PC5 unicast link |  | #129e; C1-212579
| TS 24.554: Configuration parameters for 5G ProSe direct communication over PC5 interface |  | #129e; C1-212586
| TS 24.554: 5G ProSe direct link modification procedure. |  | #129e; C1-212587
| TS 24.554: 5G ProSe direct link identifier update procedure |  | #129e; C1-212588
| TS 24.554: 5G ProSe direct link keep-alive procedure. |  | #129e; C1-212589
| TS 24.554: 5G ProSe direct discovery procedure over PC5 interface |  | #129e; C1-212590 |  | Overlapping description on PROSE PC5 DISCOVERY in clause 6.2.2, 6.2.3, 6.2.6 and 6.2.7 with clause 6.2.14
| TS 24.554: Group member discovery over PC5 interface |  | #129e; C1-212591
| 5G ProSe Direct Link Release Procedure |  | #129e; C1-212592
| 5G ProSe IE definitions for Direct Establishment and Direct Release procedures |  | #129e; C1-212594
| Removal of UE-to-UE relay related editor's notes |  | #130e; C1-213020
| TS 24.554: Configuration parameters for U2N relay |  | #130e; C1-213031
| Clean-up and Clarification on announcing UE operation |  | #130e; C1-213043
| Clean-up and Clarification on monitoring UE operation |  | #130e; C1-213044
| Clean-up and Clarification on discoveree UE operation |  | #130e; C1-213045
| Clean-up and Clarification on discoverer UE operation |  | #130e; C1-213046
| Adding IEs definitions of some missing IEs for 5G ProSe procedures |  | #130e; C1-213202
| Correcting the reference point PC3 to be PC3a |  | #130e; C1-213203
| Unifying the terminology of the 5G ProSe direct communication |  | #130e; C1-213205
| Update configuration parameters |  | #130e; C1-213568
| Add path selection for direct communication |  | #130e; C1-213569
| Handling of unknown, unforeseen, and erroneous protocol data |  | #130e; C1-213570
| Timer table |  | #130e; C1-213571
| PROSE PC5 DISCOVERY message and Ies |  | #130e; C1-213572
| Introducing the Relay Discovery Additional Information procedure |  | #130e; C1-213667
| Introducing the UE-to-network relay selection procedure |  | #130e; C1-213668
| Introducing the UE-to-network relay reselection procedure |  | #130e; C1-213670
| Unifying the terminology for PROSE PC5 |  | #130e; C1-213671
| Configuration parameters for U2N relay |  | #130e; C1-213674
| UE ProSe policy transmission |  | #130e; C1-213754
| UE-to-Network Relay Discovery procedure |  | #130e; C1-213755
| Provisioning of 5G ProSe configuration information signalling messages |  | #130e; C1-213756
| TS24.554: Broadcast mode communicaiton over PC5 interface |  | #130e; C1-213767
| TS24.554: UE-to-Network Relay Discovery over PC5 interface (Model B) |  | #130e; C1-213768
| TS24.554: Update UE-requested 5G ProSe policy provisioning procedure for adding new request type |  | #130e; C1-213770
| Update to Precedence of ProSe configuration parameters |  | #130e; C1-213802
| Defining the 5G ProSe signalling messages |  | #130e; C1-213843
| Correcting wrong references in the signalling messages definitons |  | #131e; C1-214312
| Correcting the names of MSB of KNRP ID and LSB of KNRP ID |  | #131e; C1-214313
| Correcting some PC3a messages names |  | #131e; C1-214334
| Provisioned radio resources |  | #131e; C1-214469
| Add the missing description on ProSe under avoiding double barring |  | #131e; C1-214482
| correction on precedence of configuration |  | #131e; C1-215036
| L3 relay: clarification on a RSC per U2N relay discovery message |  | #131e; C1-214595
| L3 relay: Correction on U2N relay discovery procedure |  | #131e; C1-214597
| PDU session type mandatory for RSC |  | #131e; C1-214794
| Update relay configuration parameters |  | #131e; C1-214813
| Layer-3 UE-to-Network relay with N3IWF support |  | #131e; C1-214951
| correction on precedence of configuration |  | #131e; C1-215036
| L3 relay: update on configuration parameters for 5G ProSe UE-to-network Relay |  | #131e; C1-215038
| Update direct discovery configuration parameters |  | #131e; C1-215039
| Groupcast mode 5G ProSe direct communication over PC5 |  | #131e; C1-215058
| Clean-up for group member direct discovery procedure |  | #131e; C1-215060
| ProSe PC5 discovery message function defination and contents for UE-to-Network Relay |  | #131e; C1-215066
| Adding ProSe PC5 signaling message type for ProSe dirct discovery message over PC5 interface |  | #131e; C1-215067
| QoS handling for Relay operations |  | #131e; C1-215069
| Clean-up for UE-to-Network Relay discovery procedure |  | #131e; C1-215072
| IP address allocation for L3 UE-to-Network Relay |  | #131e; C1-215037
| Listing the Relay Discovery Additional Information procedures |  | #131e; C1-215107
| Adding the Overview clause for the 5G ProSe UE-to-network relay |  | #131e; C1-215110
| Adding the trigger for the Remote UE report procedure |  | #131e; C1-215113
| Adding the contents of the PROSE_PC5_DISCOVERY message for the Relay Discovery Additional Information procedure |  | #131e; C1-215119
| Removing ProSe Application ID and User Info ID from PROSE PC5 DISCOVERY messages |  | #131e; C1-215127
| Adding the Relay Service Code to the ProSe direct link establishment request |  | #131e; C1-215140
| Checking whether the associated S-NSSAI with Relay Service Code is in the Allowed NSSAI for Layer-3 UE-to-Network Relay discovery |  | #131e; C1-215141
| Add ProSe Ethernet packet filter set for ProSe direct communication |  | #132e; C1-215615
| Add layer indications of Layer-2/Layer-3 for 5G ProSe direct discovery |  | #132e; C1-215616
| Correct the timer in figure |  | #132e; C1-215620
| Resolving the Editor's note related to the inclusion of the NCGI in the relay discovery additional information |  | #132e; C1-215829
| Referring to the relay UE as "5G ProSe UE-to-network relay UE" |  | #132e; C1-215844
| Coding of PC3a messages |  | #132e; C1-216034
| Correction on relay reselection |  | #132e; C1-216035
| Correction on QoS handling on L3 relay UE |  | #132e; C1-216036
| Add relay related hanlding to direct link management procedure |  | #132e; C1-216037
| Remove editor's notes |  | #132e; C1-216038
| Align cause value |  | #132e; C1-216041
| IPv6 prefix delegation via DHCPv6 for 5G ProSe layer-3 UE-to-network relay |  | #132e; C1-216095
| Replace "ProSe application identifier" with "ProSe identifier" |  | #132e; C1-216106
| clarification on not support of MBS |  | #132e; C1-216147
| Correct the indication of using N3IWF access |  | #132e; C1-216155
| Correction of target info for group member discovery |  | #132e; C1-216156
| Determinate destination L2 ID of group member discovery |  | #132e; C1-216158
| Resolve EN for combinations of pack filter sets |  | #132e; C1-216159
| Resolve EN for public safety of group member discovery |  | #132e; C1-216160
| Add ProSe direct discovery PC5 message type in PROSE PC5 DISCOVERY message |  | #132e; C1-216175
| Impact of NAS level congestion control for 5G ProSe UE-to-Network Relay |  | #132e; C1-216162
| New conditions for releasing the 5G ProSe PC5 direct link |  | #132e; C1-216183
| Updates for Relay Discovery Additional Information procedure |  | #132e; C1-216184
| 5G Prose layer-2 UE-to-network relay UE to trigger Service Request procedure due to layer-2 relaying |  | #132e; C1-216186
| Cell ID announcement request procedure |  | #132e; C1-216188
| The indication of direct discovery message for the transmission of PC5 DISCOVERY message |  | #132e; C1-216189
| Terms and abbreviations in TS 24.554 |  | #132e; C1-216190
| Redefine monitoring UE |  | #132e; C1-216191
| Update destination layer 2 ID for remote |  | #133e; C1-216701
| Remove EN on ARP |  | #133e; C1-216704
| resolving EN for N3IWF selection |  | #133e; C1-216776
| Correction on ProSe application ID |  | #133e; C1-216896
| Corrections to some IEs in the PROSE DIRECT LINK ESTABLISHMENT REQUEST message and PROSE DIRECT LINK ESTABLISHMENT ACCEPT message |  | #133e; C1-216990
| Selecting PC5 Discovery Model if both Model A and Model B are supported by the UE |  | #133e; C1-216991
| Correcting the referral to the relay UE to be "5G ProSe UE-to-network relay UE" |  | #133e; C1-216992
| Reusing an existing PDU session to perform the 5G ProSe layer-3 UE-to-network relay with N3IWF |  | #133e; C1-217005
| Removing the ENs for ProSe timer value |  | #133e; C1-217119
| Correction on group member discovery |  | #133e; C1-217145
| Correction on PC3a coding |  | #133e; C1-217148
| Correction on IE name in XML |  | #133e; C1-217149
| Update to Layer-2 Relay selection |  | #133e; C1-217164
| Introduction of TS 33.503 and other cleanups |  | #133e; C1-217193
| Correction on link local IPv6 address |  | #133e; C1-217194
| Non-IP PDU handling for ProSe Direct Communication |  | #133e; C1-217270
| Clarification on target group info when discovering an application layer group |  | #133e; C1-217362
| Use ProSe ID to represent a ProSe service |  | #133e; C1-217363
| Clarification on relay operation in mobility restriction |  | #133e; C1-217364
| The inclusion of NCGI in the PROSE PC5 DISCOVERY message for layer-2 UE-to-network relay discovery announcement and layer-2 UE-to-network relay discovery response |  | #133e; C1-217391
| Clarifications for the Relay Discovery Additional Information procedure |  | #133e; C1-217394
| Releasing PDU session on revoking Service Authorization for 5G ProSe layer-3 UE-to-network relay UE |  | #133e; C1-217398
| Removing Relay TAI from the PROSE PC5 DISCOVERY message for layer-3 UE-to-network relay discovery response |  | #133e; C1-217403
| IP address/prefix is not included in the changed identifiers for the 5G ProSe direct link identifier update procedure in case of layer-2 relaying |  | #133e; C1-217408
24.555
| TS skeleton |  | #128e; C1-211187
| TS scope |  | #128e; C1-210884
| Add EN for U2U |  | #129e; C1-212386
| Descriptions of UE policies for 5G ProSe |  | #129e; C1-212396
| UE policy part encoding |  | #129e; C1-212530
| Removal of UE-to-UE relay related editor's notes |  | #130e; C1-213021
| Encoding policy of direct communication |  | #130e; C1-213746
| Encoding policy of direct discovery |  | #130e; C1-213574
| Update direct discovery configuration parameters |  | #131e; C1-214797
| ProSe policy coding for U2N relay |  | #131e; C1-214796
| Replace "ProSe application identifier" with "ProSe identifier" |  | #132e; C1-215653
| Encoding of N3IWF selection information for 5G ProSe layer-3 remote UE |  | #132e; C1-216108
| Update ProSeP coding for relay and remote |  | #133e; C1-217146
| Update ProSe identifier coding |  | #133e; C1-217147
23.122
| PLMN selection triggered by ProSe communicatins over NR-PC5 |  | #131e; C1-215068
24.501
| UE ProSe capability negotiation with 5GC |  | #129e; C1-212473/#130e; C1-213739
| UE ProSe policy transmission |  | #129e; C1-212476
| ProSe as a trigger for Service Request procedure |  | #129e; C1-212542
| Network shall not release the RRC connection for ProSe services |  | #129e; C1-212558
| NAS to be aware when the UE triggered ProSe provisioning procedure starts and stops |  | #129e; C1-212571
| Resuming a connection due to ProSe discovery/communication over PC5 |  | #131e; C1-214799
| Introducing the Remote UE report procedure |  | #131e; C1-215117
| Requesting ProSe resources as a trigger for Service Request procedure |  | #131e; C1-215143
| Editorial corrections for the ProSe relay terminologies and capabilities |  | #132e; C1-215830
| NAS signalling recovery from fallback when the UE was only performing ProSe PC5 procedures |  | #132e; C1-216046
| Add the SMF shall provide the QoS flow description(s) for the PDU sessions used for relaying |  | #132e; C1-216150
| Triggering Service Request procedure due to lower layers request for ProSe layer-2 UE-to-network relay |  | #132e; C1-216185
| Correcting the reference of the spec in which the UE requests the PCF to provide ProSeP |  | #133e; C1-216993
| The type of the port number in Remote UE context list information element |  | #133e; C1-217195
| IPv6 prefix delegation via DHCPv6 for 5G ProSe layer-3 UE-to-network relay |  | #133e; C1-217196
| Merging UE triggered V2X and ProSe policy provision procedure in UAC |  | #133e; C1-217345
27.007
24.526
| UE policies for 5G ProSe policy |  | #129e; C1-212449/#130; C1-212981
| Adding the 5G ProSe UE-to-Network Relay support to the URSP |  | #131e; C1-215099
| Mapping of 5G ProSe Layer-3 UE-to-Network Relay offload when moving from N1 mode to S1 mode |  | #131e; C1-215097
| 5G ProSe Layer-3 UE-to-Network Relay Offload indication for the UEs capable to act as Remote Ues |  | #132e; C1-216181
24.587
| Requested UE policies for 5G Prose |  | #129e; C1-212577
| Update on UE 5G ProSe Policy Request based on UE 5G ProSe Capability |  | #131e; C1-215064

## Expected contributions
Expected Contributions for future meetings
Spec | Topic | Related LS or other WG tdoc(s) # or TS # | Volunteered company/delegate | Contribution(s) | Open issues
24.554
SA2 TS 23.304
| Cell ID announcement procedure -> Additional parameters announcement procedure; Both cell ID and TAI are requested. Apply to both L3 and L2 relay; New trigger for additional message: TAI change | S2-2109160 (TS 23.304 clause 6.5.1.3, etc.) | CATT
| Update L2 ID - discovery message in clause 5.2.5 | TS 23.304 clause 5.1.4.1 | OPPO
| Include QoS rules in link modification procedure from both remote and relay | TS 23.304 clause 5.6.2.1, 6.4.3.4 | vivo
| Include QoS rules in link establishment accept | TS 23.304 clause 6.4.3.1 | vivo
| New trigger from AS layer to release link | TS 23.304 clause 6.4.3.6 | ASUSTeK
| Remove target group info | TS 23.304 clause 6.3.2.2.3 | OPPO
SA3 TS 33.503
| Open direct disocvery update for security | TS 33.503 clause 6.1.3.1 | OPPO
| Restricted direct discovery update for security (Model A) | TS 33.503 clause 6.1.3.2.2.1
| Restricted direct discovery update for security (Model B) | TS 33.503 clause 6.1.3.2.2.2
| Configuration parameters update for security: 1. PKMF address (relay); 2. PC5 security policies (relay and non-relay). | TS 33.503 clause 6.2.2 + 6.3.3.1 | OPPO
| PC5 authentication procedure for non-L3-relay | TS 33.503 clause 6.2.3
| PC5 security mode command procedure (non-relay and relay) | TS 33.503 clause 6.2.3 + 6.3.3.2.2 + 6.3.3.3.2 + 6.3.4 | InterDigital
| Key request procedure to PKMF by L3 relay and remote | TS 33.503 clause 6.3.3.2.2
Editor's note (with no dependance on SA3)
| Editor’s note: Details of whether specific parameters need to be set for the non-IP packet handling are FFS. | Clause 7.3.2.1.1 and 7.3.2.2
| Editor's note: Whether to transmit the application layer discovery messages as metadata in a PC5 direct discovery message or as user traffic depends on the size of the PC5 direct discovery message. The size of the PC5 direct discovery message or no size limit will be determined by RAN WG. | S2-2109170 (Clause 7.4.2.1.1, etc.) | CATT
| Editor's Note: The QoS handling for 5G ProSe layer-3 UE-to-network relay with N3IWF is FFS. | Clause 8.2.6.4 | vivo
| Editor's note: The condition of the optional IEs is FFS. | Clause 10.2.1
24.555
| Update L2 ID - discovery message | TS 23.304 clause 5.1.4.1 | OPPO
| Editor's note: It is FFS whether the coding of UE policies of 5G ProSe UE-to-network relay should be changed to adapt to the different UE ProSe capability. | Clause 5.2 | OPPO
23.122
| PLMN selection for the remote UE under L2 relay | S2-2107985 (TS 23.304 clause 5.4.2, etc.) | OPPO
24.501
| Editor's note: It is FFS what are the 5G ProSe remote UE identities that can be included in the Remote UE context list. Depending on the conclusion of this topic, the User identity field needs to be defined and also the Length of user identity is subject to change. | TS 23.304 clause 6.5.1.1
| Relay key request procedure to AMF | TS 33.503 clause 6.3.3.3.2
27.007

## Incoming LSs
Incoming liaision statements (LS)
Tdoc # | Topic | Reply LS | Related tdocs: CT1 meeting #; tdoc(s) # | Open issues | Comments
R2-2104654 | LS on R17 Layer-2 SL Relay of UE ID exposure in paging mechanism | N/A
R2-2106520 | LS on establishment/resume cause value and UAC on L2 SL Relay | C1-214795 | C1#131e
C1-215520 | LS on Tx Profile | N/A
C1-215522 | Reply LS on RAN dependency issues for 5G ProSe | N/A
C1-215540 | LS on UE POLICY PROVISIONING REQUEST message | C1-216298 | C1#132e
C1-217167 | LS on the indication of discovery message and PC5-S signalling to ProSe layer |  | C1#133e