## Tdoc cover sheet
3GPP TSG-CT WG1 Meeting #137-e E-Meeting, 18th – 26th August 2022 |  | C1-224929
Source: | Huawei, HiSilicon
Title: | Work plan for UASAPP
Agenda item: | 17.2.21
Document for: | Information
Note: The new added/updated contribution plan in the "Contributions plan" sheet is highlighted as yellow

## Contributions plan
Contribution Plan
Specs | Topic | Related LS or other WG tdoc(s) # or TS # | Volunteered company (delegate) | Meetings/Contribution(s) | Status | Comments
24.257
| Skeleton of TS 24.257 |  | Huawei, HiSilicon (Lin) | CT1#130-e/C1-213381 | agreed
| Scope of TS 24.257 |  | Huawei, HiSilicon (Lin) | CT1#130-e/C1-213382 | agreed
|  |  | Huawei, HiSilicon (Lin) | CT1#134-e/C1-221635 | agreed
| General description on the UAE layer protocol |  | Huawei, HiSilicon (Lin) | CT1#131-e/C1-214713 | agreed
|  |  | Huawei, HiSilicon (Lin) | CT1#133-e/C1-216575 | agreed
|  |  | Huawei, HiSilicon (Lin) | CT1#137-e/C1-224930 | TBD
SEAL services can be utilized to support UAE layer protocol
| The UAE server triggers location update as specified in clause 9.3.4 of 3GPP TS 23.434. | 23.255 sub 7.5.2.1 23.434 sub 9.3.4 | Huawei, HiSilicon (Lin) | CT1#131-e/C1-214714 | agreed | The UAE server (act as VAL server) can request the LM-S to initiate the existing on-demand location reporting procedure as specified in 23.434 sub 9.3.4 without any new updates. Based on the current SA6 status up to 2022.02, this is the only SEAL service (i.e. LM service) needs to be utilized by UAE layer under CT1 remit.
Communications between UAVs within a geographical area using unicast Uu
| Client procedure: - The UAE client sends the UAV application message to the UAE server. | 23.255 sub 7.2.2.1, 7.2.3.1 | Huawei, HiSilicon (Lin) | CT1#131-e/C1-215166 | agreed
| Server procedure: - The UAE server sends the received UAV application message to each of the UAV via unicast channel in the location of the UAV. | 23.255 sub 7.2.2.1, 7.2.3.1, S6-212027 | Huawei, HiSilicon (Lin) | CT1#132-e/C1-215765 | agreed
|  | 23.255 sub 7.2.1, S6-211817 | Huawei, HiSilicon (Lin) | CT1#132-e/C1-215764 | agreed
| Server procedure: - the UAE server may send an acknowledgement to the UAE client. | 23.255 sub 7.2.2.1 | Huawei, HiSilicon (Lin) | CT1#131-e/C1-215167 | agreed
UAV and UAV-C Pairing and C2 QoS Provisioning using Group ID
| Client procedure: | 23.255 sub 7.3.2, 7.3.3 | Huawei, HiSilicon (Lin) | CT1#133-e/C1-216576 | agreed | Based on the current SA6 status up to 2022.02, as per procedures and message flows in TS 23.255 sub 7.3.2, 7.3.3, currently cannot find any impact over U1-AE and U2-AE interfaces, i. e. no CT1 impact. Hence, this procedure was removed from TS 24.257 in 2021.11 CT1#133-e meeting.
| Server procedure: | 23.255 sub 7.3.2, 7.3.3 | Huawei, HiSilicon (Lin) | CT1#133-e/C1-216576 | agreed | Based on the current SA6 status up to 2022.02, as per procedures and message flows in TS 23.255 sub 7.3.2, 7.3.3, currently cannot find any impact over U1-AE and U2-AE interfaces, i. e. no CT1 impact. Hence, this procedure was removed from TS 24.257 in 2021.11 CT1#133-e meeting.
C2 Communication mode selection and switching
| Client procedure: - The UAE client sends the C2 communication modes configuration response to the UAE server. | 23.255 sub 7.4.2.2, 7.4.3.9 | Huawei, HiSilicon (Chen) | CT1#131-e/C1-214984 | agreed
| Client procedure: - The UAE client sends the C2 communication mode notification to the UAE server. | 23.255 sub 7.4.2.3, 7.4.3.10 | Huawei, HiSilicon (Chen) | CT1#131-e/C1-214986 | agreed
| Client procedure: - The UAE client sends the C2-related trigger event report to the UAE server. | 23.255 sub 7.4.2.4, 7.4.3.4 | Huawei, HiSilicon (Chen) | CT1#131-e/C1-214988 | agreed
| Client procedure: - The UAE client sends the C2 operation mode switching performed to the UAE server. | 23.255 sub 7.4.2.4, 7.4.3.12 | Huawei, HiSilicon (Chen) | CT1#133-e/C1-216733 | agreed
| Server procedure: - The UAE server sends the C2 communication modes configuration request to the UAE client. | 23.255 sub 7.4.2.2, 7.4.3.8 | Huawei, HiSilicon (Chen) | CT1#131-e/C1-214985 | agreed
|  | S6-220389 | Huawei, HiSilicon (Chen) | CT1#135-e/C1-222922 | agreed
| Server procedure: - The UAE server sends the C2 communication mode notification acknowledgement to the UAE client. | 23.255 sub 7.4.2.3, 7.4.3.11 | Huawei, HiSilicon (Chen) | CT1#131-e/C1-214987 | agreed
| Server procedure: - The UAE server sends the C2 operation mode switching to the UAE client(s) of the affected UAS. | 23.255 sub 7.4.2.4, 7.4.3.7 | Huawei, HiSilicon (Chen) | CT1#131-e/C1-214989 | agreed
Real-Time UAV Connection Status Monitoring and Location reporting
| Client procedure: | 23.255 sub 7.5.2, 7.5.3 | Huawei, HiSilicon (Lin) | CT1#133-e/C1-216576 | agreed | Based on the current SA6 status up to 2022.02, as per procedures and message flows in TS 23.255 sub 7.5.2, 7.5.3, currently cannot find any impact over U1-AE and U2-AE interfaces, i. e. no CT1 impact. Hence, this procedure was removed from TS 24.257 in 2021.11 CT1#133-e meeting.
| Server procedure: | 23.255 sub 7.5.2, 7.5.3 | Huawei, HiSilicon (Lin) | CT1#133-e/C1-216576 | agreed | Based on the current SA6 status up to 2022.02, as per procedures and message flows in TS 23.255 sub 7.5.2, 7.5.3, currently cannot find any impact over U1-AE and U2-AE interfaces, i. e. no CT1 impact. Hence, this procedure was removed from TS 24.257 in 2021.11 CT1#133-e meeting.
UAE layer registration
| Client procedure: - The UAE client sends a registration request to the UAE server. | 23.255 sub 7.6.2.1.2, 7.6.3.1, S6-212140 | Huawei, HiSilicon (Lin) | CT1#132-e/C1-215767 | agreed
| Client procedure: - The UAE client sends a deregistration request to the UAE server. | 23.255 sub 7.6.2.2.2, 7.6.3.3, S6-212140 | Huawei, HiSilicon (Lin) | CT1#132-e/C1-215771 | agreed
| Client procedure: - The UAE client sends a registration update request to the UAE server. | 23.255 sub 7.6.2.3.2, 7.6.3.5, S6-212140 | Huawei, HiSilicon (Lin) | CT1#132-e/C1-215769 | agreed
|  |  | Huawei, HiSilicon (Lin) | CT1#133-e/C1-216577 | agreed
| Server procedure: - The UAE server sends an registration response to the UAE client indicating success or failure of the registration. | 23.255 sub 7.6.2.1.2, 7.6.3.2, S6-212140 | Huawei, HiSilicon (Lin) | CT1#132-e/C1-215768 | agreed
| Server procedure: - The UAE server sends a deregistration response to the UAE client. | 23.255 sub 7.6.2.2.2, 7.6.3.4, S6-212140 | Huawei, HiSilicon (Lin) | CT1#132-e/C1-215772 | agreed
| Server procedure: - The UAE server sends an registration update response to the UAE client. | 23.255 sub 7.6.2.3.2, 7.6.3.6, S6-212140 | Huawei, HiSilicon (Lin) | CT1#132-e/C1-215770 | agreed
|  |  | Huawei, HiSilicon (Lin) | CT1#133-e/C1-216577 | agreed
Coding
| Application unique ID |  | Huawei, HiSilicon (Lin) | CT1#134-e/C1-221637 | agreed
| Structure |  | Huawei, HiSilicon (Chen) | CT1#131-e/C1-214990 | agreed
|  |  | Huawei, HiSilicon (Chen) | CT1#132-e/C1-215882 | agreed
|  |  | Huawei, HiSilicon (Chen) | CT1#132-e/C1-215885 | agreed
|  |  | Huawei, HiSilicon (Lin) | CT1#133-e/C1-216579 | agreed
|  |  | Huawei, HiSilicon (Chen) | CT1#133-e/C1-216734 | agreed
|  |  | Huawei, HiSilicon (Lin) | CT1#133bis-e/C1-220313 | agreed
|  |  | Huawei, HiSilicon (Lin) | CT1#133bis-e/C1-220314 | agreed
|  | S6-220389 | Huawei, HiSilicon (Chen) | CT1#135-e/C1-223137 | agreed
|  |  | Huawei, HiSilicon (Chen) | CT1#137-e/C1-224556 | TBD
| XML schema |  | Huawei, HiSilicon (Chen) | CT1#131-e/C1-214992 | agreed
|  |  | Huawei, HiSilicon (Chen) | CT1#132-e/C1-215884 | agreed
|  |  | Huawei, HiSilicon (Chen) | CT1#132-e/C1-215887 | agreed
|  |  | Huawei, HiSilicon (Lin) | CT1#133-e/C1-216581 | agreed
|  |  | Huawei, HiSilicon (Chen) | CT1#133-e/C1-216736 | agreed
|  |  | Huawei, HiSilicon (Lin) | CT1#133bis-e/C1-220317 | agreed
|  |  | Huawei, HiSilicon (Lin) | CT1#133bis-e/C1-220318 | agreed
|  | S6-220389 | Huawei, HiSilicon (Chen) | CT1#136-e/C1-223500 | agreed
| Data semantics |  | Huawei, HiSilicon (Chen) | CT1#131-e/C1-214991 | agreed
|  |  | Huawei, HiSilicon (Chen) | CT1#132-e/C1-215883 | agreed
|  |  | Huawei, HiSilicon (Chen) | CT1#132-e/C1-215886 | agreed
|  |  | Huawei, HiSilicon (Lin) | CT1#133-e/C1-216580 | agreed
|  |  | Huawei, HiSilicon (Chen) | CT1#133-e/C1-216735 | agreed
|  |  | Huawei, HiSilicon (Lin) | CT1#133e-bis/C1-220315 | agreed
|  |  | Huawei, HiSilicon (Lin) | CT1#133bis-e/C1-220837 | agreed
|  | S6-220389 | Huawei, HiSilicon (Chen) | CT1#136-e/C1-223499 | agreed
| MIME types |  | Huawei, HiSilicon (Lin) | CT1#133-e/C1-216578 | agreed
24.545
| Potential enhancements to SEAL LMS |  |  |  |  | Based on the current SA6 status up to 2022.02, there is no new enhancements to SEAL LMS under CT1 remit.
24.548
| Potential enhancements to SEAL NRMS |  |  |  |  | Based on the current SA6 status up to 2022.02, there is no new enhancements to SEAL NRMS under CT1 remit.
27.007
Enhancements to support new AT-commands to control MT supporting UAE layer for UAS applications
| A new AT CMD to activate or deactivate the UAE layer support in the MT. Once activated, the UE is a UE supporting UAS services and once deactivated, the UE is a UE not supporting UAS services. |  | Huawei, HiSilicon (Lin) | CT1#134-e/C1-221634 | agreed