## Tdoc cover sheet
3GPP TSG CT WG1 Meeting #137e Electronic meeting; 18-26 August 2022 |  | C1-224934
Source: | CATT, OPPO
Title: | Work plan for the CT1 part of 5G_ProSe-CT
Agenda item: | 17.2.18
Document for: | Discussion

## Contributions plan
Contribution Plan
Spec | Topic | Related LS or other WG tdoc(s) # | CT1 meeting #; tdoc(s) # | Comments | Open issues
24.554
| TS skeleton |  | #128e; C1-211183
| TS scope |  | #128e; C1-211184
| Types of discovery procedures |  | #129e; C1-212046
| Match report procedure for restricted ProSe direct discovery model A |  | #129e; C1-212274
| Match report procedure for restricted ProSe direct discovery model B |  | #129e; C1-212275
| Match Report procedure for open ProSe direct discovery |  | #129e; C1-212276
| Discovery overview |  | #129e; C1-212383
| Overview of TS 24.554 |  | #129e; C1-212384
| Add EN for U2U |  | #129e; C1-212385
| Announce request procedure for open ProSe direct discovery |  | #129e; C1-212468 |  | Overlapping description on PROSE PC5 DISCOVERY in clause 6.2.2, 6.2.3, 6.2.6 and 6.2.7 with clause 6.2.14
| Monitor request procedure for open ProSe direct discovery |  | #129e; C1-212469
| Announce request procedure for restricted ProSe direct discovery model A |  | #129e; C1-212470 |  | Overlapping description on PROSE PC5 DISCOVERY in clause 6.2.2, 6.2.3, 6.2.6 and 6.2.7 with clause 6.2.14
| Monitor request procedure for restricted ProSe direct discovery model A |  | #129e; C1-212472
| Announcing Alert procedure |  | #129e; C1-212474
| Direct discovery update procedure for open discovery |  | #129e; C1-212475
| Precedence of ProSe configuration parameters |  | #129e; C1-212477
| Configuration parameters for 5G ProSe Direct Discovery |  | #129e; C1-212488
| Direct Discovery update procedure for restricted discovery |  | #129e; C1-212495
| Discoverer request procedure for restricted ProSe Direct Discovery Model B |  | #129e; C1-212498 |  | Overlapping description on PROSE PC5 DISCOVERY in clause 6.2.2, 6.2.3, 6.2.6 and 6.2.7 with clause 6.2.14
| TS 24.554: Overview of 5G ProSe direct communications. |  | #129e; C1-212505
| Discoveree request procedure for restricted ProSe Direct Discovery Model B |  | #129e; C1-212507 |  | Overlapping description on PROSE PC5 DISCOVERY in clause 6.2.2, 6.2.3, 6.2.6 and 6.2.7 with clause 6.2.14
| UE-requested 5G ProSe policy provisioning procedure |  | #129e; C1-212531
| 5G ProSe Direct Link Establishment Procedure |  | #129e; C1-212572
| 5G ProSe PC5 QoS flow establishment |  | #129e; C1-212574
| 5G ProSe Data transmission mechanism over PC5 unicast link |  | #129e; C1-212579
| TS 24.554: Configuration parameters for 5G ProSe direct communication over PC5 interface |  | #129e; C1-212586
| TS 24.554: 5G ProSe direct link modification procedure. |  | #129e; C1-212587
| TS 24.554: 5G ProSe direct link identifier update procedure |  | #129e; C1-212588
| TS 24.554: 5G ProSe direct link keep-alive procedure. |  | #129e; C1-212589
| TS 24.554: 5G ProSe direct discovery procedure over PC5 interface |  | #129e; C1-212590 |  | Overlapping description on PROSE PC5 DISCOVERY in clause 6.2.2, 6.2.3, 6.2.6 and 6.2.7 with clause 6.2.14
| TS 24.554: Group member discovery over PC5 interface |  | #129e; C1-212591
| 5G ProSe Direct Link Release Procedure |  | #129e; C1-212592
| 5G ProSe IE definitions for Direct Establishment and Direct Release procedures |  | #129e; C1-212594
| Removal of UE-to-UE relay related editor's notes |  | #130e; C1-213020
| TS 24.554: Configuration parameters for U2N relay |  | #130e; C1-213031
| Clean-up and Clarification on announcing UE operation |  | #130e; C1-213043
| Clean-up and Clarification on monitoring UE operation |  | #130e; C1-213044
| Clean-up and Clarification on discoveree UE operation |  | #130e; C1-213045
| Clean-up and Clarification on discoverer UE operation |  | #130e; C1-213046
| Adding IEs definitions of some missing IEs for 5G ProSe procedures |  | #130e; C1-213202
| Correcting the reference point PC3 to be PC3a |  | #130e; C1-213203
| Unifying the terminology of the 5G ProSe direct communication |  | #130e; C1-213205
| Update configuration parameters |  | #130e; C1-213568
| Add path selection for direct communication |  | #130e; C1-213569
| Handling of unknown, unforeseen, and erroneous protocol data |  | #130e; C1-213570
| Timer table |  | #130e; C1-213571
| PROSE PC5 DISCOVERY message and Ies |  | #130e; C1-213572
| Introducing the Relay Discovery Additional Information procedure |  | #130e; C1-213667
| Introducing the UE-to-network relay selection procedure |  | #130e; C1-213668
| Introducing the UE-to-network relay reselection procedure |  | #130e; C1-213670
| Unifying the terminology for PROSE PC5 |  | #130e; C1-213671
| Configuration parameters for U2N relay |  | #130e; C1-213674
| UE ProSe policy transmission |  | #130e; C1-213754
| UE-to-Network Relay Discovery procedure |  | #130e; C1-213755
| Provisioning of 5G ProSe configuration information signalling messages |  | #130e; C1-213756
| TS24.554: Broadcast mode communicaiton over PC5 interface |  | #130e; C1-213767
| TS24.554: UE-to-Network Relay Discovery over PC5 interface (Model B) |  | #130e; C1-213768
| TS24.554: Update UE-requested 5G ProSe policy provisioning procedure for adding new request type |  | #130e; C1-213770
| Update to Precedence of ProSe configuration parameters |  | #130e; C1-213802
| Defining the 5G ProSe signalling messages |  | #130e; C1-213843
| Correcting wrong references in the signalling messages definitons |  | #131e; C1-214312
| Correcting the names of MSB of KNRP ID and LSB of KNRP ID |  | #131e; C1-214313
| Correcting some PC3a messages names |  | #131e; C1-214334
| Provisioned radio resources |  | #131e; C1-214469
| Add the missing description on ProSe under avoiding double barring |  | #131e; C1-214482
| correction on precedence of configuration |  | #131e; C1-215036
| L3 relay: clarification on a RSC per U2N relay discovery message |  | #131e; C1-214595
| L3 relay: Correction on U2N relay discovery procedure |  | #131e; C1-214597
| PDU session type mandatory for RSC |  | #131e; C1-214794
| Update relay configuration parameters |  | #131e; C1-214813
| Layer-3 UE-to-Network relay with N3IWF support |  | #131e; C1-214951
| correction on precedence of configuration |  | #131e; C1-215036
| L3 relay: update on configuration parameters for 5G ProSe UE-to-network Relay |  | #131e; C1-215038
| Update direct discovery configuration parameters |  | #131e; C1-215039
| Groupcast mode 5G ProSe direct communication over PC5 |  | #131e; C1-215058
| Clean-up for group member direct discovery procedure |  | #131e; C1-215060
| ProSe PC5 discovery message function defination and contents for UE-to-Network Relay |  | #131e; C1-215066
| Adding ProSe PC5 signaling message type for ProSe dirct discovery message over PC5 interface |  | #131e; C1-215067
| QoS handling for Relay operations |  | #131e; C1-215069
| Clean-up for UE-to-Network Relay discovery procedure |  | #131e; C1-215072
| IP address allocation for L3 UE-to-Network Relay |  | #131e; C1-215037
| Listing the Relay Discovery Additional Information procedures |  | #131e; C1-215107
| Adding the Overview clause for the 5G ProSe UE-to-network relay |  | #131e; C1-215110
| Adding the trigger for the Remote UE report procedure |  | #131e; C1-215113
| Adding the contents of the PROSE_PC5_DISCOVERY message for the Relay Discovery Additional Information procedure |  | #131e; C1-215119
| Removing ProSe Application ID and User Info ID from PROSE PC5 DISCOVERY messages |  | #131e; C1-215127
| Adding the Relay Service Code to the ProSe direct link establishment request |  | #131e; C1-215140
| Checking whether the associated S-NSSAI with Relay Service Code is in the Allowed NSSAI for Layer-3 UE-to-Network Relay discovery |  | #131e; C1-215141
| Add ProSe Ethernet packet filter set for ProSe direct communication |  | #132e; C1-215615
| Add layer indications of Layer-2/Layer-3 for 5G ProSe direct discovery |  | #132e; C1-215616
| Correct the timer in figure |  | #132e; C1-215620
| Resolving the Editor's note related to the inclusion of the NCGI in the relay discovery additional information |  | #132e; C1-215829
| Referring to the relay UE as "5G ProSe UE-to-network relay UE" |  | #132e; C1-215844
| Coding of PC3a messages |  | #132e; C1-216034
| Correction on relay reselection |  | #132e; C1-216035
| Correction on QoS handling on L3 relay UE |  | #132e; C1-216036
| Add relay related hanlding to direct link management procedure |  | #132e; C1-216037
| Remove editor's notes |  | #132e; C1-216038
| Align cause value |  | #132e; C1-216041
| IPv6 prefix delegation via DHCPv6 for 5G ProSe layer-3 UE-to-network relay |  | #132e; C1-216095
| Replace "ProSe application identifier" with "ProSe identifier" |  | #132e; C1-216106
| clarification on not support of MBS |  | #132e; C1-216147
| Correct the indication of using N3IWF access |  | #132e; C1-216155
| Correction of target info for group member discovery |  | #132e; C1-216156
| Determinate destination L2 ID of group member discovery |  | #132e; C1-216158
| Resolve EN for combinations of pack filter sets |  | #132e; C1-216159
| Resolve EN for public safety of group member discovery |  | #132e; C1-216160
| Add ProSe direct discovery PC5 message type in PROSE PC5 DISCOVERY message |  | #132e; C1-216175
| Impact of NAS level congestion control for 5G ProSe UE-to-Network Relay |  | #132e; C1-216162
| New conditions for releasing the 5G ProSe PC5 direct link |  | #132e; C1-216183
| Updates for Relay Discovery Additional Information procedure |  | #132e; C1-216184
| 5G Prose layer-2 UE-to-network relay UE to trigger Service Request procedure due to layer-2 relaying |  | #132e; C1-216186
| Cell ID announcement request procedure |  | #132e; C1-216188
| The indication of direct discovery message for the transmission of PC5 DISCOVERY message |  | #132e; C1-216189
| Terms and abbreviations in TS 24.554 |  | #132e; C1-216190
| Redefine monitoring UE |  | #132e; C1-216191
| Update destination layer 2 ID for remote |  | #133e; C1-216701
| Remove EN on ARP |  | #133e; C1-216704
| resolving EN for N3IWF selection |  | #133e; C1-216776
| Correction on ProSe application ID |  | #133e; C1-216896
| Corrections to some IEs in the PROSE DIRECT LINK ESTABLISHMENT REQUEST message and PROSE DIRECT LINK ESTABLISHMENT ACCEPT message |  | #133e; C1-216990
| Selecting PC5 Discovery Model if both Model A and Model B are supported by the UE |  | #133e; C1-216991
| Correcting the referral to the relay UE to be "5G ProSe UE-to-network relay UE" |  | #133e; C1-216992
| Reusing an existing PDU session to perform the 5G ProSe layer-3 UE-to-network relay with N3IWF |  | #133e; C1-217005
| Removing the ENs for ProSe timer value |  | #133e; C1-217119
| Correction on group member discovery |  | #133e; C1-217145
| Correction on PC3a coding |  | #133e; C1-217148
| Correction on IE name in XML |  | #133e; C1-217149
| Update to Layer-2 Relay selection |  | #133e; C1-217164
| Introduction of TS 33.503 and other cleanups |  | #133e; C1-217193
| Correction on link local IPv6 address |  | #133e; C1-217194
| Non-IP PDU handling for ProSe Direct Communication |  | #133e; C1-217270
| Clarification on target group info when discovering an application layer group |  | #133e; C1-217362
| Use ProSe ID to represent a ProSe service |  | #133e; C1-217363
| Clarification on relay operation in mobility restriction |  | #133e; C1-217364
| The inclusion of NCGI in the PROSE PC5 DISCOVERY message for layer-2 UE-to-network relay discovery announcement and layer-2 UE-to-network relay discovery response |  | #133e; C1-217391
| Clarifications for the Relay Discovery Additional Information procedure |  | #133e; C1-217394
| Releasing PDU session on revoking Service Authorization for 5G ProSe layer-3 UE-to-network relay UE |  | #133e; C1-217398
| Removing Relay TAI from the PROSE PC5 DISCOVERY message for layer-3 UE-to-network relay discovery response |  | #133e; C1-217403
| IP address/prefix is not included in the changed identifiers for the 5G ProSe direct link identifier update procedure in case of layer-2 relaying |  | #133e; C1-217408
| Clarification on path preference mapping rules |  | #133bis-e; C1-220462
| QoS flow descriptions IE to become optional in the PROSE DIRECT LINK SECURITY MODE COMPLETE message for Layer-2 Relaying |  | #133bis-e; C1-220489
| Claean-ups related to the terminology "NR" for 5G ProSe |  | #133bis-e; C1-220494
| Resolving the Editor's Note related to the condition of the optional IEs in the 5G ProSe PC5 direct discovery messages |  | #133bis-e; C1-220497
| Correcting the name of the De-registration procedure and other corrections |  | #133bis-e; C1-220498
| Correction to ProSeP policy provisioning procedure |  | #133bis-e; C1-220499
| Setting the PC5 signalling integrity security policy to “REQUIRED” for 5G ProSe Layer-3 UE-to-Network Relay |  | #133bis-e; C1-220500
| ProSe direct link security mode control procedure |  | #133bis-e; C1-220601
| IEI in messages |  | #133bis-e; C1-220633
| New cause for ProSe direct link release from AS layer |  | #133bis-e; C1-220634
| Length correction |  | #133bis-e; C1-220635
| Clarify L2 ID-initial discovery messages |  | #133bis-e; C1-220636
| Configuration update for security |  | #133bis-e; C1-220637
| Security for open direct discovery |  | #133bis-e; C1-220638
| Security for restricted direct discovery |  | #133bis-e; C1-220639
| Additional parameters announcement procedure |  | #133bis-e; C1-220686
| Remove target group info |  | #133bis-e; C1-220688
| Update to coding of path preference mapping rules field |  | #133bis-e; C1-220743
| Update to QoS handling of L3 U2N relay without N3IWF to include PC5 QoS rule |  | #133bis-e; C1-220745
| Update to link establishment procedure for PC5 QoS rule |  | #133bis-e; C1-220746
| Clarification on 5G ProSe direct link context |  | #133bis-e; C1-220752
| Specifying the usage of PC5 QoS Rules in the ProSe PC5 direct link procedures |  | #133bis-e; C1-220775
| Deriving the PC5 packet filters from the packet filters received over Uu reference point by the layer-3 Relay UE |  | #133bis-e; C1-220777
| Clarifications on the parameters provided in the Relay Discovery Additional Information procedure and the destination layer-2 ID for Relay discovery |  | #133bis-e; C1-220779
| Defining the Metadata IE that is used in the 5G ProSe direct discovery messages |  | #133bis-e; C1-220781
| Missing description of Metadata information in the procedures of 5G ProSe direct discovery |  | #133bis-e; C1-220782
| Referring to the spec of Security aspects for 5G ProSe in the Overview clause |  | #133bis-e; C1-220789
| Modifications for Security parameters related to Open 5G ProSe Direct Discovery (Model A) |  | #133bis-e; C1-220791
| Modifications for Security parameters related to Restricted 5G ProSe Direct Discovery (Model A and Model B) |  | #133bis-e; C1-220794
| Definition of PC5 QoS rule IE |  | #133bis-e; C1-220803
| Clarifications on QoS handling for 5G ProSe layer-3 UE-to-network relay without N3IWF |  | #133bis-e; C1-220805
| QoS handling for 5G ProSe layer-3 UE-to-network relay with N3IWF |  | #133bis-e; C1-220807
| Clarification on group member discovery model |  | #134e; C1-221149
| Correction of L2 ID in PROSE PC5 DISCOVERY message |  | #134e; C1-221154
| Resolve the ENs in clause 7.3.2 |  | #134e; C1-221158
| Clean up validity timers and TTL timers |  | #134e; C1-221163
| Clarification on PC5 QoS rule |  | #134e; C1-221312
| Aligning terminologies of 5G ProSe remote UE and 5G ProSe UE-to-network relay UE |  | #134e; C1-221492
| Referring to 5G ProSe security specification 3GPP TS 33.503 |  | #134e; C1-221494
| Security of 5G ProSe procedures over the PC3a interface |  | #134e; C1-221495
| confidentiality protection of the UE Identity transmitted during the PC3a control protocol procedures for 5G ProSe direct discovery |  | #134e; C1-221496
| Resolving the Editor's note related to NR-PC5 unicast security policies in TS 24.554 |  | #134e; C1-221499
| Some corrections for different 5G ProSe procedures |  | #134e; C1-221501
| Resolving the Editor's notes related to security topics for different 5G ProSe direct link signalling messages |  | #134e; C1-221506
| Corrections for security parameters related to 5G ProSe PC5 Direct Discovery messages |  | #134e; C1-221508
| Correcting references to the 5G ProSe direct link authentication procedure |  | #134e; C1-221509
| Clarifications on group member discovery over PC5 interface |  | #134e; C1-221570
| Clarifications on security parameters in procedures for restricted 5G ProSe direct discovery |  | #134e; C1-221571
| Corrections on 5G ProSe discovery messages over PC3a |  | #134e; C1-221572
| Resolving Editor's Notes in announcing alert procedure |  | #134e; C1-221574
| Miscellaneous changes |  | #134e; C1-221782
| Remove ENs on security |  | #134e; C1-221783
| IP address allocation for broadcast and groupcast modes of 5G ProSe direct communication |  | #134e; C1-221837
| Clarification on target user info |  | #134e; C1-221863
| Clarification on path preference mapping rule |  | #134e; C1-221864
| Including the SUCI of the remote UE in the direct link establishment request procedure |  | #134e; C1-221873
| Introducing the 5G ProSe direct link re-keying procedure |  | #134e; C1-221875
| Introducing the 5G ProSe direct link authentication procedure |  | #134e; C1-221877
| Resolving the Editor's notes related to security topics for different 5G ProSe direct link procedures |  | #134e; C1-221879
| Applicability of 5G ProSe direct link security mode control procedure for layer-2 UE-to-network relay |  | #134e; C1-221880
| Clarification on ProSe identifier for PC5 QoS rule |  | #134e; C1-221949
| IANA registration for MIME types |  | #135e; C1-222570
| Clarifications on 5G ProSe direct discovery procedure over PC5 interface |  | #135e; C1-222633
| Resolving Editor's Notes in match report |  | #135e; C1-222634
| Corrections for UTC-based counter LSB parameter |  | #135e; C1-222635
| PC5 discovery message encoding changes for security protection |  | #135e; C1-222770
| Release of PC5 link by an L2 remote UE due to mobility management back-off timer |  | #135e; C1-222803
| Correction for the privacy timer of 5G ProSe transmission over PC5 |  | #135e; C1-222880
| Replacing configured PC5 security policies with the PC5 security policies received during restricted 5G ProSe direct discovery procedures |  | #135e; C1-222883
| Clarification regarding the application identity used in the 5G ProSe direct discovery procedures |  | #135e; C1-222884
| Signalling integrity protection policy for layer-2 UE-to-network relay |  | #135e; C1-222885
| Configuring PC5 security policies for layer-2 UE-to-network relay |  | #135e; C1-222886
| Resolving the EN related to possible changes to the 5G ProSe direct link release procedure due to the security requirements of UE-to-network relay |  | #135e; C1-222893
| Rejection of 5G ProSe direct link due to unsuccessful PDU session establishment by L3 relay UE |  | #135e; C1-223011
| Rejection of PC5 link modification due to lack of packet filters for the PDU session |  | #135e; C1-223012
| DRX configuration parameters and Tx profiles |  | #135e; C1-223014
| Privacy timer for U2N relay |  | #135e; C1-223015
| Security algorithm exchange in restricted direct discovery |  | #135e; C1-223016
| RRC container in L2 relay discovery message |  | #135e; C1-223017
| L2 relay not using authentication over PC5 |  | #135e; C1-223018
| ProSe remote user key procedure |  | #135e; C1-223019
| PC5-S for forwading EAP message |  | #135e; C1-223020
| Resolving Editor's Notes in 5G ProSe UE-to-network relay discovery over PC5 procedures |  | #135e; C1-223078
| Update to configuration parameters |  | #135e; C1-223079
| Update to direct link establishment for 5G ProSe layer 3 relay |  | #135e; C1-223080
| Update to Mobility Restrictions for 5G ProSe UE-to-Network Relaying |  | #135e; C1-223081
| Update to QoS handling for layer-3 relay with N3IWF |  | #135e; C1-223082
| ProSe application traffic descriptor introduction |  | #135e; C1-223083
| Changes to Match report message for MIC check |  | #135e; C1-223084
| Pending indication for PDU session with secondary authentication for remote UE |  | #135e; C1-223096
| Clarification on 5G PKMF |  | #135e; C1-223097
| New cause for direct link release |  | #135e; C1-223118
| Update to QoS flow handling for L3 U2N relay |  | #135e; C1-223128
| Clarification on different source L2 IDs for discovery and communication |  | #135e; C1-223149
| Add target user ID in relay discovery solicitation message |  | #135e; C1-223150
| Handling of destination layer-2 ID collision for direct discovery and direct communication in the UE |  | #135e; C1-223152
| Clarification on the initiating UE stopping passing the same PROSE PC5 DISCOVERY message to lower layers |  | #135e; C1-223153
| General parts for procedures for PC8 interface |  | #135e; C1-223161
| 5G ProSe UE-to-network relay discovery security parameters request procedure for PC8 interface |  | #135e; C1-223163
| Key request procedure for PC8 interface |  | #135e; C1-223165
| Handling of unknown, unforeseen, and erroneous protocol data for PC8 interface |  | #135e; C1-223170
| Harmonizing the terminologies "LSBs of KNRP ID" and "MSBs of KNRP ID" |  | #135e; C1-223172
| Times for PC8 interface |  | #135e; C1-223173
| Unifying the terminologies of 5G ProSe UE-to-network relay UE and 5G ProSe remote UE |  | #135e; C1-223174
| Security protection of the restricted 5G ProSe Direct Discovery messages over PC5 |  | #135e; C1-223176
| UE-to-network relay unicast direct communication procedures over PC5 interface |  | #135e; C1-223186
| Applicability of 5G ProSe direct link authentication procedure to UE-to-network relay |  | #135e; C1-223188
| Resolving the ENs related to possible changes to the 5G ProSe direct link establishment procedure due to the security requirements of UE-to-network relay |  | #135e; C1-223189
| Resolving the EN related to possible changes to the 5G ProSe direct link re-keying procedure due to the security requirements of UE-to-network relay |  | #135e; C1-223190
| Resolving the EN related to possible changes to the 5G ProSe direct link security mode control procedure due to the security requirements of UE-to-network relay |  | #135e; C1-223192
| Introducing KNRP freshness parameter 1 and KNRP freshness parameter 2 |  | #135e; C1-223194
| Introducing the GBA Push Info (GPI) in the 5G ProSe direct link security mode control procedure |  | #135e; C1-223196
| Handling of synchronization failure for 5G ProSe UE-to-network relay security |  | #135e; C1-223202
| Triggering 5G ProSe direct link release procedure due to secondary authentication failure |  | #135e; C1-223203
| Authorization to use Model A and Model B for 5G ProSe UE-to-network relay discovery |  | #135e; C1-223209
| References, definitions and abbreviations for 5G ProSe charging |  | #136e; C1-223375
| IANA registrations for MIME types for 3gpp-5g-prose-pc3ch+xml |  | #136e; C1-223382
| Provisioning of ProSe NR frequencies associated with the ProSe identifier for unicast communication mode to lower layers |  | #136e; C1-223588
| Pending indication for PDU session with secondary authentication for remote UE |  | #136e; C1-223594
| RRC container in L2 relay discovery message |  | #136e; C1-223605
| ProSe remote user key procedure |  | #136e; C1-223606
| Correction on indication in L2 relay UE to send SR |  | #136e; C1-223609
| Relay Service Code Privacy Protection |  | #136e; C1-223684
| Correcting missing implementation related to security preservation for 5G ProSe |  | #136e; C1-223823
| Correction for the cases of deleting the old security context for 5G ProSe |  | #136e; C1-223824
| Clarification on different source L2 IDs for discovery and communication |  | #136e; C1-223833
| Correction on 5G ProSe direct discovery over PC5 when UE not in coverage |  | #136e; C1-223834
| Remove the default destination layer-2 ID in direct communication when provisioning |  | #136e; C1-223837
| Authorization to use Model A and Model B for 5G ProSe UE-to-network relay discovery |  | #136e; C1-223840
| Some editorial corrections |  | #136e; C1-223877
| PC5-S for forwarding EAP message |  | #136e; C1-223965
| Editorial changes |  | #136e; C1-223968
| Changes to Match report message for MIC check |  | #136e; C1-224085
| Charging information collection for 5G ProSe Direct Discovery |  | #136e; C1-224108
| Precedence between the 5G PKMF address provided in the ProSeP by the PCF and by the 5G DDNMF |  | #136e; C1-224135
| Transport protocol for PC3ch Control Protocol for 5G ProSe direct communication |  | #136e; C1-224137
| Update to configuration by application server |  | #136e; C1-224144
| Rejection of 5G ProSe direct link due to congestion at the 5GSM layer in the layer-3 UE to network relay |  | #136e; C1-224156
| Adding DRX handling for unicast communication procedures |  | #136e; C1-224166
| Adding 5G PKMF address request procedure in general clause |  | #136e; C1-224177
| Clairification on performing 5G ProSe direct discovery over PC5 |  | #136e; C1-224178
| PKMF address request procedure over PC3a interface |  | #136e; C1-224179
| Clarification regarding the application identity used in the 5G ProSe direct discovery procedures - ALT. B |  | #136e; C1-224180
| The impact of NR Tx profile on the transmission and reception of Broadcast and Groupcast modes of 5G ProSe communication |  | #136e; C1-224203
| Introducing the validity timer of the security related parameters for discovery |  | #136e; C1-224218
| Applicability of Key establishment information container IE to the security of the UE-to-network relay |  | #136e; C1-224219
| Some miscellaneous corrections for 5G ProSe |  | #136e; C1-224221
| Resolving the EN related to possible changes to the 5G ProSe direct link security mode control procedure due to the security requirements of UE-to-network relay |  | #136e; C1-224222
| Handling of synchronization failure for 5G ProSe UE-to-network relay security |  | #136e; C1-224223
| Rejecting PC5 connection establishment request upon security failure |  | #136e; C1-224224
| UE-to-network relay reselection upon security failure |  | #136e; C1-224225
| UE not providing SUPI in PC3a messages |  | #136e; C1-224234
| PC8 messages XML elements, semantic and parameters |  | #136e; C1-224235
| Key request procedure for PC8 interface |  | #136e; C1-224241
| General parts for procedures for PC8 interface |  | #136e; C1-224243
| Usage information reporting configuration in the UE |  | CP#96; CP-221072
| Procedures for PC3ch Control Protocol for ProSe direct communication |  | CP#96; CP-221073
| Messages transmitted over the PC3ch interface |  | CP#96; CP-221074
| Formats for messages transmitted over the PC3ch interface |  | CP#96; CP-221075
24.555
| TS skeleton |  | #128e; C1-211187
| TS scope |  | #128e; C1-210884
| Add EN for U2U |  | #129e; C1-212386
| Descriptions of UE policies for 5G ProSe |  | #129e; C1-212396
| UE policy part encoding |  | #129e; C1-212530
| Removal of UE-to-UE relay related editor's notes |  | #130e; C1-213021
| Encoding policy of direct communication |  | #130e; C1-213746
| Encoding policy of direct discovery |  | #130e; C1-213574
| Update direct discovery configuration parameters |  | #131e; C1-214797
| ProSe policy coding for U2N relay |  | #131e; C1-214796
| Replace "ProSe application identifier" with "ProSe identifier" |  | #132e; C1-215653
| Encoding of N3IWF selection information for 5G ProSe layer-3 remote UE |  | #132e; C1-216108
| Update ProSeP coding for relay and remote |  | #133e; C1-217146
| Update ProSe identifier coding |  | #133e; C1-217147
| Clarify L2 ID-initial discovery messages |  | #133bis-e; C1-220067
| Remove FFS on ProSeP based on UE capability |  | #133bis-e; C1-220068
| Corrections on encoding of UE policies for 5G ProSe direct communications |  | #134e; C1-221160
| Modify the encoding of PDU session parameters for layer-3 relay UE field |  | #134e; C1-221161
| Policy coding update for security |  | #134e; C1-221315
| Correcting the references to the figure and table of "ProSe identifier to ProSe application server address mapping rules" in TS 24.555 |  | #134e; C1-221497
| Resolving the Editor's note related to NR-PC5 unicast security policies in TS 24.555 |  | #134e; C1-221498
| spare RSC values |  | #134e; C1-221825
| Resolving the Editor's note related to the UE policies of the security parameters used for UE-to-network relay in TS 24.555 |  | #134e; C1-221874
| ProSeP update |  | #135e; C1-223021
| Encoding of 5G PKMF addressing information |  | #135e; C1-223098
| Clarification on coding of path preference mapping rule |  | #135e; C1-223148
| Corrections for "PC5 security policies" and "PDU session parameters for layer-3 relay UE" in the ProSe policies |  | #135e; C1-223184
| Defining the "ProSe group IP multicast address" field |  | #135e; C1-223200
| Remove range in direct discovery configuration |  | #136e; C1-223612
| ProSeP update |  | #136e; C1-223966
| Remove coding for default destination layer-2 ID in direct communication when provisioning |  | #136e; C1-224181
| Resolving the EN related to security parameters used for the UE-to-network relay discovery over PC5 interface |  | #136e; C1-224217
| Corrections for the Authorized PLMN lists |  | #136e; C1-224227
| Encoding of UE policies for 5G ProSe usage reporting |  | CP#96; CP-221076
23.122
| PLMN selection triggered by ProSe communicatins over NR-PC5 |  | #131e; C1-215068
| L2 remote UE PLMN selection |  | #133bis-e; C1-220640
| PLMN selection based on RRC container from L2 relay |  | #135e; C1-222573
24.501
| UE ProSe capability negotiation with 5GC |  | #129e; C1-212473/#130e; C1-213739
| UE ProSe policy transmission |  | #129e; C1-212476
| ProSe as a trigger for Service Request procedure |  | #129e; C1-212542
| Network shall not release the RRC connection for ProSe services |  | #129e; C1-212558
| NAS to be aware when the UE triggered ProSe provisioning procedure starts and stops |  | #129e; C1-212571
| Resuming a connection due to ProSe discovery/communication over PC5 |  | #131e; C1-214799
| Introducing the Remote UE report procedure |  | #131e; C1-215117
| Requesting ProSe resources as a trigger for Service Request procedure |  | #131e; C1-215143
| Editorial corrections for the ProSe relay terminologies and capabilities |  | #132e; C1-215830
| NAS signalling recovery from fallback when the UE was only performing ProSe PC5 procedures |  | #132e; C1-216046
| Add the SMF shall provide the QoS flow description(s) for the PDU sessions used for relaying |  | #132e; C1-216150
| Triggering Service Request procedure due to lower layers request for ProSe layer-2 UE-to-network relay |  | #132e; C1-216185
| Correcting the reference of the spec in which the UE requests the PCF to provide ProSeP |  | #133e; C1-216993
| The type of the port number in Remote UE context list information element |  | #133e; C1-217195
| IPv6 prefix delegation via DHCPv6 for 5G ProSe layer-3 UE-to-network relay |  | #133e; C1-217196
| Corrections for Service Request procedure when requesting 5G ProSe resources is the trigger for the procedure |  | #133bis-e; C1-220504
| Collision of network initiated PDU session release and remote UE report procedures |  | #133bis-e; C1-220561
| Remote UE report not allowed when 5GSM BO timer is running |  | #133bis-e; C1-220627
| Correction of IEI values for the REMOTE UE REPORT message |  | #134e; C1-221811
| Update to NAS security mode command during PC5 link establishment |  | #134e; C1-222025
| The remote UE report procedure is initiated by a 5G ProSe layer-3 UE-to-network relay UE |  | #135e; C1-222876
| Secondary authentication via L3 relay |  | #135e; C1-223022
| Authentication and key agreement for 5G ProSe layer-3 UE-to-network relay |  | #135e; C1-223095
| UE-requested PDU session establishment procedure based on ProSeP |  | #135e; C1-223099
| IE coded as 'comprehension required' |  | #136e; C1-223404
| A few cleanups on 5G ProSe |  | #136e; C1-223590
| Invalid PDU session identity in Remote UE Report message |  | #136e; C1-223673
| Secondary authentication via L3 relay |  | #136e; C1-223967
| Interaction between 5GSM entity and upper layers with respect to the ProSeP |  | #136e; C1-224119
| The timer for authentication and key agreement for 5G ProSe UE-to-network relay |  | #136e; C1-224121
| Authentication and key agreement for 5G ProSe UE-to-network relay |  | #136e; C1-224123
24.502
| Support of QoS differentiation in case of accessing via UE-to-network relay |  | #134e; C1-221150
24.007
| Add 24.554 |  | #133bis-e; C1-220073
| Correction related to PC3a and PC3 messages |  | #135e; C1-223201
24.526
| UE policies for 5G ProSe policy |  | #129e; C1-212449/#130; C1-212981
| Adding the 5G ProSe UE-to-Network Relay support to the URSP |  | #131e; C1-215099
| Mapping of 5G ProSe Layer-3 UE-to-Network Relay offload when moving from N1 mode to S1 mode |  | #131e; C1-215097
| 5G ProSe Layer-3 UE-to-Network Relay Offload indication for the UEs capable to act as Remote Ues |  | #132e; C1-216181
| Alignment of ProSe Policy and V2X Policy |  | #134e; C1-221865
| Corrections on handling of the RSDs matching the existing connection |  | #135e; C1-223100
| Corrections on handling of the RSDs matching the existing connection |  | #136e; C1-224124
24.587
| Requested UE policies for 5G Prose |  | #129e; C1-212577
| Update on UE 5G ProSe Policy Request based on UE 5G ProSe Capability |  | #131e; C1-215064

## Expected contributions
Expected Contributions for future meetings
Spec | Topic | Related LS or other WG tdoc(s) # or TS # | Volunteered company/delegate | Contribution(s) | Open issues
24.554
| Control Plane Security Indicator in U2N configuration | Clause 5.1.4.1 | Nokia
| SDU type used over user plane for NR PC5 reference point | C1-224523/R2-2206597 | ZTE
SA3 TS 33.503
| U2N relay disocvery with 5G DDNMF while CP based procedure is used | Clause 6.1.3.2.2.1 and 6.1.3.2.2.2 | Nokia
| PRUK ID coding updae to include home network identifier, and to update the inclusion condition in PROSE DIRECT LINK ESTABLISHMENT REQUEST message | Clause 6.3.3.2.2 | ZTE
| PRUK ID of remote UE included in key response message from PKMF to relay UE | Clause 6.3.3.2.2 | ZTE
| Key request message IEs update | Clause 6.3.3.2.2 | ZTE
| HPLMN ID IE definition |  | Ericsson
| Corrections for PC8 interface to indicate PRUK ID in key accept | S3-221271 | Ericsson
| Corrections for PC8 interface to remove PC5 security policies from key accept | S3-221294 | Ericsson
| PC8 messages XML elements, semantic and parameters |  | Ericsson
| Requesting V2XP, ProSeP or both during registration |  | Ericsson
SA5 TS 32.277 v17.1.0
| UE policies for 5G ProSe usage information reporting in Requested UE policies |  | Ericsson
| Requesting UE policies for 5G ProSe usage information reporting |  | Ericsson
Editor's note
| Editor's note: It is FFS how the UE determines whether the security for 5G ProSe layer-3 relay uses the security procedure over control plane or the security procedure over user plane as specified in 3GPP TS 33.503 [34]. | Clause 7.2.2.2 | Nokia (see "Control Plane Security Indicator in U2N configuration")
| Editor’s note: detail operation of the mapping with the traffic descriptor in the ProSeP is FFS. | Clause 8.2.1.2.3.2, 8.2.1.3.1.2 | Nokia
| Editor's note: The interface name PC3ch may be changed based on the decision by SA WG5. | SA5 reply LS S5-224463, with attached draft CR S5-224462 | CATT
| Editor's note: It is FFS which PC5 link signalling message is used to convey the Pending indication or if there is any another approach to achieve the desired behavior. | SP-220701 | OPPO Nokia |  | Remove due to SA conclusion and SP-220701
Others
24.555
| Control Plane Security Indicator in U2N configuration | Clause 5.1.4.1 | Nokia
24.501
| ProSeP request in registration | Reply LS S2-2201294 | Ericsson; Lenovo; Huawei?
| 5GPRUK ID as remote user ID in remote UE report, per remote UE | TS 33.503 Clause 6.3.3.2.2 | Nokia | Related to the EN for remote UE identifier
| Editor's note: It is FFS what are the 5G ProSe remote UE identities that can be included in the Remote UE context list. Depending on the conclusion of this topic, the User identity field needs to be defined and also the Length of user identity is subject to change. | TS 23.304 clause 6.5.1.1 | Nokia
| Editor's note: It is FFS what are the types of 5G ProSe remote UE identities that can be included in the REMOTE UE REPORT message as this is waiting for stage-2 definitions. | TS 23.304 clause 6.5.1.1 | Nokia
| Editor's note: Whether other parameters are included is FFS and will be determined by SA3. |  | Nokia
| Editor’s note: Whether and why the Authorized QoS flow description IE is included is FFS. |  | OPPO (see "Remove secondary authentication")
| Remove secondary authentication | SP-220701 | OPPO
27.007

## Incoming LSs
Incoming liaision statements (LS)
Tdoc # | Topic | Reply LS | Related tdocs: CT1 meeting #; tdoc(s) # | Open issues | Comments
R2-2104654 | LS on R17 Layer-2 SL Relay of UE ID exposure in paging mechanism | N/A
R2-2106520 | LS on establishment/resume cause value and UAC on L2 SL Relay | C1-214795 | C1#131e
C1-215520 | LS on Tx Profile | N/A
C1-215522 | Reply LS on RAN dependency issues for 5G ProSe | N/A
C1-215540 | LS on UE POLICY PROVISIONING REQUEST message | C1-216298 | C1#132e
C1-217167 | LS on the indication of discovery message and PC5-S signalling to ProSe layer |  | C1#133e
S2-2201294 | Reply LS on UE POLICY PROVISIONING REQUEST message |  | C1#134e
S2-2201842 | LS reply on RSC determination in the remote UE for 5G ProSe Layer-3 UE-to-network relay scenario |  | C1#134e
S2-2201296 | LS reply on support of RAN sharing and discovery signalling |  | C1#134e
S2-2201298 | Reply LS on discovery and data associated to different L2 IDs |  | C1#134e
S5-224463 | Reply LS on name of the interface for usage information collection | Reply to C1-224296
CP-221322 | LS on CT specification on Control Plane based security procedures for 5G ProSe UE-to-Network Relay
R2-2206597 | Reply LS on SDU type used over user plane for NR PC5 reference point
S2-2204904 | LS on 5G ProSe security open items
SP-220716 | Reply LS on 5G ProSe security open items