## Tdoc cover sheet
3GPP TSG CT WG1 Meeting #142 Bratislava 22– 26 May 2023 |  | C1-233194
Source: | Huawei, HiSilicon
Title: | Work plan for the CT1 part of SEALDD
Agenda item: | 18.2.16
Document for: | Discussion

## Contributions plan
Contribution Plan
Spec | Topic | Related stage 2 agreed CR # other WG tdoc(s) # | Responsible company | Related LS or other WG tdoc(s) # | CT1 meeting #; tdoc(s) # | Comments | Open issues
24.543 | Data delivery management SEAL service
| TS - Skeleton |  | Huawei |  | #140; C1-230388
| Scope |  | Huawei |  | #140; C1-230389
| Definition of terms and abbreviations |  | Huawei |  | #140; C1-230868
| General description |  | Huawei |  | #140; C1-230869
| Functional entities |  | Huawei |  | #140; C1-230870
| General on on-network procedures |  | Huawei |  | #140; C1-230871
| SEALDD enabled signalling transmission connection establishment procedure | TS 23.433
| SEALDD enabled E2E redundant transmission procedure | TS 23.433
| SEALDD server discovery and selection procedure | TS 23.433
| SEALDD enabled data storage procedure | TS 23.433
| SEALDD server relocation procedure | TS 23.433
| SEALDD enabled data transmission quality measurement procedure | TS 23.433
| SEALDD enabled bandwidth control for different VAL users procedure | TS 23.433
| Off-network procedures |  | Huawei |  | #140; C1-230395
| Support for CoAP | TS 23.434 | Huawei |  | #140; C1-230872
24.544 | Group Management SEAL service
24.545 | Location Management SEAL service
24.546 | Configuration Management SEAL service
24.547 | Identity Management SEAL service
24.548 | Network Resource Management SEAL service
24.549 | Network slice capability management SEAL service
24.538 | Enabling MSGin5G service
24.558 | APIs for enabling the edge applications over 3GPP networks
| Seamless transport layer service continuity functionality | C3-230796 | Huawei

## Incoming LSs
Incoming liaision statements (LS)
Tdoc # | Topic | Reply LS | Related tdocs: CT1 meeting #; tdoc(s) # | Open issues | Comments

## Outgoing LSs
Outgoing liaision statements (LS)
Tdoc # | Topic | Related tdocs: CT1 meeting #; tdoc(s) # | Open issues | Comments