## Tdoc cover sheet
3GPP TSG CT WG1 Meeting #144 Xiamen, China, 09– 13 October 2023 |  | C1-237278
Source: | Huawei, HiSilicon
Title: | Work plan for MCOver5GProSe
Agenda item: | 18.3.4
Document for: | Discussion

## Contributions plan
Contribution Plan
Spec | Topic | Related stage 2 agreed CR # other WG tdoc(s) # | Responsible company | Related LS or other WG tdoc(s) # | CT1 meeting #; tdoc(s) # | Comments | Open issues
24.281
| PQI for MC over 5GProSe | TS 23.289 | Huawei
| Update to MC Video service to support 5GProSe UE-to-network relay | TS 23.289
24.282
| PQI for MC over 5GProSe | TS 23.289 | Huawei
24.379
| PQI for MC over 5GProSe | TS 23.289 | Huawei
| Suppport Groupcast mode 5G ProSe Direct Communication | TS 23.289
| Support Unicast mode 5G ProSe Direct Communication | TS 23.289
| Update to the MCPTT service to support 5GProSe UE-to-network relay | TS 23.289
24.481
| PQI for MC over 5GProSe | TS 23.289 | Huawei
| Update to the MC Group service to support 5GProSe UE-to-network relay | TS 23.289
24.483
| PQI for MC over 5GProSe | TS 23.289 | TD Tech
| Update to the MCS MO to support 5GProSe UE-to-network relay | TS 23.289
24.484
| PQI for MC over 5GProSe | TS 23.289 | Huawei
24.38
|  | TS 23.289 |  |  |  |  | Potential update of MCPTT media plane control specs to support MCOver5GProSe
24.581
|  | TS 23.289 |  |  |  |  | Potential update of MCVideo media plane control specs to support MCOver5GProSe
24.582
|  | TS 23.289 |  |  |  |  | Potential update of MCData media plane control specs to support MCOver5GProSe

## Incoming LSs
Incoming liaision statements (LS)
Tdoc # | Topic | Reply LS | Related tdocs: CT1 meeting #; tdoc(s) # | Open issues | Comments

## Outgoing LSs
Outgoing liaision statements (LS)
Tdoc # | Topic | Related tdocs: CT1 meeting #; tdoc(s) # | Open issues | Comments