## Tdoc cover sheet
3GPP TSG-CT WG1 Meeting #144 Xiamen, China, 9 - 13 October, 2023 |  |  | C1-237530
Source: |  | Xiaomi
Title: | Title | Work Plan: CT aspects of Ranging based services and sidelink positioning
Agenda Item: |  | 18.2.23
Document for: |  | Information

## CT1 Topics
Topic number | Description | Stage-2 reference | TS | Contributor | Meeting# | agreed tdoc# | status | Notes
A | General
| Skeleton of TS 24.514 |  | 24.514 | Xiaomi | CT1#141 | C1-232663 | agreed
| Scope of TS 24.514 |  | 24.514 | Xiaomi | CT1#141 | C1-232665 | agreed
| General section for ranging and sidelink positioning control |  | 24.514 | QUALCOMM | CT1#141 | C1-232783 | agreed | Clause 4
B | Provisioning of configuration information for Ranging/SL positioning service
Ranging_SL capability | Ranging capability over NAS | 23.586 Clause 5.1&6.2 | 24.501 | OPPO, ZTE, Qualcomm Incorporated, Nokia, Nokia Shanghai Bell, Ericsson | CT1#141 | C1-232640 | agreed | CR 5225 revised to CP-231304 (CT Meeting #100)
| Service request for ranging |  | 24.501 | OPPO | CT1#141 | C1-232750 | agreed | CR 5226
| Capability of SL Positioning Server UE over PC5 |  | 24.501 | vivo | CT1#142 | C1-234001 | agreed | CR 5437
Provisioning of configuration information for Ranging/SL | UE requested policy provisioning procedure for ranging |  | 24.514 | OPPO | CT1#141 | C1-232639 | agreed | Clause
| Extending “Requested UE policies IE” with an indicator for Ranging/SL Positioning policies |  | 24.587 | Nokia, Nokia Shanghai Bell, OPPO, xiaomi, Ericsson | CT1#141 | C1-232722 | agreed | CR 0269
| Transmission of Ranging/SL Positioning Policy |  | 24.501 | Nokia, Nokia Shanghai Bell, Ericsson | CT1#141 | C1-232723 | agreed | CR 5197
| Specifying and adding reference for Ranging/SL Positioning Policy |  | 24.526 | Nokia, Nokia Shanghai Bell, Ericsson | CT1#141 | C1-232724 | agreed | CR 0181
| RSLPP parameters |  | 24.514 | OPPO | CT1#142 | C1-234000 | agreed
| update RSLPP |  | 24.514 | OPPO | CT1#143 | C1-236094 | agreed
| RSLPP encoding |  | 24.514 | OPPO | CT1#143 | C1-236095 | agreed
C | Ranging/Sidelink Positioning UE discovery
UE discovery over PC5 for 5G ProSe capable Ues | General description for 5G ProSe capable UEs discovery over PC5 interface | 23.586 Clause 5.2&6.4.2.1 | 24.514 | xiaomi | CT1#142 | C1-234207 | agreed | Tdoc agreed with EN to be solved, depending on the outcome from RAN2/SA2/SA3
| Ranging/SL Positioning UE discovery in Model A with 5G ProSe capable Ues | 23.586 Clause 5.2&6.4.2.1 | 24.514 | xiaomi | CT1#142 | C1-234208 | agreed | Tdoc agreed with EN to be solved, depending on the outcome from RAN2/SA2/SA3
| Ranging/SL Positioning UE discovery in Model B with 5G ProSe capable Ues | 23.586 Clause 5.2&6.4.2.1 | 24.514 | xiaomi | CT1#143 | C1-236367 | agreed | Tdoc agreed with EN to be solved, depending on the outcome from RAN2/SA2/SA3
| Ranging/SL Positioning Group member discovery in Model A with 5G ProSe capable Ues | 23.586 Clause 5.2&6.4.2.2 | 24.514 | xiaomi | CT1#143 | C1-236101 | agreed | Tdoc agreed with EN to be solved, depending on the outcome from RAN2/SA2/SA3
| Ranging/SL Positioning Group member discovery in Model B with 5G ProSe capable Ues | 23.586 Clause 5.2&6.4.2.2 | 24.514 | xiaomi | CT1#143 | C1-236102 | agreed | Tdoc agreed with EN to be solved, depending on the outcome from RAN2/SA2/SA3
| Ranging/SL Positioning UE discoverywith V2X capable UE | 23.586 Clause 5.2&6.4.3 | 24.514 | xiaomi | CT1#142 | C1-234209 | agreed
| Ranging and sidelink positioning UE discovery | 23.586 Clause 5.2&6.4.2.1 | 24.514 | ZTE | CT1#143 | C1-235869 | agreed
| UE-LMF interaction for Located UE Discovery | 23.586 Clause 5.2&23.273 Clause 6.20 | 24.514/24.571 |  |  |  | expected | Ineraction between UE and LMF in SLPP or LCS-SS is not clear in stage 2 in SA2 spec
| UE-LMF interaction for SL Positioning Server UE | 23.586 Clause 5.2 | 24.514/24.571 |  |  |  | expected | Ineraction between UE and LMF in SLPP or LCS-SS is not clear in stage 2 in SA2 spec
| Update UE discovery procedures on security aspects |  | 24.514 |  |  |  | expected | procedure and element for the security is not clear in stage 2 in SA3 spec
D | Ranging/Sidelink Positioning communication
Ranging and sidelink positioning direct communication over PC5 | General for Ranging and sidelink positioning direct communication over PC5 |  | 24.514 | QUALCOMM | CT1#142 | C1-232783 | agreed | clause 7.2.1
| 5G ProSe communication for ranging and sidelink positioning | the ProSe PC5 link establishment and maintainance, which is common to all the stage 2 procedures for Ranging/Sidelink Positioning communication over PC5 | 24.514 | xiaomi | CT1#142 | C1-234011 | agreed | The general part and referring part in 24.514
| ProSe PC5 link establishment and maintainance procedures for ranging and sidelink positioning (direct link modification, direct link identifier update, direct direct link keep-alive, direct direct link release) |  | 24.554 |  |  |  | expected | Update for procedure description and messages in 24.554 is missing and expected.
| V2X communication for ranging and sidelink positioning | The V2X PC5 link establishment and maintainance, which is common to all the stage 2 procedures for Ranging/Sidelink Positioning communication over PC5 | 24.514 | xiaomi | CT1#142 | C1-234209 | agreed | The general part and referring part in 24.514 is agreed.
| Message udpate for V2X direct link establishment procedure for ranging and sidelink positioning |  | 24.587 | xiaomi | CT1#142 | C1-234007 | agreed | Messge in 24.587 for establishment is agreed.Update for procedure description and messages other than that for establishment is missing and expected.
| V2X PC5 link establishment and maintainance procedures for ranging and sidelink positioning (direct link modification, direct link identifier update, direct direct link keep-alive, direct direct link release) |  | 24.587 |  |  |  | expected
Ranging and sidelink positioning procedure on LCS aspect | Pseudo-CR on general description for ranging and sidelink positioning communication on LCS aspect | 23.586 Clause 5.5&6.5 | 24.514 | vivo/xiaomi | CT1#143 | C1-236348 | agreed
| Mobile Originated Location Request for Ranging_SL |  | 24.571 |  |  |  | expected | C1-236098 postponed from CT1#143
| Mobile Terminated Location Request for Ranging_SL |  | 24.571 |  |  |  | expected | C1-236099 postponed from CT1#143 because of the following EN in clause 6.20.3 of 23.273 Editor's note: Whether supplementary services message or lpp will be sent from LMF to UE is FFS and needs the coordination with RAN WGs.
E | Security for ranging and sidelink positioning
General Description | General for Security for ranging and sidelink positioning |  | 24.514 |  |  |  | expected
Security for ranging and sidelink positioning UE discovery | Security for ranging and sidelink positioning UE discovery with 5G ProSe capable UE |  | 24.514 |  |  |  | expected
| Security for ranging and sidelink positioning UE discovery with V2X capable UE |  | 24.514 |  |  |  | expected
Security for ranging and sidelink positioning communication | Security for unicast direct communication over RSPP between the Ues over PC8* |  | 24.514 |  |  |  | expected
| Security for broadcast/groupcast communication over RSPP over PC8* |  | 24.514 |  |  |  | expected
| Security for ranging and sidelink positioning communication with V2X capable UE |  | 24.514 |  |  |  | expected

## CT3 Topics
Topic number | Description | Stage-2 reference | TS | Contributor | Meeting# | tdoc# | status | Notes
A | PCF services/procedures
| Add RSLPP in call flows of Policy Control | 23.586 clause 5.1&6.2 &S2-2305280 | 29.513 | Xiaomi | CT3#128 | C3-233730 | agreed
| Update UE Policy Control Service for Ranging_SL |  | 29.525 |  |  |  | expected
B | NEF services
| Add ParmForRangingSl | 23.586 clause 5.1&6.2 &S2-2305280 | 29.522 | Xiaomi | CT3#128 | C3-233755 | agreed
| Location exposure for Ranging_SL | 23.586 clause 5.6&6.7.2 &S2-2305280 | 29.122 | Xiaomi | CT3#128 | C3-233733 | agreed
| Location exposure for Ranging_SL |  | 29.522 | Xiaomi | CT3#128 | CP-232177 | agreed
| Update Location exposure for Ranging_SL |  | 29.122 |  |  |  | expected
| Service for mapping between application layer ID and GPSI | S2-2309831 | 29.522 |  |  |  | expected
C | UDR services for policy data
| Add ParmForRangingSl | 23.586 clause 5.1&6.2 &S2-2305280 | 29.519 | Xiaomi | CT3#128 | C3-233731 | agreed
18.44 | CT aspects of Ranging based services and sidelink positioning [Ranging_SL] | [5 empty] | CP-230331 (CT1 leading)

## CT4 Topics
Topic number | Description | Stage-2 reference | TS | Contributor | Meeting# | tdoc# | status | Notes
A | Common
| Add Ranging Sidelink Positioning Subscription data | S2-2304508 | 29.571 | Huawei | CT4#116 | C4-232610 | agreed | With EN for assistant UE
| Update common data for Ranging Sidelink Positioning | 23.586 | 29.571 | Xiaomi | CT4#117 | C4-233881 | agreed
B | UDM services
| Add Ranging Sidelink Positioning Subscription data | S2-2304508 | 29.503 | Huawei | CT4#116 | C4-232609 | agreed | With EN for QoS parameters
| Resolve Editor’s Note | 23.586 clause 5.7.2 | 29.503 | Huawei | CT4#117 | C4-233859 | agreed | PC5 QoS parameters related to RSPP transport over PC5
| Update to support SLPKMF |  | 29.503 |  |  |  | expected
C | Subscription data
| Add Ranging Sidelink Positioning Subscription data | S2-2304508 | 29.504 | Huawei | CT4#116 | C4-232274 | agreed
| Add Ranging Sidelink Positioning Subscription data | S2-2304508 | 29.505 | Huawei | CT4#116 | C4-232510 | agreed
D | NRF services
| PCF selection considering the Ranging/SL Positioning Capability | 23.586 clause 5.1&6.2 | 29.510 | Xiaomi | CT4#117 | C4-233860 | agreed
| LMF selection considering ranging_SL support | S2-2305278 | 29.510 | Xiaomi | CT4#117 | C4-233723 | agreed
| Update to support SLPKMF |  | 29.510 |  |  |  | expected
E | GMLC services
| Update on gmlc service for ranging_sl |  | 29.515 |  |  |  | expected
F | LMF services
| Update on LMF service for MT procedures for ranging_SL | 23.586 Clause 5.5&6.5 | 29.572 | Xiaomi | CT4#117 | CP-232178 | agreed
| Update on LMF service for ranging_SL |  | 29.572 |  |  |  | expected
G | AMF services
| Update on AMF service for MT procedures for ranging_SL | 23.586 Clause 5.5&6.5 | 29.518 | Xiaomi | CT4#117 | C4-233861 | agreed | Including: - Namf_Location_ProvidePositioningInfo (SL-MT) - Namf_Communication_N1N2MessageTransfer((Periodic-Triggered)SL-MT-LR, Event Report Ack) - Namf_Communication_N1MessageNotify((Periodic-Triggered)SL-MT-LR response, Event Report)
| update on amf services for ranging_sl |  | 29.518 |  |  |  | expected
| PC5 QoS parameters related to RSPP transport over PC5 | 23.586 clause 6.3.7 | 29.518 | Huawei | CT4#117 | C4-233866 | agreed
G | SLPKMF services
| General parts to support SLPKMF services | [5 empty] | expected
| Definition of SLPKMF services | [5 empty] | expected
6.2.20 CT aspects of Ranging based services and sidelink positioning [Ranging_SL]

## others
Incoming liaision statements (LS)
Tdoc # | Topic | Reply LS | Related tdocs: CT1 meeting #; tdoc(s) # | Open issues | Comments
Outgoing liaision statements (LS)
Tdoc # | Topic | Reply LS | Related tdocs: CT1 meeting #; tdoc(s) # | Open issues | Comments
C1-236527 | LS on procedures for UE discovery for Ranging_SL |  | CT1#143 |  | Send to SA2 Clarification on how to applying the "discovery type" to support UE discovery for ranging_SL
expected | Clarification on key and security materials used for ranging and sidelink positining service. |  | 33.503 approved in SA#101 in September, 2023. |  | S2-2309831 agreed in SA2#158 for Updating UDR, NEF, GMLC functionality in order to execute UE ID translation, however how and which service is used to implement the related functionality is not defined.
General
Latest WID: | CP-230331
Completion Status: | CT#99:0%

## Annex A
CRs agreed in SA2 for TS other than 23.586
No | TDoc | Meting# | Title | Source | Spec | Version | Summary | Stage3 Impact
| S2-2309281 | SA2#158 | Remove Editor s Note on feasiblity of the Relative Velocity with Uncertainty shape | Qualcomm Incorporated | 23.032 | 18.0.0 | Remove the editor s note on the Relative Velocity with Uncertainty shape in clause 8.4a.
| S2-2309832 | SA2#158 | Cleanup about the usage of GPSI | OPPO | 23.273 | 18.2.0 | Update clause 6.20.3 to support the GPSI only scenario. | (H)GMLC queries the NEF for the mapping Application Layer ID from the only GPSI.
| S2-2307514 | SA2#157 | Support of MT-LR for Ranging and Sidelink Positioning | Qualcomm Incorporated, Huawei, HiSilicon, Xiaomi | 23.273 | 18.1.0 | Add MT Ranging/Sidelink Positioning procedures | 1) LCS service request/response to/from the 5GC for Ranging/Sidelink Positioning location results for the n UEs from AF/Client UE - CT1(24.571/ 24.501)/ CT4(29.572/24.080/29.518) 2) UE descovery -CT1 (24.514/ 24.571) 3) Ranging and sidelink positioning communication over PC5/ CT1(24.514)
| S2-2307552 | SA2#157 | Ranging and Sidelink Positioning MO-LR procedure | Qualcomm Incorporated, Xiaomi, Sony, vivo, Interdigital, Huawei, HiSilicon, Philips International B.V. | 23.273 | 18.1.0 | Add MO Ranging/Sidelink Positioning procedures | 1)Provisioning of configuration information for Ranging/SL positioning service -CT1 (24.514/ 24.587/ 24.526) -CT3 ((29.522/29.525/29.519)) 2) UE discovery -CT1 (24.514/ 24.571) 3) Ranging and sidelink positioning procedure - over PC5/ CT1(24.514) - between UE/AMF/LMF CT1(24.571/ 24.501)/ CT4(29.572/24.080/29.518)
| S2-2304508 | SA2#156e | Ranging Sidelink Positioning Subscription data | Huawei, HiSilicon | 23.502 | 18.1.1 | Add Ranging Sidelink Positioning Subscription data stored in UDR | CT4 (29.503/29.504/29.505)
| S2-2305278 | SA2#156e | Updates to LMF selection to support Ranging/Sidelink Positioning | Xiaomi | 23.273 | 18.1.0 | LMF selection considering ranging_SL support | CT4 29.510
| S2-2305280 | SA2#156e | Updates to support Ranging/Sidelink Positioning | Xiaomi | 23.503 | 18.1.0 | Provisioning of configuration information for Ranging/SL positioning service | CT3 (29.122/29.522/29.525/29.519)
| S2-2305340 | SA2#156e | TS23.501 Support of SL Positioning | Intel | 23.501 | 18.1.0 | General feature support | NA
| S2-2305748 | SA2#156e | Support of MT-LR for Ranging and Sidelink Positioning | Qualcomm Incorporated | 23.273 | 18.1.0 | SL_MT_LR procedure | 1) LCS service request/response to/from the 5GC for Ranging/Sidelink Positioning location results for the n UEs from AF/Client UE -CT4 ((29.515/29.518/29.572)) 2) UE descovery -CT1 (24.514/ 24.571) 3) Ranging and sidelink positioning communication - over PC5/ CT1(24.514) - between UE and LMF. CT1(24.571/ 24.501)/ CT4(29.572)
| S2-2305749 | SA2#156e | Ranging and Sidelink Positioning MO-LR procedure | Qualcomm Incorporated | 23.273 | 18.1.0 | SL_MO_LR procedure | 1)Provisioning of configuration information for Ranging/SL positioning service -CT1 (24.514/ 24.587/ 24.526) -CT3((29.522/29.525/29.519)) 2) UE discovery -CT1 (24.514/ 24.571) 3) Ranging and sidelink positioning communication - over PC5/ CT1(24.514) - between UE and LMF. CT1(24.571/ 24.501)/ CT4(29.572)
| S2-2305751 | SA2#156e | New GAD Shapes for Ranging and Sidelink Positioning Location Results | Qualcomm Incorporated | 23.032 | 17.2.0 | New GAD Shapes definition for ranging_SL | NA
| S2-2303193 | SA2#155 | Support of Ranging and Sidelink Positioning | Qualcomm Incorporated | 23.273 | 18.0.0 | General feature support | NA
| S2-2303258 | SA2#155 | Introduce Sidelink positioning procedure into LCS architecture | Ericsson | 23.273 | 18.0.0 | Architecture update | NA
TS 23.586 with responsible group of SA2
No | Stage 2 Clause# | Stage 3 Impact
|  | Responsible group | Impacted Spec | Status | Impacted items |  |  | Notes
A | Provisioning of configuration information for Ranging/SL positioning service
| Clause 5.1&6.2 | CT1 | 24.501/24.514, 24.587/24.526 | done | UE capability and UE policy
|  | CT3 | 29.122/29.522/29.525/29.519 | done | 1) updates to the NEF northbound interface (i.e. Nnef_ServiceParameter API) to support the provisioning of Ranging/SideLink Positioning service parameters by an AF; 2) updates to the UDR to support the provisioning and storage of Ranging/SideLink Positioning service parameters 3) updates to the PCF to support service authorisation policy and parameters provisioning in Ranging based services and sidelink positioning;
|  | CT4 | 29.510 | done | PCF selection
B | Ranging/Sidelink Positioning UE discovery
| Clause 5.2&6.4.2.1 | CT1 | 24.514/24.554 | partially done | General procedure for 1) Ranging/SL Positioning UE discovery in Model A with 5G ProSe capable UEs 2) Ranging/SL Positioning UE discovery in Model B with 5G ProSe capable Ues |  |  | Tdoc agreed with EN to be solved depending on RAN2 and SA3 aspects
|  | CT1 | 24.514/24.554/24.571 | expected when SA2 is clear | 3) UE-LMF interaction for Located UE Discovery 4) UE-LMF interaction for SL Positioning Server UE
| Clause 5.2&6.4.2.2 | CT1 | 24.514/24.554 | partially done | Ranging/SL Positioning Group member discovery 1) Model A with 5G ProSe capable UEs 2) Model B with 5G ProSe capable Ues |  |  | Tdoc agreed with EN to be solved depending on RAN2 and SA3 aspects
| Clause 5.2&6.4.3 | CT1 | 24.514/24.587 | done | Ranging/SL Positioning UE discoverywith V2X capable UE
C | Ranging/Sidelink Positioning communication
| Clause 5.5&6.5 | CT1 | 24.514/24.501/24.571 | expected | Network/UE based SL Positioning for UE with/without NAS connection using MO/MT location procedure - between UE and LMF. CT1(24.571/ 24.501) |  |  | Include the following parts: - UE discovery (refer to UE discovery part) - the PC5 link establishment and maintainance - SL positioning information request/response between target UE and Located UE in stage 2 is transported over PC5-U - QoS flow management/data transmission/security/authentication
|  | CT4 | 29.515/29.572 | done | Network/UE based SL Positioning for UE with/without NAS connection using MO/MT location procedure - GMLC - LMF
| S2-2309831 | CT3 | 29.522 | expected | Application Layer ID translation to GPSI during the MO/MT or exposure procedure
| Clause 5.11&6.6 | CT1 | 24.514 | expected | refer to Clause 5.5&6.5 for the interaction over PC5 and between UE-LMF
| Clause 6.7.1.1 | CT1 | 24.514 | expected | the interaction over PC5
| Clause 6.7.1.2 | CT3 | 29.522 | done | Updates to the NEF northbound interface (i.e. Nnef_EventExposure API reusing the eLCS feature) to support the exposing of Ranging based services and sidelink positioning services to an AF.
| Clause 6.7.1.2 | CT1 | 24.514/24.501/24.571 | expected | In addtion to clause 5.5&6.5 interaction between SL Positioning Client UE and the AMF is needed
| Clause 6.8 | CT1 | 24.514 | expected
TS 33.503 with responsible group of SA3
No | Stage 2 Clause# | Stage 3 Impact
|  | Responsible group | Impacted Spec | Status | Impacted items |  |  | Notes
A | Security for Ranging/SL positioning UE discovery | [6 empty] | CT1: key&security materials used over PC5 - 24.514 key&security materials used for PC5 UE discovery procedures. - 24.554/24.587 key&security materials used for PC5 communication procedures. CT4: Support SLPKMF - 29.503 interact with UDM - 29.510 support SLPKMF - new TS or 29.559 support SLPKMF services
| clause 6.2 | CT1 | 24.514 | expected | key&security materials used for PC5 UE discovery procedures.
|  | CT4 | 29.503/29.510/29.559 or new TS | expected | SLPKMF services
B | Authorization for Ranging/SL positioning service
| clause 6.3 | refer to clause 6.2&6.4
C | Security for communication of Ranging/SL positioning control
| clause 6.4 | CT1 | 24.514 | expected | key&security materials used for PC5 communication procedures.
|  | CT4 | 29.503/29.510/29.559 or new TS | expected | SLPKMF services
Note on D2: Free text. Maximum length: 200 characters
Note on E2: Free text. Maximum length: 200 characters