## General
Latest update: 06/Nov/2023
| Source | Samsung
| Title | Work Plan: CT Aspect of Architecture Enhancements for Vehicle Mounted Relays (VMR) | : CT aspect of Seamless UE context recovery (SUECR)
Agenda Item:
Document for: Discussion
Latest WID: CP-223262
Completion Status: CT#98: CT1-75% CT#99: CT1->90%, CT3->75%, CT4->75% CT#100: CT1->95%, CT3->90%, CT4->90% CT#101: CT1->95%, CT3->90%, CT4->90%

## CT1 topic
Latest update: 06/April/2023
CT1 Topic
Topic number | Description | Stage-2 reference | TS | Contributor | Meeting# tdoc# | status | Notes
A | General
| General section for unavailability period |  | 24.501 | Qualcomm Incorporated,Samsung | C1-227130 | Agreed | Samsung CR C1-226697 is merged to C1-227130
B | NAS procedure update to Negotiate support of "Unavailability Period"
| Update Registration procedure to indicate support of "Unavailability Period" |  | 24.501 | Qualcomm Incorporated, Samsung | C1-227130 | Agreed
C | NAS procedure update to indicate "Unavailability Period duration" to AMF
| Update Registration procedure to indicate "Unavailability Period" duration |  | 24.501 | Qualcomm Incorporated,Samsung | C1-227130 | Agreed
| Update De-registration procedure to indicate "Unavailability Period" duration |  | 24.501 | Qualcomm Incorporated,Samsung | C1-227130 | Agreed
D | AT Command
| AT command support to configure unavailability support duration |  | 27.007 | InterDigital, Apple | C1-231147 | Agreed

## CT1 Contributions
Latest update: 10/August//2023
CT1 Contributions including LS
Meeting | Title | Source | Tdoc number | Type | Status | Notes
CT1#139 | Support for Unavailability Period | Qualcomm Incorporated, Samsung | C1-226517 revised to C1-227035 revised to C1-227130 | CR | Agreed | Tdoc C1-227130 is agreed
CT1#139 | Introduction to SUECR | Samsung | C1-226697 | CR | Merged | Merged with C1-227130
CT1#140 | AT Command to configure the Unavailability Period Duration | Apple | C1-230315 | CR | Merged | Merged with C1-231147
CT1#140 | Clarification on determination of T3512 value based on unavailability period duration | ZTE | C1-230443 | CR | Agreed
CT1#140 | LS on Unavailability period support in non-3GPP | Samsung | C1-230548 | LS Out | Postponed | Qualcomm, Nokia is in opinon that the feature is applicable to 3GPP access only thus no LS is required
CT1#140 | Abnormal case handling for registration procedure due to Unavailability period duaration | Samsung | C1-230559 | CR | Agreed
CT1#140 | UE initiated de-registration procedure for Unavailability Period |  | C1-230949 | CR
CT1#140 | Handling UE NAS timers in duration of unavailability period | MediaTek Inc. / Marko | C1-230378 is revised to C1-230950 | CR |  | Tdoc C1-230950 is agreed
CT1#140 | AT Command for Unavailability Period | InterDigital, Apple | C1-230157 is revised to C1-230948 is revised to C1-231147 | CR | Agreed | Tdoc C1-231147 is agreed
CT1#141 | Periodic PLMN searches when unavailability period is activated | MediaTek Inc. / Marko | C1-232655 | CR | Agreed
CT1#142 | Adding inclusion criteria for newly added IE | Apple | C1-233974 | CR | Agreed
CT1#142 | Unavailability period duration IE as a non-cleartext IE | Samsung | C1-233975 | CR | Agreed
CT1#142 | The AMF behaviour on the unavailability period duration | vivo | C1-233977 | CR | Agreed
CT1#142 | AT command correction for unavailability period | Samsung | C1-233980 | CR | Agreed
CT1#142 | 5GMM state for unavailability period | MediaTek Inc., Huawei, HiSilicon | C1-233981 | CR | Agreed
CT1#142 | Coming out of unavailability period when deregistered | MediaTek Inc., Huawei, HiSilicon | C1-233982 | CR | Agreed
CT1#142 | Unavailability period duration for MUSIM UE | InterDigital | C1-234346 | CR | Agreed
CT1#144 | Encoding of unavailability information and related corrections | Qualcomm Incorporated, Ericsson, Nokia, Nokia Shanghai Bell / Amer | C1-237731 | CR | Agreed | Applicable for 5GSAT_ph2 and SUECR
CT1#144 | Cell Selection/reselection during unavailability period | MediaTek Inc., Samsung | C1-237750 | CR | Agreed | Applicable for 5GSAT_ph2 and SUECR
CT1#144 | Encoding of unavailability information | Qualcomm Incorporated, Ericsson, Nokia, Nokia Shanghai Bell | C1-237905 | CR | Agreed | Applicable for 5GSAT_ph2 and SUECR

## CT3 Topic
Latest update: 06/April/2023
CT3 Topic
Topic number | Description | Stage-2 reference | TS | Contributor | Meeting# tdoc# | status | Notes
A | Support of Unavailability Period Duration information
| Loss of connectivity in 5GS in Monitoring Event API |  | 29.122 | KDDI, Samsung, Huawei | C3-230638 | Agreed
| Unavailability Period Duration in the Monitoring Event API |  | 29.522 | KDDI, Samsung, Huawei | C3-230639 | Agreed
| Clarification on Loss_of_connectivity_notification_5G |  | 29.122 | Huawei | C3-231422 | Agreed

## CT4 Topic
Latest update: 06/April/2023
CT4 Topic
Topic number | Description | Stage-2 reference | TS | Contributor | Meeting# tdoc# | status | Notes
A | Unavailability Period Duration for "LOSS_OF_CONNECTIVITY” monitoring event.
| Providing Unavailability duration with LOSS_OF_CONNECTIVITY event |  | 29.518 | Samsung | C4-230644 | Agreed

## LSes
Incoming liaision statements (LS)
Tdoc # | Topic | Reply LS | Related tdocs: CT1 meeting #; tdoc(s) # | Open issues | Comments
Outgoing liaision statements (LS)
Tdoc # | Topic | Reply LS | Related tdocs: CT1 meeting #; tdoc(s) # | Open issues | Comments
C1-233275 | LS on the Applicability of the Unavailability Period for Dual Registered UEs |  |  |  | The LS is sent to SA2 to know the imapct of unavailability period on EPC in dual registration
C1-233533 | LS on Unavailability period support in non-3GPP |  |  |  | The LS is sent to SA2 to know the unavailability period feature is applicable on non-3GPP access
C1-234364 | LS on the Applicability of the Unavailability Period during Network congestion |  |  |  | The LS is sent to SA2 to know the SA2 opinion that deregistration can be initiated in congestion if the de-registration is for the unavailability period
Incoming liaision statements (LS)
Tdoc # | Topic | Reply LS | Related tdocs: CT1 meeting #; tdoc(s) # | Open issues | Comments
S2-2311697 | de-registration during congestion timer | Reply LS on the Applicability of the Unavailability Period during Network congestion | C1-237138 |  | The reply LS is received from SA2 for the LS C1-234364 and there was no consensus to enable UE to send de-registration message to report unavailability when congestion timer is running.
C1-238516 | Support of unavilability on non-3GPP Access | Reply LS on Unavailability period support in non-3GPP | C1-233533 |  | The SA2 clarifies that SUECR is applicable for the 3GPP access only and the Related CR C1-239216 is agreed in CT#145 to align with the stage-2 requirements.
C1-238518 | Reply LS on the Applicability of the Unavailability Period for Dual Registered UEs | Reply LS on the Applicability of the Unavailability Period for Dual Registered UEs | C1-233275 |  | Stage 2 clarifies that SUECR feature is applicable for the 5GS only. This LS to be noted.