**3GPP TSG-CT Meeting #103CP-240abc**

**Maastricht, Netherlands; 18th – 19th March 2024**

**Source: CATT**

**Title: Rel-18 Work Item Exception for 5G\_eLCS\_Ph3**

**Document for: Approval**

**Agenda Item: 18.1**

3GPP™ Work Item Exception

# Title : CT aspects of enhancement to the 5GC location services - phase 3

## Acronym : 5G\_eLCS\_Ph3

## Unique Identifier : 980003

**Release 18 Submission form**

|  |  |
| --- | --- |
| **Feature / Item:** | **5G\_eLCS\_Ph3** |
| **Affects:** | **UICC apps:** | **ME:**X | **AN:** | **CN:**X | **Others (specify):** |
| **Expected Completion Date:** | CT#104 (Jun 2024) |
| **Service(s) impacted:** | 5GC location services |
| **Specification(s) affected:** | TS 24.572 |
| **Task(s) within work which are not complete:** | 1. Resolution of the LCS user plane connection(waiting for SA2 to provide the solutions):a) how to link the association between the TLS connection and the UE;b) how the LMF associates the LCS service request to the TLS connection of the UE.2. Remaining Editor’s notes. |
| **Consequences if not included in Release 18:** | The CT1 stage-3 aspects for 5GC location services are not specified completely in the Rel-18 version of 3GPP specification, which does not specify how to link the association between the TLS connection and the UE. |

**Abstract of document:**

This work item exception requests to extend the deadline of the CT1 5GC location services work till June 2024.

**Contentious Issues:**

None.