## Tdoc cover sheet
3GPP TSG CT WG1 Meeting #152 Orlando, US, 18th – 22nd November 2024 |  | C1-247163
Source: | CATT
Title: | Work plan for the CT1 part of 5G_ProSe_Ph3-CT
Agenda item: | 19.36
Document for: | Information

## Contributions plan
Contribution Plan
Spec | Topic | Related LS or other WG tdoc(s) # | CT1 meeting # | tdoc(s) # | Comments | Open issues
24.554
| Adding a reference to the type 6 container |  | CT1#151 | C1-245252
| Introducing the overview of the 5G ProSe multi-hop procedures and the skeleton of the new clauses |  | CT1#151 | C1-245480
| Adding description about policies for 5G ProSe multi-hop Relays |  | CT1#151 | C1-245894
| Adding the Multi-hop path info information element |  | CT1#151 | C1-245898
| Adding an informative annex for the spec rapporteurs |  | CT1#151 | C1-245899
| Multi-hop UE-to-network relay discovery over PC5 interface with model A |  | CT1#151 | C1-245927 |  | Multi-hop UE-to-network relay selection and reselection procedure are FFS. Impacts to the message definition of PROSE PC5 DISCOVERY message for multi-hop UE-to-network relay discovery announcement based on security related agreements in stage-2 are FFS..
| 5G ProSe multi-hop UE-to-network relay additional parameters |  | CT1#151 | C1-245928 |  | Impacts to the message definition of PROSE PC5 DISCOVERY message for multi-hop UE-to-network relay discovery additional information based on security related agreements in stage-2 are FFS..
| Definition on 5G ProSe intermediate parent and child UE-to-network relay |  | CT1#151 | C1-245935
| Introducing the terms, definitions and scope for 5G ProSe multi-hop communications |  | CT1#151 | C1-245944
| Updating the UE-requested ProSeP policy provisioning procedure for multi-hop communications |  | CT1#151 | C1-245945
| Authorization and provisioning for 5G ProSe multi-hop relays |  | CT1#151 | C1-245953
24.555
| The skeleton and overview for 5G ProSe multi-hop relays |  | CT1#151 | C1-245890
| Terms for 5G ProSe multi-hop and single-hop communications |  | CT1#151 | C1-245891
24.501
| Enhancement of 5G ProSe capability for multi-hop relays | C1-245799, LS on the supporting 5G ProSe multi-hop Relays | CT1#151 | C1-245912 |  | It is FFS how to enhance the 5G ProSe capability for multi-hop relays.
24.587
| Updating the Requested UE policies information element for multi-hop communications | C1-245799, LS on the supporting 5G ProSe multi-hop Relays | CT1#151 | C1-245946 |  | Whether the whole 5 new bits added for UE policies for 5G ProSe multi-hop are all needed or they can be reduced, is FFS

## Expected contributions
Expected Contributions for future meetings
Spec | Topic | Related LS or other WG tdoc(s) # or TS # | Volunteered company/delegate | Contribution(s) | Comments/Open issues
24.554
SA2 TS 23.304
| Procedures to support ProSe U2N multihop relay discovery Model B | S2-2409537 CR 0451 (Huawei, HiSilicon, Samsung, Interdigital, CATT, KPN N.V. Nokia, Nokia Shanghai Bell, China Telecom, OPPO) S2-2409537 CR 0451 (Huawei, HiSilicon, Samsung, Interdigital, CATT, KPN N.V. Nokia, Nokia Shanghai Bell, China Telecom, OPPO)
| Procedures to support 5G ProSe Multi-hop UE-to-UE Relay for IP PDU type model A | S2-2409556 CR 0460(Qualcomm Incorporated, AT&T, Ericsson, FirstNet, Intel)
| Procedures to support 5G ProSe Multi-hop UE-to-UE Relay for IP PDU type model B | S2-2409556 CR 0460(Qualcomm Incorporated, AT&T, Ericsson, FirstNet, Intel)
| Procedures to support 5G ProSe U2U Multihop Relay for non-IP PDU model A | S2-2409398 CR 0450 (Huawei, HiSilicon, China Telecom, Samsung, Interdigital, CATT, KPN N.V, OPPO)
| Procedures to support 5G ProSe U2U Multihop Relay for non-IP PDU Model B | S2-2409398 CR 0450 (Huawei, HiSilicon, China Telecom, Samsung, Interdigital, CATT, KPN N.V, OPPO)
Define Hop count, hop limit and Accumulated QoS in clause 11
24.555
| Coding for 5G ProSe multi-hop U2N relay UE | S2-2409085 CR 0444 (CATT, China Telecom, OPPO)
| Coding for 5G ProSe intermediate U2N relay UE | S2-2409085 CR 0444 (CATT, China Telecom, OPPO)
| Coding for 5G ProSe multi-hop U2N remote UE | S2-2409085 CR 0444 (CATT, China Telecom, OPPO)
| Coding for 5G ProSe multi-hop U2U relay UE | S2-2409085 CR 0444 (CATT, China Telecom, OPPO)
| Coding for 5G ProSe multi-hop U2U end UE | S2-2409085 CR 0444 (CATT, China Telecom, OPPO)
24.501

## Incoming LSs
Incoming liaision statements (LS)
Tdoc # | Topic | Reply LS | Related tdocs: CT1 meeting #; tdoc(s) # | Open issues | Comments