## Tdoc cover sheet
3GPP TSG-CT WG3 Meeting #115e eMeeting, 14-23 April 2021 |  | C3-212263
Source: | Samsung Electronics
Title: | Work plan for CT3 aspects of EDGEAPP
Agenda item: | 17.9
Document for: | Information

## Contributions plan
Contribution Plan
Spec | Topic | Related LS or other WG tdoc(s) # | CT3 meeting #; tdoc(s) # | Comments | Open issues
29.558 | Enabling Edge Applications (Rel-17)
| TS - Skeleton |  | CT3#113e (C3-210300)
| Scope |  | CT3#113e (C3-210301)
| References |  | Updated from multiple contributions
| Definition of Terms and Abbreviation |  | CT3#113e (C3-210182), CT3#114e (C3-211365) CT3#115e (C3-212264)
| Overview |  | CT3#113e (C3-210301)
| EDGEAPP design aspects common for all APIs |  | CT3#114e (C3-211503)
| Introduction of EDGEAPP services |  | CT3#114e (C3-2113504, C3-211506) | Clause 6.7.2 of TS 23.558 referred for new/update to list of APIs
EES Services
Registration
| EAS Registration API (Eees_EASRegistration) |  |  |  | Pending Editor Notes, PATCH Method for partial update
| Service Description |  | CT3#114e (C3-211504)
| API Definition |  | CT3#114e(C3-211505), CT3#115e (C3-212265)
Open API Specification
Capability Exposure APIs to EAS
UE Location APIs (Eees_UELocation)
| Service Description |  | CT3#115e (C3-212266)
| API Definition |  | CT3#115e (C3-212267)
Open API Specification
| ACR Management Events API (Eees_ACRManagementEvent) |  |  | "User plane path change", "ACR monitoring", "ACR facilitation"
Service Description
API Definition
Open API Specification
Application Client Information Exposure APIs (Eees_AppClientInformation)
Service Description
API Definition
Open API Specification
UE Identifier API (Eees_UEIdentifier)
| Service Description |  | CT3#115e (C3-212268)
| API Definition |  | CT3#115e (C3-212269)
Open API Specification
Session with QoS API (Eees_SessionWithQoS)
Service Description
API Definition
Open API Specification
Service Continuity APIs
Target EAS Discovery API (Eees_TargetEASDiscovery)
Service Description
API Definition
Open API Specification
Automated ACR API (Eees_AutomatedACR)
Service Description
API Definition
Open API Specification
ECS Services
Registration
| EES Registration API (Eecs_EESRegistration) |  |  |  | Pending Editor Notes, PATCH Method for partial update
| Service Description |  | CT3#114e (C3-211506)
| API Definition |  | CT3#114e (C3-211507), CT3#115e (C3-212265)
Open API Specification
Service Continuity APIs
Target EES Discovery (Eecs_TargetEESDiscovery)
Service Description
API Definition
Open API Specification
Network capability exposure to EAS
Using Common API Framework
Utlizing 3GPP core network capabilities
| Security |  |  |  | TBD, aligning to SA3 conclusions
Dynamic EAS instantiation triggering
Annex Updates
TS cleanup - Editorials
| TS (for Info) |  | CT#92e | v0.1.0 - CT3#113e (C3-210322) - 5% v0.2.0 - CT3#114e (C3-211508) - 20%
| TS (For approval) |  | CT#93e
29.222 | Common API Framework for 3GPP Northbound APIs (Rel-17) |  | Samsung

## Incoming LSs
Incoming liaision statements (LS)
Tdoc # | Topic | Reply LS | Related tdocs: CT3 meeting #; tdoc(s) # | Open issues | Comments
C3-205086 | LS on APIs in EDGEAPP | C3-205335 |  |  | SA6 informing decision of APIs for EDGE-1/4 interfaces and unification of APIs.
C3-212047 | Reply LS on clarification regarding EEC ID |  |  |  | SA6 clarified SA3 on EEC ID.

## Outgoing LSs
Outgoing liaision statements (LS)
Tdoc # | Topic | Related tdocs: CT3 meeting #; tdoc(s) # | Open issues | Comments
C3-205335 | Reply to LS on APIs in EDGEAPP |  | Work split coordination with CT1 Unification of APIs response from SA6 | CT3 would like to understand exactly which APIs could be modelled as unified service and which service consumers are served by such APIs? Based on this information, CT3 would be able to provide concrete feedback on the design choice.