## CT3
5MBS WI (C3-220371) - CT3 Work Plan - 02/2022
Impact Description |  | Specification | Contributor company | Agreed Tdoc Numbers | Targeted CT3 meeting | Status
Impacts to the PCC framework
New Npcf_MBSPolicyControl service/API exposed by the PCF to support 5G MBS Policy Association management and MBS QoS control procedures. | TS Skeleton and general clauses (e.g. Scope, Overview, Definitions, etc.) | 29.537 (new) | Huawei, Nokia | C3-220113, C3-220114, C3-220401, C3-220402, C3-220403 | CT3#119-bis-e | Done
| Service and service operations description clauses | 29.537 (new) | Nokia, Huawei | C3-220491 | CT3#119-bis-e | Ongoing
| API general clauses (i.e. Introduction, Usage of HTTP, Error Handling, Feature negotiation, Security) | 29.537 (new) | Huawei, Nokia | C3-220115 | CT3#119-bis-e | Ongoing
| API resources and custom operations clauses | 29.537 (new) | Huawei, Nokia | C3-220116 | CT3#119-bis-e | Ongoing
| API notifications clauses | 29.537 (new) | Nokia, Huawei | C3-220492 | CT3#119-bis-e | Ongoing
| API data model clauses | 29.537 (new) | Huawei, Nokia | C3-220404 | CT3#119-bis-e | Ongoing
| OpenAPI description | 29.537 (new) | Nokia, Huawei | C3-220493 | CT3#119-bis-e | Ongoing
| General clean-up and resolving ENs | 29.537 (new) | Huawei, Nokia |  | CT3#120-e/CT3#121-e | Planned
Potential new Npcf_MBSPolicyAuthorization service exposed by the PCF to support 5G MBS Policy Authorization procedures. | To be evaluated based on the progress of Stage 2. | 29.537 (new) | Huawei |  | CT3#120-e/CT3#121-e | Pending
Potential enhancements to the BSF services to support 5G MB session binding. | To be evaluated based on the progress of Stage 2. | 29.521 | Huawei |  | CT3#120-e/CT3#121-e | Pending
Impacts to the UDR services for QoS information storage and retrieval (e.g. by the PCF) to support 5G MB Session configuration and management procedures. | Definition of preconfigured 5MBS policy information (e.g. applicable QoS, the MBS Session-AMBR and/or default 5QI) To be evaluated based on the progress of Stage 2. | 29.519 | Nokia??, Ericsson?? |  | CT3#120-e/CT3#121-e | Pending
| Impacts on the existing service operations or definition of new ones to support the storage and retrievel (e.g. by the PCF) of 5MBS policy information. To be evaluated based on the progress of Stage 2. | 29.519 | Nokia??, Ericsson?? |  | CT3#120-e/CT3#121-e | Pending
Potential impacts to TS 29.512 to support 5G MBS session and QoS management. | To be evaluated later based on the progress of Stage 2. | 29.512 | Ericsson?? |  | CT3#120-e/CT3#121-e | Pending
Impacts to PCC signalling procedures defined in TS 29.513 to support 5G MBS session and QoS management. | Update the PCC signalling procedures to support 5MBS policy control (e.g. definition of the procedures related to MBS policy control). To be done when the above items are stable enough both in Stage 2 and Stage 3. | 29.513 | Ericsson?? |  | CT3#120-e/CT3#121-e | To be done
Impacts to the 3GPP Northbound Interfaces
New Nnef_MBSTMGI service/API exposed by the NEF to support MBS TMGI allocation procedures. | Procedures description part | 29.522 | Huawei, Nokia, Ericsson | C3-215332, C3-220106 | CT3#118-e | Done
| API definition part (i.e. Introduction, Resources, Custom operations, Notifications, Data model, Used features) | 29.522 | Huawei, Nokia, Ericsson | C3-216345 | CT3#118-e/CT3#119-e | Done
| OpenAPI description | 29.522 | Huawei, Nokia, Ericsson | C3-216346 | CT3#118-e/CT3#119-e | Done
| General clean-up and resolving ENs | 29.522 | Huawei, Nokia | C3-220034 | CT3#119-bis-e/CT3#120-e | Ongoing
New Nnef_MBSSession service/API exposed by the NEF to support MB session management procedures and operations towards 5GC (e.g. TMGI allocation, MBS session management, etc.). | Procedures description part | 29.522 | Nokia, Huawei | C3-216096, C3-220107 | CT3#119-e | Done
| API definition part (i.e. Introduction, Resources, Custom operations, Notifications, Data model, Used features) | 29.522 | Nokia, Huawei | C3-216097, C3-220108 | CT3#119-e | Done
| OpenAPI description | 29.522 | Nokia, Huawei | C3-216098 | CT3#119-e | Done
| General clean-up and resolving ENs | 29.522 | Huawei, Nokia | C3-220034, C3-220109 | CT3#119-bis-e/CT3#120-e | Ongoing
User Plane related impacts
N6mb between MB-UPF and AF/AS | Impacts to the N6 interface to support 5MBS data delivery. | 29.561 | Ericsson |  | CT3#120-e/CT3#121-e | To be done
N6mb between MB-UPF and MBSTF | Impacts to the N6 interface to support 5MBS data delivery. | 29.561 | ?? |  | CT3#120-e/CT3#121-e | To be done
MBSF & MBSTF
Definition of the new Nmbsf interface (Nmb5 and Nmb10 interfaces): Support TMGI allocation and MB session management procedures and operations towards 5GC (e.g. MBS session management, etc.). To be further evaluated later based on the progress of Stage 2. | TS Skeleton and general clauses (e.g. Scope, Overview, Definitions, etc.) | 29.cde (new) | Huawei |  | CT3#120-e | Planned
| Service and service operations description clauses | 29.cde (new) | Huawei, ?? |  | CT3#121-e/CT3#122-e | To be done
| API general clauses (i.e. Introduction, Usage of HTTP, Error Handling, Feature negotiation, Security) | 29.cde (new) | Huawei, ?? |  | CT3#121-e/CT3#122-e | To be done
| API resources and custom operations clauses | 29.cde (new) | Huawei, ?? |  | CT3#121-e/CT3#122-e | To be done
| API notifications clauses | 29.cde (new) | Huawei, ?? |  | CT3#121-e/CT3#122-e | To be done
| API data model clauses | 29.cde (new) | Huawei, ?? |  | CT3#121-e/CT3#122-e | To be done
| OpenAPI description | 29.cde (new) | Huawei, ?? |  | CT3#121-e/CT3#122-e | To be done
| General clean-up and resolving ENs | 29.cde (new) | Huawei, ?? |  | CT3#121-e/CT3#122-e | To be done
Definition of the Nmb8 interface between an AF/AS and an MBSTF. | To be evaluated later based on the progress of Stage 2. | Tbd | ?? |  | CT3#121-e/CT3#122-e | To be done