## Tdoc cover sheet
3GPP TSG-CT WG3 Meeting #123e eMeeting, 18th - 26th August 2022 |  | C3-224407 revision of C3-22xxxx
Source: | Samsung Electronics
Title: | Work plan for CT3 aspects of EDGEAPP
Agenda item: | 17.9
Document for: | Information

## Contributions plan
Contribution Plan
Spec | Topic | Related LS or other WG tdoc(s) # | CT3 meeting #; tdoc(s) # | Comments | Open issues/Outstanding work
29.558 | Enabling Edge Applications (Rel-17)
| TS - Skeleton |  | CT3#113e (C3-210300)
| Scope |  | CT3#113e (C3-210301)
| References |  | Updated from multiple contributions, CT3#119e (C3-216348)
| Definition of Terms and Abbreviation |  | CT3#113e (C3-210182), CT3#114e (C3-211365)
| Overview |  | CT3#113e (C3-210301)
| EDGEAPP design aspects common for all APIs |  | CT3#114e (C3-211503), CT3#119bis-e (C3-220276), CT3#121e (C3-222362), CT3#122e (C3-223195, C3-223337, C3-223677)
| Introduction of EDGEAPP services |  | CT3#114e (C3-2113504, C3-211506), CT3#121e (C3-222364) | Clause 6.7.2 of TS 23.558 referred for new/update to list of APIs
EES Services
Registration
EAS Registration API (Eees_EASRegistration)
| Service Description |  | CT3#114e (C3-211504), CT3#117e (C3-214388), CT3#119e (C3-216385), CT3#121e (C3-222362)
| API Definition |  | CT3#114e(C3-211505), CT3#117e (C3-214388), CT3#118e(C3-215236), CT3#119e (C3-216385), CT3#119bis-e (C3-220275), CT3#120e (C3-221726), CT3#121e (C3-222362, C3-222363), CT3#122e (C3-223327, C3-223676)
| Open API Specification |  | CT3#118e(C3-215236), CT3#119e (C3-216385), CT3#119bis-e (C3-220275), CT3#120e (C3-221726), CT3#122e (C3-223675)
Capability Exposure APIs to EAS
UE Location APIs (Eees_UELocation)
| Service Description |  | CT3#115e (C3-212367), CT3#117e (C3-214392), CT3#121e (C3-222362)
| API Definition |  | CT3#115e (C3-212368), CT3#117e (C3-214392), CT3#119Bis-e (C3-220133), CT3#119Bis-e (C3-220406) - TS 29.122, Accuracy data type extended supporting Civic Address, CT3#120e (C3-221046) - TS 29.522, Civic address for Accuracy in Monitoring event API. CT3#121e (C3-222362), CT3#122e (C3-223607, C3-223647)
| Open API Specification |  | CT3#119bis-e(C3-220420), CT3#122e (C3-223675)
| ACR Management Events API (Eees_ACRManagementEvent) |  |  | "User plane path change", "ACR monitoring", "ACR facilitation"
| Service Description |  | CT3#117e (C3-214513)
| API Definition |  | CT3#117e (C3-214513),CT3#120e (C3-221410), CT3#121e (C3-222139, C3-222141, C3-222362, C3-222410, C3-222411, C3-222449) , CT3#122e (C3-223321, C3-223323, C3-223606, C3-223649, C3-223650, C3-223691)
| Open API Specification |  | CT3#117e (C3-214513),CT3#120e (C3-221410), CT3#121e (C3-222139, C3-222141, C3-222410, C3-222411, C3-222449), CT3#122e (C3-223649, C3-223650, C3-223675, C3-223691)
Application Client Information Exposure APIs (Eees_AppClientInformation)
| Service Description |  | CT3#116e (C3-213325), CT3#121e (C3-222362)
| API Definition |  | CT3#116e (C3-213326), CT3#117e (C3-214570), CT3#118e(C3-215339), CT3#121e (C3-222362), CT3#122e (C3-223608)
| Open API Specification |  | CT3#119bis-e(C3-220419), CT3#122e (C3-223675)
| UE Identifier API (Eees_UEIdentifier) |  |  |  | > Editor’s Note: How the user’s consent is obtained to share the UE identifier with EAS is FFS and to be aligned with security aspects defined by SA3. Waiting for feedback from SA6 and SA3 on applicability of user consent management for this API.
| Service Description |  | CT3#115e (C3-212369)
| API Definition |  | CT3#115e (C3-212370), CT3#120e (C3-221687), CT3#121e (C3-222508), CT3#122e (C3-223781, C3-223792, C3-223793)
| Open API Specification |  | CT3#122e (C3-223794)
Session with QoS API (Eees_SessionWithQoS)
| Service Description |  | CT3#116e (C3-213324), CT3#121e (C3-222362)
| API Definition |  | CT3#116e(C3-213324), CT3#117e(C3-214387),CT3#118e(C3-215338), CT3#119e(C3-216182), CT3#121e (C3-222362), CT3#122e (C3-223575, C3-223606, C3-223648)
| Open API Specification |  | CT3#118e(C3-215338), CT3#122e (C3-223648, C3-223675)
Service Continuity APIs
| Target EAS Discovery API (Eees_TargetEASDiscovery) |  | Huawei | Merged with Eees_EASDiscovery API specified in TS 24.558
| Service Description |  | CT3#116e (C3-213547), CT3#118e (C3-215378), CT3#119e (C3-216347), CT3#121e (C3-222362), CT3#122e (C3-2236467)
| API Definition |  | CT3#116e (C3-213547), CT3#118e (C3-215377), CT3#121e (C3-222362), CT3#122e (C3-2236467)
| Open API Specification |  | None | No Open API, as the this API is merged with Eees_EASDiscovery Service specified in CT1 TS 24.558
Automated ACR API (Eees_EELManagedACR)
| Service Description |  | CT3#120e (C3-221635), CT3#121e (C3-222362)
| API Definition |  | CT3#120e (C3-221636), CT3#120e (C3-221407), CT3#120e (C3-221408), CT3#121e (C3-222362), CT3#122e (C3-223336)
| Open API Specification |  | CT3#120e (C3-221637), CT3#121e (C3-222137), CT3#122e (C3-223675)
| App Context relocation API (Eees_AppContextRelocation) |  |  | Discussed on how to specify this API between CT1 and CT3 specifications, as both EEC and EAS are consumers of this API. Unification with Eees_SelectedTargetEAS API. Working Agreement - CT3#121e (C3-222576), to merge the SelectedTargetEAS andn AppContextRelocation APIs. The SelectedTargetEAS is proposed to be part/as service operation of AppContextrelocation API.
| Service Description |  | CT3#121e (C3-222576), CT3#122e (C3-223334)
| API Definition |  |  | API definition specified in TS 24.558
| Open API Specification |  |  | Open API file specified in TS 24.558
| Selected Target EAS API (Eees_SelectedTargetEAS) |  |  | Discussed on Unification with Eees_AppContextRelocation API. Working Agreement - CT3#121e (C3-222576), to merge the SelectedTargetEAS andn AppContextRelocation APIs. The SelectedTargetEAS is proposed to be part/as service operation of AppContextrelocation API.
| Service Description |  | CT3#117e (C3-214390), CT3#121e (C3-222362), CT3#121e (C3-222576)
| API Definition |  | CT3#117e (C3-214390), CT3#121e (C3-222362), CT3#121e (C3-222576) | Merged with Eees_APPContextRelocation API. Specified in TS 24.558
| Open API Specification |  |  | Merged with Eees_APPContextRelocation API. Specified in TS 24.558
ACR status update (Eees_ACRStatusUpdate)
| Service Description |  | CT3#120e (C3-221630), CT3#121e (C3-222362)
| API Definition |  | CT3#120e (C3-221631, C3-221632, C3-221633), CT3#121e (C3-222362, C3-222143, C3-222409)
| Open API Specification |  | CT3#120e (C3-221634), CT3#121e (C3-222136, C3-222143, C3-222409), CT3#122e (C3-223675)
EEC Context Relocation APIs
| EEC Context Pull (Eees_EECContextPull) |  |  | EEC Context Push and Pull APIs merged to singel API Eees_EEContextRelocation API.
| Service Description |  | CT3#118e (C3-215342), CT3#119bis-e (C3-220459), CT3#121e (C3-222362)
| API Definition |  | CT3#119bis-e (C3-220459), CT3#121e (C3-222362, C3-223756)
| Open API Specification |  | CT3#119bis-e (C3-220459), CT3#122e (C3-223675, C3-223756)
| EEC Context Push (Eees_EECContextPush) |  |  | EEC Context Push and Pull APIs merged to singel API Eees_EEContextRelocation API.
| Service Description |  | CT3#118e (C3-215342), CT3#119bis-e (C3-220459)
| API Definition |  | CT3#119bis-e (C3-220459), CT3#122e (C3-223756)
| Open API Specification |  | CT3#119bis-e (C3-220459), CT3#122e (C3-223675, C3-223756)
ECS Services
Registration
EES Registration API (Eecs_EESRegistration)
| Service Description |  | CT3#114e (C3-211506), CT3#117e (C3-214389), CT3#121e (C3-222362)
| API Definition |  | CT3#114e (C3-211507), CT3#116e (C3-213327), CT3#117e (C3-214389), CT3#118e(C3-215341), CT3#119e (C3-216386), CT3#120e (C3-221726), CT3#121e (C3-222362, C3-222363), CT3#122e (C3-223331)
| Open API Specification |  | CT3#118e(C3-215341), CT3#119e (C3-216386), CT3#122e (C3-223675)
Service Continuity APIs
Target EES Discovery (Eecs_TargetEESDiscovery)
| Service Description |  | CT3#117e (C3-214391), CT3#121e (C3-222362)
| API Definition |  | CT3#117e (C3-214391), CT3#121e (C3-222362), CT3#122e (C3-223325)
| Open API Specification |  | CT3#119bis-e(C3-220421), CT3#122e (C3-223675)
| Network capability exposure to EAS |  | CT3#120e (C3-221401)
| Using Common API Framework |  | CT3#120e (C3-221401)
| Utlizing 3GPP core network capabilities |  |  | Covered in CAPIF clause.The additional aspects on how to EES/EAS can leverage core network capabilites is specified in stage 2 (23.558), no additional aspects to be specified in TS 29.558
| Security |  | CT3#118e(C3-215340), CT3#121e (C3-222362), CT3#122e (C3-223675)
| Dynamic EAS instantiation triggering |  |  | No stage 3 impacts identified.
| Annex Updates |  |  | Only Open API updates
| TS cleanup - Editorials |  |  | Removed the guidance text and template clauses as part of TS 29.558 v1.5.0 implementation
| TS (For Info) |  | CT#93e TS cover for Information - CT3#117e (C3-214569) | v0.1.0 - CT3#113e (C3-210322) - 5% v0.2.0 - CT3#114e (C3-211508) - 20% V0.3.0 - CT3#115e (C3-212520) - 30% v0.4.0 - CT3#116e (C3-213328) - 50% v0.5.0 - CT3#117e (C3-214571) - 60% v1.0.0 - Submitted for information to CT#93e plenary. V1.1.0 - CT3#118e (C3-215471) - 70% v1.2.0 - CT3#119e (C3-216515)- 75% v1.3.0 - CT3#119Bis-e (C3-220447) - 82% v1.4.0 - CT3#120e (C3-221510) - 90% v1.5.0 - CT3#121e (C3-222481) - 96% v1.6.0 - CT3#122e (C3-223504) - 100% (TS) | WID Revised - CT3#116e (C3-213323) - CT#92e (CP-211196) WID Revision (Move Approval to CT#95e-Mar 22) - CT3#119e (C3-216367) WID Revision (Include TS 29.122, 29.522) - CT3#120e (C3-221696) WID revision - Include some user consent aspects impact - CT3#121e (C3-222474) WID completion - 99% (After CT3#122e meeting)
| TS (For approval) |  | CT#94e | CT3#119e (C3-216367) - Move to CT#95e TS Approved in CT#96-e - June 2022 > Presentation sheet - C3-223768 > TS v1.6.0 - C3-223504 | Exception sheet taken - CT3#120e (C3-221739) Exception sheet - CT3#122e (C3-223800) > Alignment of user consent aspects based on stage-2 feedback.
29.222 | Common API Framework for 3GPP Northbound APIs (Rel-17)
| AEF Location support in service API - Publish Service API |  | CT3#118e(C3-215325)
| Service Description |  |  |  | No updates needed
| API Definition |  | CT3#118e(C3-215325)
| Open API specification |  | CT3#118e(C3-215325)
29.522 29.122 | AF Specific UE ID retreival |  |  |  | NEF APIs as per TS 23.502, to retrieve UE ID by an AF.
| TS 29.522 |  | CT3#120e (C3-221116), CT3#122e (C3-223645, C3-223757, C3-223769)
| TS 29.122 |  | CT3#120e (C3-221586, C3-221587, C3-221588), CT3#122e (C3-223318)

## Incoming LSs
Incoming liaision statements (LS)
Tdoc # | Topic | Reply LS | Related tdocs: CT3 meeting #; tdoc(s) # | Open issues | Comments
C3-205086 | LS on APIs in EDGEAPP | C3-205335 |  |  | SA6 informing decision of APIs for EDGE-1/4 interfaces and unification of APIs.
C3-212047 | Reply LS on clarification regarding EEC ID |  |  |  | SA6 clarified SA3 on EEC ID.

## Outgoing LSs
Outgoing liaision statements (LS)
Tdoc # | Topic | Related tdocs: CT3 meeting #; tdoc(s) # | Open issues | Comments
C3-205335 | Reply to LS on APIs in EDGEAPP |  | Work split coordination with CT1 Unification of APIs response from SA6 | CT3 would like to understand exactly which APIs could be modelled as unified service and which service consumers are served by such APIs? Based on this information, CT3 would be able to provide concrete feedback on the design choice.
C3-212554 | LS on clarification on the API design principle |  | Criteria for querying information - Get method vs Custom (POST) op Criteria for custom operation with or without resources
C3-220481 | LS out Rel-17 LS on Enquires on Application Context Relocation (ACR) functionality
C3-220405 | LS out Rel-17 LS on clarifications to the Application Context Relocation (ACR) functionality
C3-223780 | LS out Rel-17 LS on user’s consent for EDGEAPP |  | User consent aspects for UE Identifier API