## CT3
[C3-224416] CT3 Work Plan - 08/2022 - 5MBS WI (CP-221084) - Exception sheet for Q3-2022 (CP-221102)
# | Impact Description |  | Specification | Contributing company(ies) | Agreed Tdoc Numbers | Targeted CT3 meeting | Status
Impacts to the PCC framework
1 | New Npcf_MBSPolicyControl service/API exposed by the PCF to support MBS Policy Association management and MBS QoS control procedures. | TS Skeleton and general clauses (e.g. Scope, Overview, Definitions, etc.) | 29.537 (new) | Huawei, Nokia | C3-220113, C3-220114, C3-220401, C3-220402, C3-220403 | CT3#119-bis-e | Done
2 |  | Service and service operations description clauses | 29.537 (new) | Nokia, Huawei | C3-220491, C3-222056, C3-222462, C3-223564 | CT3#119-bis-e --> CT3#123-e | Ongoing
3 |  | API general clauses (i.e. Introduction, Usage of HTTP, Error Handling, Feature negotiation, Security) | 29.537 (new) | Huawei, Nokia | C3-220115 | CT3#119-bis-e --> CT3#121-e | Done
4 |  | API resources and custom operations clauses | 29.537 (new) | Huawei, Nokia | C3-220116, C3-222056 | CT3#119-bis-e --> CT3#123-e | Ongoing
5 |  | API notifications clauses | 29.537 (new) | Nokia, Huawei | C3-220492, C3-222462 | CT3#119-bis-e --> CT3#123-e | Ongoing
6 |  | API data model clauses | 29.537 (new) | Huawei, Nokia | C3-220404, C3-222056, C3-222462 | CT3#119-bis-e --> CT3#123-e | Ongoing
7 |  | OpenAPI description | 29.537 (new) | Nokia, Huawei | C3-220493, C3-222056, C3-222462 | CT3#119-bis-e --> CT3#123-e | Ongoing
8 |  | Corrections, general clean-up and resolving ENs | 29.537 (new) | Huawei, Nokia | C3-222124, C3-223308, C3-223561, C3-223565, C3-223566, C3-223568, C3-223573, C3-223574 | CT3#120-e --> CT3#123-e | Ongoing
9 | New Npcf_MBSPolicyAuthorization service/API exposed by the PCF to support MBS Policy Authorization procedures. | TS Skeleton and general clauses (e.g. Scope, Overview, Definitions, etc.) | 29.537 (new) | Huawei | C3-222403 | CT3#121-e | Done
10 |  | Service and service operations description clauses | 29.537 (new) | Huawei | C3-222404 | CT3#121-e --> CT3#123-e | Ongoing
11 |  | API general clauses (i.e. Introduction, Usage of HTTP, Error Handling, Feature negotiation, Security) | 29.537 (new) | Huawei | C3-222127 | CT3#121-e | Done
12 |  | API resources and custom operations clauses | 29.537 (new) | Huawei | C3-222405 | CT3#121-e --> CT3#123-e | Ongoing
13 |  | API notifications clauses | 29.537 (new) | Huawei |  | CT3#121-e --> CT3#123-e | Ongoing
14 |  | API data model clauses | 29.537 (new) | Huawei | C3-222406 | CT3#121-e --> CT3#123-e | Ongoing
15 |  | OpenAPI description | 29.537 (new) | Huawei | C3-222407 | CT3#121-e --> CT3#123-e | Ongoing
16 |  | Corrections, general clean-up and resolving Ens | 29.537 (new) | Huawei | C3-223308, C3-223562, C3-223563 | CT3#122-e --> CT3#123-e | Ongoing
17 | Enhancements to the BSF services to support MBS Session binding. Pending the final decision from stage 2 (in SA2). | Update the Nbsf_management_Register/Update/Deregister service operations to allow a PCF to register itself / update its registration / deregister itself at the BSF as the PCF handling an MBS session. | 29.521 | Huawei |  | CT3#123-e | Planned
18 |  | Update the Nbsf_Management_Discovery service operation to allow the AF/NEF/MBSF to discover the PCF handling an MBS Session (in case the Npcf_MBSPolicyAuthorization_Create service operation is invoked by the AF/NEF/MBSF). | 29.521 | Huawei |  | CT3#123-e | Planned
19 |  | Potential update of the Nbsf_management_Subscribe/Unsubscribe/Notify service operations to support the case of subscription to MBS PCF registration/deregistration events | 29.521 | Huawei |  | CT3#123-e | Planned
20 | Impacts to the UDR services for QoS information storage and retrieval (e.g. by the PCF) to support MB Session configuration and management procedures. Pending the final decision from stage 2 (in SA2). | Definition of preconfigured/provisioned MBS session related policy information (e.g. applicable QoS, MBS Session-AMBR and/or default 5QI) for an MBS session ID or an application ID. | 29.519 | Huawei, Nokia, Ericsson |  | CT3#123-e | Planned
21 |  | Impacts on the existing service operations or definition of new ones to support the storage, provisioning (e.g. by an AF) and retrievel (by the PCF) of MBS session related policy information. | 29.519 | Huawei, Nokia, Ericsson |  | CT3#123-e | Planned
22 | Impacts to PCC signalling procedures defined in TS 29.513 to support MBS session and QoS management. Pending the final decision from stage 2 (in SA2). | Update the PCC signalling procedures to support MBS Session related policy control (e.g. definition of the procedures related to MBS policy control, MBS session binding, interactions with the UDR, etc.). | 29.513 | Ericsson | C3-223478, C3-223479, C3-223480, C3-223481, C3-223502, C3-223483, C3-223484, C3-223485 | CT3#122-e --> CT3#123-e | Ongoing
Impacts to the 3GPP Northbound Interfaces
23 | New Nnef_MBSTMGI service/API exposed by the NEF to support MBS TMGI allocation procedures. | Procedures description part | 29.522 | Huawei, Nokia, Ericsson | C3-215332, C3-220106 | CT3#118-e | Done
24 |  | API definition part (i.e. Introduction, Resources, Custom operations, Notifications, Data model, Used features) | 29.522 | Huawei, Nokia, Ericsson | C3-216345 | CT3#118-e/CT3#119-e | Done
25 |  | OpenAPI description | 29.522 | Huawei, Nokia, Ericsson | C3-216346 | CT3#118-e/CT3#119-e | Done
26 |  | General clean-up, corrections and resolving ENs | 29.522 | Huawei, Nokia | C3-220034, C3-221418, C3-223559 | CT3#119-bis-e --> CT3#123-e | Ongoing
27 | New Nnef_MBSSession service/API exposed by the NEF to support MB session management procedures and operations towards 5GC (e.g. TMGI allocation, MBS session management, etc.). | Procedures description part | 29.522 | Nokia, Huawei | C3-216096, C3-220107 | CT3#119-e | Done
28 |  | API definition part (i.e. Introduction, Resources, Custom operations, Notifications, Data model, Used features) | 29.522 | Nokia, Huawei | C3-216097, C3-220108, C3-223316 | CT3#119-e | Done
29 |  | OpenAPI description | 29.522 | Nokia, Huawei | C3-216098 | CT3#119-e | Done
30 |  | Support of location dependent MBS session | 29.522 | Nokia | C3-222054 | CT3#121-e | Done
31 |  | Support of MBS Frequency Selection Area Identifier management | 29.522 | Nokia | C3-222055 | CT3#121-e | Done
32 |  | General clean-up, corrections and resolving ENs | 29.522 | Huawei, Nokia | C3-220034, C3-221310, C3-221489, C3-221483, C3-221111, C3-221555, C3-221629, C3-222463, C3-222059, C3-222060C3-223317, C3-223558, C3-223560 | CT3#119-bis-e --> CT3#123-e | Ongoing
33 | Impacts to the NEF services to support the provisioning of MBS Session authorization information by an AF. | Impacts to the Nnef_ParameterProvision service API to support that an AF provisions MBS Session authorization information. | 29.522 | Huawei |  | CT3#123-e | Planned
34 | Definition of the new Nnef_MBSUserService service/API: Support MBS User Service provisioning, retrieval, update and removal. | TS Skeleton and general clauses (e.g. Scope, Overview, Definitions, etc.) | 29.522 | Huawei |  | CT3#123-e | Planned
35 |  | Service and service operations description clauses | 29.522 | Huawei |  | CT3#123-e | Planned
36 |  | API general clauses (i.e. Introduction, Usage of HTTP, Error Handling, Feature negotiation, Security) | 29.522 | Huawei |  | CT3#123-e | Planned
37 |  | API resources and custom operations clauses | 29.522 | Huawei |  | CT3#123-e | Planned
38 |  | API notifications clauses | 29.522 | Huawei |  | CT3#123-e | Planned
39 |  | API data model clauses | 29.522 | Huawei |  | CT3#123-e | Planned
40 |  | OpenAPI description | 29.522 | Huawei |  | CT3#123-e | Planned
41 |  | General clean-up and resolving ENs | 29.522 | Huawei |  | CT3#123-e | Planned
42 | Definition of the new Nnef_MBSUserDataIngestSession service/API: Support MBS User Data Ingest Session creation, retrieval, update and removal, in addition to MBS User Data Ingest Session events monitoring subscription creation/deletion and the related notifications. | TS Skeleton and general clauses (e.g. Scope, Overview, Definitions, etc.) | 29.522 | Ericsson |  | CT3#123-e | Planned
43 |  | Service and service operations description clauses | 29.522 | Ericsson |  | CT3#123-e | Planned
44 |  | API general clauses (i.e. Introduction, Usage of HTTP, Error Handling, Feature negotiation, Security) | 29.522 | Ericsson |  | CT3#123-e | Planned
45 |  | API resources and custom operations clauses | 29.522 | Ericsson |  | CT3#123-e | Planned
46 |  | API notifications clauses | 29.522 | Ericsson |  | CT3#123-e | Planned
47 |  | API data model clauses | 29.522 | Ericsson |  | CT3#123-e | Planned
48 |  | OpenAPI description | 29.522 | Ericsson |  | CT3#123-e | Planned
49 |  | General clean-up and resolving ENs | 29.522 | Ericsson |  | CT3#123-e | Planned
User Plane related impacts
50 | N6mb between MB-UPF and AF/AS | Impacts to the N6 interface to support 5MBS data delivery. | 29.561 | Ericsson | C3-223427, C3-223428 | CT3#122-e --> CT3#123-e | Ongoing
51 | Nmb8 between MBSTF and AF/AS | Impacts on MBSTF receive MBS data packets from AF/AS via reference point Nmb8. | 29.561 | Ericsson | C3-223427, C3-223429 | CT3#122-e --> CT3#123-e | Ongoing
52 | Nmb9 between MB-UPF and MBSTF | Impacts on MBSTF sends MBS data packets to the MB UPF via reference point Nmb9. | 29.561 | Ericsson | C3-223427, C3-223428 | CT3#122-e --> CT3#123-e | Ongoing
MBSF APIs
53 | Definition of the new Nmbsf_MBSUserService service/API: Support MBS User Service provisioning, retrieval, update and removal. More details are expected from stage 2 in SA4 on the data model. Conf. Call to be organised in June/July by SA4 WI rapporteur to clarify the remaining open points. | TS Skeleton and general clauses (e.g. Scope, Overview, Definitions, etc.) | 29.580(new) | Huawei | C3-221311, C3-221312, C3-221313, C3-222374 | CT3#120-e --> CT3#122-e | Done
54 |  | Service and service operations description clauses | 29.580 (new) | Ericsson | C3-222408, C3-222475, C3-223410, C3-223547, C3-223417, C3-223418, C3-223419 | CT3#121-e/CT3#122-e | Done
55 |  | API general clauses (i.e. Introduction, Usage of HTTP, Error Handling, Feature negotiation, Security) | 29.580 (new) | Ericsson | C3-223412 | CT3#122-e | Done
56 |  | API resources and custom operations clauses | 29.580 (new) | Huawei | C3-223310, C3-223604 | CT3#122-e | Done
57 |  | API notifications clauses | 29.580 (new) | Huawei | C3-223311 | CT3#122-e | Done
58 |  | API data model clauses | 29.580 (new) | Ericsson | C3-223545 | CT3#122-e --> CT3#123-e | Ongoing
59 |  | OpenAPI description | 29.580 (new) | Ericsson |  | CT3#123-e | Planned
60 |  | General clean-up and resolving ENs | 29.580 (new) | Huawei, Ericsson | C3-222373, C3-223315 | CT3#121-e --> CT3#123-e | Ongoing
61 | Definition of the new Nmbsf_MBSUserDataIngestSession service/API: Support MBS User Data Ingest Session creation, retrieval, update and removal, in addition to MBS User Data Ingest Session events monitoring subscription creation/deletion and the related notifications. More details are expected from stage 2 in SA4 on the data model. Conf. Call to be organised in June/July by SA4 WI rapporteur to clarify the remaining open points. | TS Skeleton and general clauses (e.g. Scope, Overview, Definitions, etc.) | 29.580 (new) | Huawei | C3-221311, C3-221312, C3-221313, C3-222374 | CT3#120-e --> CT3#122-e | Done
62 |  | Service and service operations description clauses | 29.580 (new) | Ericsson | C3-222408, C3-222476, C3-223543, C3-223745, C3-223421, C3-223422, C3-223423, C3-223747, C3-223748, C3-223750 | CT3#121-e/CT3#122-e | Done
63 |  | API general clauses (i.e. Introduction, Usage of HTTP, Error Handling, Feature negotiation, Security) | 29.580 (new) | Ericsson | C3-223544 | CT3#122-e | Done
64 |  | API resources and custom operations clauses | 29.580 (new) | Huawei | C3-223313, C3-223605 | CT3#122-e | Done
65 |  | API notifications clauses | 29.580 (new) | Huawei | C3-223314 | CT3#122-e | Done
66 |  | API data model clauses | 29.580 (new) | Ericsson | C3-223546 | CT3#122-e --> CT3#123-e | Ongoing
67 |  | OpenAPI description | 29.580 (new) | Ericsson |  | CT3#123-e | Planned
68 |  | General clean-up and resolving ENs | 29.580 (new) | Huawei, Ericsson | C3-222373, C3-223315 | CT3#121-e --> CT3#123-e | Ongoing
MBS Security requirements from SA3
69 | Definition of the stage 3 requirements related to the stage 2 MBS security requirements (e.g. MBS keys management) defined in Annex W of 3GPP TS 33.501. | Impacts to the MBSF to support MBS Security Context (i.e. MSK/MTK and the related information) management. More details from stage 2 in SA4 are expected (ongoing LS exchange between SA4 and SA3) | 29.580 (new) | Huawei |  | CT3#123-e | Planned
xMB interface
70 | xMB interface enhancement to support the necessary extensions for 5GMS via eMBMS, as defined in 3GPP TS 26.348. | Impacts to xMB interface to support the necessary extensions for 5GMS via eMBMS, as defined in 3GPP TS 26.348. | 29.116 | Huawei, Qualcomm |  | CT3#123-e | Planned