## Tdoc cover sheet
3GPP TSG-CT WG3 Meeting #126 Athens, Greece, 27th Feb - 3rd Mar, 2023 |  | C3-230584
Source: | Samsung Electronics
Title: | Work plan for CT3 aspects of System Support for AI/ML-based Services
Agenda item: | 18.1.3
Document for: | Information

## Contributions plan
Contribution Plan
Spec (Rel-18) | Topic | SA2 agreed CR(s) | Responsible Company | Related LS or other WG tdoc(s) # | CT3 meeting #; tdoc(s) # | Comments | Open issues
To be approved WID - CP-23xxxx
29.xxx | 5G System; Planned Data Transfer Policy Control Service; Stage 3
TS Skeleton
| Enhancements of PCF Services and NEF Services | S2-2211333 | Huawei, OPPO
| Enhancements of PCF Services and NEF Services | S2-2211426 | Huawei, OPPO
| Adding support for Negotiations for planned data transfer with QoS (PDTQ) with QoS requirements as agreed in TR 23.700-80 | S2-2211427 | Ericsson, OPPO
TS for Information (CT3#102 Dec 2023)
TS for approval (CT3#103 Dec 2024)
29.122 | T8 reference point for Northbound APIs
| AIMLsys: KI#1 – 23.502 Solution for 5GC assistance to support Group-MBR Monitoring via NEF Event Exposure Extensions | S2-2211439 | Huawei, OPPO, Toyota
| Adding support for Negotiations for planned data transfer with QoS (PDTQ) with QoS requirements as agreed in TR 23.700-80 | S2-2211427 | Ericsson, OPPO
29.522 | 5G System; Network Exposure Function Northbound APIs; Stage 3
| Enhancements of PCF Services and NEF Services | S2-2211333 | Huawei, OPPO
| Enhancements of PCF Services and NEF Services | S2-2211426 | Huawei, OPPO
| AIMLsys: KI#1 – 23.502 Solution for 5GC assistance to support Group-MBR Monitoring via NEF Event Exposure Extensions | S2-2211439 | Huawei, OPPO, Toyota
29.513 | 5G System; Policy and Charging Control signalling flows and QoS parameter mapping; Stage 3
29.514 | 5G System; Policy Authorization Service; Stage 3
29.519 | 5G System; Usage of the Unified Data Repository Service for Policy Data, Application Data and Structured Data for Exposure; Stage 3
29.520 | 5G System; Network Data Analytics Services; Stage 3
| TS 23.288 Enhancement to Support AI/ML Data Transfer | S2-2211182 | NTT DOCOMO, OPPO
| Enhancements to Network Performance Analytics to support AIML data traffic policies | S2-2211331 | Huawei
| NWDAF updates to assist resource monitoring of AI/ML-based services | S2-2211330 | Samsung
29.552 | 5G System; Network Data Analytics signalling flows; Stage 3 |  |  |  |  | Is this Spec is impacted? Update WID
29.521 | 5G System; Binding Support Management Service; Stage 3
| Security aspects (any additional) |  |  |  |  | To include the SA3 agreed CRs
Annex Updates (if needed)
WID Target Completion - TSG CT#103 (March 2024)

## Incoming LSs
Incoming liaision statements (LS)
Tdoc # | Topic | Reply LS | Related tdocs: CT3 meeting #; tdoc(s) # | Open issues | Comments

## Outgoing LSs
Outgoing liaision statements (LS)
Tdoc # | Topic | Related tdocs: CT3 meeting #; tdoc(s) # | Open issues | Comments