## Tdoc cover sheet
3GPP TSG-CT WG3 Meeting #128 Bratislava, Slovakia, 22nd - 26th May, 2023 |  | C3-232342
Source: | Samsung Electronics
Title: | Work plan for CT3 aspects of EDGEAPP_Ph2
Agenda item: | 18.14
Document for: | Information

## Contributions plan
Contribution Plan
Spec | Topic | SA6 agreed CR(s) | Responsible Company | Related LS or other WG tdoc(s) # | Approved CT3 meeting tdoc(s) | Comments | Open issues
29.558 | EDGEAPP APIs specification; Stage 3; (Rel-18) |  |  |  |  | Approved WID - CP-223207
Overview
References
Definition of Terms and Abbreviation
| Definitions of terms, symbols and abbreviations | S6-230373 | China Mobile
Introduction of EES services
Eees_EASRegistration (Service description, API definition, OpenAPI)
| ACR request trigger timing | S6-223518 | KPN N.V. |  | C3-230725 | EAS Profile update. May have impacts to AppContextRelocation API
| EAS Bundles | S6-231074 | Qualcomm, Huawei |  | C3-231589 | Editor’s note: Whether the EAS bundle requirements are needed within the EAS profile/EAS discovery filters or EES Profile is FFS. The definition of this data type is FFS and needs to align with 3GPP TS 24.558.
| EEC selected ACR scenario for EAS bundles | S6-231075 | Huawei |  | C3-231589 | Editor’s note: Whether the EAS bundle requirements are needed within the EAS profile/EAS discovery filters or EES Profile is FFS. The definition of this data type is FFS and needs to align with 3GPP TS 24.558.
Eees_UELocation (Service description, API definition, OpenAPI)
Eees_UEIdentifier (Service description, API definition, OpenAPI)
| Updating UE Identifier API procedure to enable EEC invoke UE ID request for NATed IP address | S6-23103, S6-231036 | AT&T, Qualcomm, China Mobile, Ericsson |  |  | This API can be extended in CT3, when the consumer is EEC.
| EAS-specific UE ID (Edge UE ID) | S6-231032 | AT&T, Qualcomm, Samsung, KPN, Intel |  |  | Definition of EAS specific UE ID.
| UE ID definition Clarification | S6-231033 | AT&T, Qualcomm, Samsung, KPN, Intel
Eees_AppClientInformation (Service description, API definition, OpenAPI)
Eees_SessionWithQoS (Service description, API definition, OpenAPI)
| Support more traffic filters | S6-223038 | Ericsson |  | C3-231508 | Editor's Note: The response codes for ProblemDetails data type is FFS. Editor's Note: The HTTP status code is FFS.
Eees_EASDiscovery (Service description, API definition, OpenAPI)
| Support Discover T-EAS with Edge load performance information | S6-231011 | NTT |  |  | Check for stage-3 impacts (if any)
| Selected EAS instantiation | S6-230402 | Ericsson
Eees_ACRManagementEvent (Service description, API definition, OpenAPI)
| Support more traffic filters | S6-223038 | Ericsson |  | C3-231507 | Pending ENs: > Editor's Note: The data structure of the TrafficFilterInfo data type is FFS. > Editor's Note: The response codes for ProblemDetails data type is FFS. > Editor's Note: The HTTP status code is FFS.
| Addition of prediction expiration time IE and ACR information procedure | S6-223505 | Huawei |  | C3-231393 | Potential impacts to ACR Start/Stop events
| ACR scenario combination | S6-223534 | InterDigital, Samsung, Huawei |  | C3-231698 | "ACR Selection" event > Multiple EN's added to align the data model after agreement of information flows in stage-2 > Open API alignment pending.
Eees_AppContextRelocation (Service description, API definition, OpenAPI)
| EES monitoring the UE mobility for service continuity planning | S6-223616 | Huawei
| Support simu-EAS connectivity in ACR | S6-223078 | Ericsson |  |  | To check, any impacts in CT3
| Update ACR scenarios with ACR parameter procedure | S6-223599 | Huawei
| Addition of prediction expiration time IE and ACR information procedure | S6-223505 | Huawei |  |  | ACR procedure udpates
| ACR modification procedure | S6-230472 | Huawei
| Solve EN about multi-EAS connection | S6-230142 | Ericsson
| Editorial correction "General Context holding time duration" IE usage | S6-230029 | KPN N.V. |  | C3-230725, C3-231588
| Update ACR parameter information procedure | S6-230842 | Samsung |  |  | CT3 impacts based on resolution of EN in 23.558 "Editor's note: It is FFS whether and how EAS Acknowledgement requires enhancement."
| Solve EN about multi-EAS connection | S6-230142 | Ericsson
Eees_EECContextRelocation (Service description, API definition, OpenAPI)
| ACR scenario re-selection after a successful ACR | S6-231037 | Huawei, Samsung, InterDigital |  | C3-231696 | Stage-2 EN: Editor’s note: If EEC context does not exist, it is FFS how the selected ACR scenario list can be transferred to the T-EES during the ACR.
| EEC sharing UE Mobility requirement | S6-231072 | Samsung |  | C3-231703 | Update EEC context data type
Eees_EELManagedACR (Service description, API definition, OpenAPI)
Eees_ACRStatusUpdate (Service description, API definition, OpenAPI)
| ACR scenario re-selection after a successful ACR | S6-231037 | Huawei, Samsung, InterDigital |  |  | Stage-2 Editor’s note: Potential changes to ACR scenarios is FFS.
| Eees_TrafficInfluenceEAS (Service description, API definition, OpenAPI) |  |  |  |  | New API
| eEDGE_Application traffic influence trigger from EAS | S6-223566 | China Mobile
Introduction of ECS services
| Eecs_EESRegistration (Service description, API definition, OpenAPI) |  |  |  |  | Stage-2 EN: Editor’s note: Potential changes to ACR scenarios is FFS.
| EAS instantiation status provisioned by ECS | S6-223598 | Huawei |  | C3-231702 | EESProfile update.
| Updates to dynamic instantiation solution | S6-231082 | Samsung, Huawei |  | C3-231702 | EESProfile update. Editor’s Note: Inclusion of further criteria information in InstantiationCriteria data type is FFS.
| EAS Bundles | S6-231074 | Qualcomm, Huawei |  | C3-231589 | Editor’s note: Whether the EAS bundle requirements are needed within the EAS profile/EAS discovery filters or EES Profile is FFS. The definition of this data type is FFS and needs to align with 3GPP TS 24.558.
| EEC selected ACR scenario for EAS bundles | S6-231075 | Huawei |  | C3-231589 | Editor’s note: Whether the EAS bundle requirements are needed within the EAS profile/EAS discovery filters or EES Profile is FFS. The definition of this data type is FFS and needs to align with 3GPP TS 24.558.
| Supporting SNPN for the EES Topological Service Area |  | Ericsson |  | C3-231406
Eecs_TargetEESDiscovery (Service description, API definition, OpenAPI)
| Support for federation and roaming | S6-231070 | Huawei, Qualcomm, Samsung, NTT |  | C3-231395
ECS Edge Repository services
| ECS registration / deregistration | S6-231070 | Huawei, Qualcomm, Samsung, NTT |  |  | ECS --> ER
| ECS Discovery | S6-231070 | Huawei, Qualcomm, Samsung, NTT |  |  | ECS --> ER
| Service provisioning information retrieval | S6-231070 | Huawei, Qualcomm, Samsung, NTT |  |  | ECS --> ECS
| EAS discovery in edge node sharing | S6-231099 | Ericsson, Samsung, Huawei, Qualcomm |  |  | ECS <-> ECS, ECS-ER <-> ECS-ER
Cloud Application Server and Cloud enabler server
| Architecture with CAS and CES | S6-230465 | Ericsson |  |  | Check for any potential stage-3 impacts
| Architecture for ACR between edge and cloud | S6-230474 | Samsung, KPN |  |  | Check for any potential stage-3 impacts
| CR procedure btw EAS and CAS | S6-231071 | Ericsson |  |  | Check for any potential stage-3 impacts
CAPIF impacts
| Updates to architectural assumptions for EAS Service APIs enablement | S6-222878 | ETRI, Uangel |  | C3-231590
| Adding a CAPIF deployment for exposure of EAS Service APIs | S6-230463 | ETRI, Uangel |  | C3-231590
| EAS Service KPI support in Onboard, Publish, Discovery and Interconnect procedures | S6-230469 | China Mobile, ETRI
| Usage of SEAL services (for Notification Management Service) |  |  |  |  | New clause "Using SEAL" can be added to illustrate the usage of SEAL NMS by EES, ECS
| Edge Notification Service - solution | S6-222565 | Samsung |  |  | No stage3 procedure impacts.
| Edge Notification Service - architecture | S6-222564 | Samsung |  |  | EES or ECS as VAL Server contact SEAL NM server over NM-S ref point. No stage 3 procedure impacts
| Security aspects (any additional) |  |  |  |  | To include the SA3 agreed CRs
Annex Updates (if needed)
Target Completion - TSG CT#102 (December 2023)

## Incoming LSs
Incoming liaision statements (LS)
Tdoc # | Topic | Reply LS | Related tdocs: CT3 meeting #; tdoc(s) # | Open issues | Comments

## Outgoing LSs
Outgoing liaision statements (LS)
Tdoc # | Topic | Related tdocs: CT3 meeting #; tdoc(s) # | Open issues | Comments