## Tdoc cover sheet
3GPP TSG-CT3 Meeting #130 Xiamen, China, 9th – 13th October 2023 |  | C3-234125
Source: | Huawei
Title: | Updated SEALDD WI CT3 Work Plan
Agenda item: | 18.22
Document for: | Agreement

## CT3
CT3 Work Plan - CT3#130 - 2023-10 - SEALDD WI (CP-231284)
# | Impact Description |  | Specification | Contributing company(ies) | Agreed Tdoc Numbers | Targeted CT3 meeting | Status
1. Define SEALDD Server APIs exposed over the SEALDD-S and SEALDD-E interfaces
0 | New SEALDD Server Services TS | TS Skeleton | 29.548 (new) | Huawei | C3-230474 | CT3#126 | Done
|  | TS general clauses | 29.548 (new) | Huawei | C3-231212, C3-231568, C3-231214, C3-231569 | CT3#127-e | Done
1 | New SDD_RegularTransmission Service API to support SEALDD enabled regular data transmission management and SEALDD connection status event reporting | Service and service operations description clauses | 29.548 (new) | Huawei, Ericsson | C3-233658, C3-233718 | CT3#129 | Done
2 |  | API general clauses (i.e. Introduction, Usage of HTTP, Error Handling, Feature negotiation, Security) | 29.548 (new) | Huawei, Ericsson | C3-233659, C3-233719 | CT3#129 | Done
3 |  | API resources and custom operations clauses | 29.548 (new) | Huawei, Ericsson | C3-233659, C3-233719 | CT3#129 | Done
4 |  | API notifications clauses | 29.548 (new) | Huawei, Ericsson | C3-233659, C3-233719 | CT3#129 | Done
5 |  | API data model clauses | 29.548 (new) | Huawei, Ericsson | C3-233659, C3-233719 | CT3#129 | Done
6 |  | OpenAPI description | 29.548 (new) | Huawei, Ericsson | C3-233660, C3-233719, C3-234xxx | CT3#129 | Ongoing
7 |  | Corrections, general clean-up and resolving ENs | 29.548 (new) | Huawei, Ericsson | C3-234xxx | CT3#130 onwards | Planned
8 | New SDD_URLLCTransmission Service API to support SEALDD enabled URLLC data transmission service management | Service and service operations description clauses | 29.548 (new) | Huawei | C3-233658 | CT3#129 onwards | Ongoing
9 |  | API general clauses (i.e. Introduction, Usage of HTTP, Error Handling, Feature negotiation, Security) | 29.548 (new) | Huawei | C3-233659 | CT3#129 onwards | Done
10 |  | API resources and custom operations clauses | 29.548 (new) | Huawei | C3-233659 | CT3#129 onwards | Ongoing
11 |  | API notifications clauses | 29.548 (new) | Huawei | C3-233659 | CT3#129 onwards | Done
12 |  | API data model clauses | 29.548 (new) | Huawei | C3-233659 | CT3#129 onwards | Done
13 |  | OpenAPI description | 29.548 (new) | Huawei | C3-233660 | CT3#129 onwards | Done
14 |  | Corrections, general clean-up and resolving ENs | 29.548 (new) | Huawei |  | CT3#130 onwards | Planned
15 | New SDD_DataStorage Service API to support SEALDD data storage management (coordination with CT1 may be needed) | Service and service operations description clauses | 29.548 (new) | Huawei | C3-234xxx | CT3#130 onwards | Planned
16 |  | API general clauses (i.e. Introduction, Usage of HTTP, Error Handling, Feature negotiation, Security) | 29.548 (new) | Huawei | C3-234xxx | CT3#130 onwards | Planned
17 |  | API resources and custom operations clauses | 29.548 (new) | Huawei | C3-234xxx | CT3#130 onwards | Planned
18 |  | API notifications clauses | 29.548 (new) | Huawei | C3-234xxx | CT3#130 onwards | Planned
19 |  | API data model clauses | 29.548 (new) | Huawei | C3-234xxx | CT3#130 onwards | Planned
20 |  | OpenAPI description | 29.548 (new) | Huawei | C3-234xxx | CT3#130 onwards | Planned
21 |  | Corrections, general clean-up and resolving ENs | 29.548 (new) | Huawei |  | CT3#131 onwards | Planned
22 | New SDD_DDContext Service API to support SEALDD context relocation | Service and service operations description clauses | 29.548 (new) | Ericsson | C3-232513, C3-233715 | CT3#128 --> CT3#129 | Done
23 |  | API general clauses (i.e. Introduction, Usage of HTTP, Error Handling, Feature negotiation, Security) | 29.548 (new) | Ericsson | C3-233716 | CT3#128 --> CT3#129 | Done
24 |  | API resources and custom operations clauses | 29.548 (new) | Ericsson | C3-233716 | CT3#128 --> CT3#129 | Done
25 |  | API notifications clauses | 29.548 (new) | Ericsson | C3-233716 | CT3#128 --> CT3#129 | Done
26 |  | API data model clauses | 29.548 (new) | Ericsson | C3-233716 | CT3#128 --> CT3#129 | Done
27 |  | OpenAPI description | 29.548 (new) | Ericsson | C3-233717 | CT3#128 --> CT3#129 | Done
28 |  | Corrections, general clean-up and resolving ENs | 29.548 (new) | Ericsson, Huawei | C3-234xxx | CT3#130 onwards | Planned
29 | New SDD_TransmissionQualityMeasurement Service API to support SEALDD data transmission quality measurement management | Service and service operations description clauses | 29.548 (new) | Huawei | C3-232524, C3-233655, C3-233657 | CT3#129 onwards | Done
30 |  | API general clauses (i.e. Introduction, Usage of HTTP, Error Handling, Feature negotiation, Security) | 29.548 (new) | Huawei | C3-232525 | CT3#129 onwards | Done
31 |  | API resources and custom operations clauses | 29.548 (new) | Huawei | C3-232525, C3-233657 | CT3#129 onwards | Done
32 |  | API notifications clauses | 29.548 (new) | Huawei | C3-232525 | CT3#129 onwards | Done
33 |  | API data model clauses | 29.548 (new) | Huawei | C3-232526, C3-233656, C3-233657 | CT3#129 onwards | Done
34 |  | OpenAPI description | 29.548 (new) | Huawei | C3-232527, C3-233657 | CT3#129 onwards | Done
35 |  | Corrections, general clean-up and resolving ENs | 29.548 (new) | Huawei | C3-233657, C3-234xxx | CT3#129 onwards | Ongoing
36 | New SDD_PolicyConfiguration Service API to support SEALDD policy configuration management | Service and service operations description clauses | 29.548 (new) | Huawei | C3-234xxx | CT3#130 onwards | Planned
37 |  | API general clauses (i.e. Introduction, Usage of HTTP, Error Handling, Feature negotiation, Security) | 29.548 (new) | Huawei | C3-234xxx | CT3#130 onwards | Planned
38 |  | API resources and custom operations clauses | 29.548 (new) | Huawei | C3-234xxx | CT3#130 onwards | Planned
39 |  | API notifications clauses | 29.548 (new) | Huawei | C3-234xxx | CT3#130 onwards | Planned
40 |  | API data model clauses | 29.548 (new) | Huawei | C3-234xxx | CT3#130 onwards | Planned
41 |  | OpenAPI description | 29.548 (new) | Huawei | C3-234xxx | CT3#130 onwards | Planned
42 |  | Corrections, general clean-up and resolving ENs | 29.548 (new) | Huawei |  | CT3#130 onwards | Planned
2. Enhancement to support SEALDD related functionalities
43 | Enhancement to the SEAL specifications to support SEALDD related functionalities | Introduction of SEALDD related functionalities in TS 29.549 and linkage between TS 29.549 and the new TS 29.548. | 29.549 | Huawei | C3-231211 (CR#0145) | CT3#127-e | Done
3. Enhancements to support SEALDD server (acting as EAS) with transport layer service continuity capability
44 | Enhancements to support SEALDD server (acting as EAS) with transport layer service continuity capability. | Definition of the EAS capability for seamless transport layer service continuity for enabling seamless service continuity during SEALDD Server relocation (for the specific case of SEALDD context transfer with IP replacement). | 29.558 | Ericsson, Huawei | C3-230796, C3-231567 (CR#0065) | CT3-126/CT3#127-e | Done
45 |  | Definition of the SEALDD related EAS types/categories. (to be re-evaluated based on the feedback from SA6) | 29.538 | Huawei |  | CT3#129 onwards | Ongoing
4. Enhancements to the N6 interface to support SEALDD services
46 | Enhancements to the N6 interface to support SEALDD services | Updates to support the usage or the SEALDD enabler layer for data delivery over the N6 interface. | 29.561 | Huawei |  | CT3#131 onwards | Planned