## Tdoc cover sheet
3GPP TSG-CT WG3 Meeting #134 Changsha, China, 15th 19th April, 2024 |  | C3-242386
Source: | Samsung Electronics
Title: | Work plan for CT3 aspects of SEAL_Ph3
Agenda item: | 18.7
Document for: | Information

## Contributions plan
|  | In Progress | Completed | Not Started
Spec | Topic | SA6 agreed CR(s) | Responsible Company | Related LS or other WG tdoc(s) # | CT3 meeting #; tdoc(s) # | Comments | Open issues
29.549 | SEAL API Specification; Stage 3 (Rel-18) |  |  |  |  | Approved WID - CP-233219 (97% Complete)
Overview
| Add missing SEAL services | S6-230608 | Ericsson
References
| Definition of Terms and Abbreviation | S6-231612 | AT&T |  |  | Update not needed, its for SEAL-UU interface.
Introduction of SEAL services
Location Management APIs (Service description, API definition, OpenAPI)
| VAL service area identifier usage | S6-223588 | Samsung |  | C3-234467
| SS_LocationReporting API (data model and open API) | S6-232735 | Ericsson |  | C3-231603, C3-234668, C3-234668, C3-235713, C3-241678
| SS_LocationAreaInfoRetrieval API (data model and Open API) |  | Samsung |  | C3-233530
| SS_LocationMonitoring API (update SS_Events "LM_LOCATION_DEVIATION_MONITOR" event, data model and Open API) |  | Samsung |  | C3-233531
| SS_LocationAreaMonitoring API (Update SS_Events "LM_LOCATION_AREA_MONITOR") |  |  |  | CT3#126: C3-230722, C3-241557
| New SS_VALServiceAreaConfiguration API (service description, table 5.1-1, 5.1-2) | S6-231532 | Samsung, Ericsson |  | C3-232556, C3-234667
| New SS_VALServiceAreaConfiguration API (API data model) | S6-231532, S6-233736 | Ericsson, Samsung |  | C3-232654, C3-234664, C3-234664, C3-234667, C3-234696, C3-235590, C3-235661 | Editor's note: The error cases for the SS_VALServiceAreaConfiguration API are FFS.
| New SS_VALServiceAreaConfiguration API (Open API specification) | S6-231532, S6-233736 | Ericsson, Samsung |  | C3-232655, C3-234665, C3-234665, C3-234696, C3-235656, C3-241416
| Improved location monitoring procedure | S6-230400 | Ericsson |  |  | No stage-3 impacts.
| Supplmentation Location information source | S6-231064 | CATT, Kyonggi University |  |  | Already implemented in stage-3
| RAT change report via the LMS | S6-230858 | Ericsson |  | C3-234668 | Update with trigger information in LocationReporting API
| SS_LocationInfoEvent Update subscription | S6-233247 | Nokia |  | C3-241556 | Update service table with udpate service operation
| SS_LocationMonitoring Update subscription | S6-233248 | Nokia |  | C3-241556 | Update service table with udpate service operation
| Group Management APIs (Service description, API definition, OpenAPI) |  |  |  | C3-234467
| Complete location retrieval in an area | S6-220291 | Ericsson |  | CT3#125: C3--225572
| SS_GroupManagement API (Location Based group) - Service, Data model, Open API | S6-223588 | Samsung |  | CT3#126: C3-230723, C3-241690
Configuration Management APIs (Service description, API definition, OpenAPI)
| Minor correction on get VAL service | S6-230866 | China Mobile |  | C3-231600
| SS_VALServiceData API |  | Ericsson |  | C3-231600, C3-231601, C3-231602, C3-241534 | Editor's Note: The application errors in the SS_VALServiceData API are FFS. Editor's Note: Whether either the VAL UE(s) or the VAL user(s) can be provided in the query string, or combinations of VAL UE(s) and the VAL user(s) can be provided in the query string of this GET method is FFS and pending stage 2 feedback.
| Network resource Management APIs (Service description, API definition, OpenAPI) |  |  |  | C3-234669, C3-234669, C3-235099, C3-241322
| Application level control signalling over 5G MBS sessions | S6-222562 | Huawei
| Group media transmissions over 5G MBS sessions | S6-222254 | Huawei
| Activate or de-activate multicast MBS sessions | S6-222253 | Huawei |  | C3-231577, C3-233661, C3-233662
| MBS session deletion | S6-222512 | Huawei |  | C3-231577
| Updating MBS resources for group communications | S6-222561 | Huawei
| MBS session creation and MBS session announcement | S6-222510 | Huawei |  | C3-231577
| Update the NRM functional model to support 5MBS | S6-222509 | Huawei |  | C3-231577
| Update the requirement to support 5MBS | S6-222560 | Huawei |  |  | No stage-3 impacts. The related procedures and informations from stage-2 to be implemented
| Update the scope and reference to support 5MBS | S6-222247 | Huawei |  |  | No stage-3 impacts. The related procedures and informations from stage-2 to be implemented
| Update Unicast QoS Monitoring Subscription operation in the SS_NetworkResourceMonitoring API | S6-222458 | Ericsson |  | CT3#125: C3-225569, C3-225570, C3-225571
| VAL service over 5GS supporting EPS interworking | S6-223420 | Huawei |  |  | No stage-3 impacts. Stage-3 has everything needed.
| VAL service inter-system switching between 5G and LTE | S6-223555 | Huawei |  |  | Covered by the Notify_UP_Delivery_Mode notification. No further Stage-3 impacts
| Service continuity between 5G MBS delivery and unicast delivery | S6-223491 | Huawei
| NRM coordination for redundant PDU Session establishment | S6-223034, S6-233874 | Huawei, Nokia |  | C3-241533
| Updating MBS with dynamic PCC | S6-222997 | Huawei
| Information flows for MBS procedures | S6-222996 | Huawei |  | C3-231578, C3-231226, C3-231579, C3-231580, C3-234510, C3-235098
| Clarification on MBS service area in pre-conditions | S6-230859 | Huawei
| Clarification on UE session join notification | S6-230860 | Huawei
| Clarification on the unicast deliver stop after multicast MBS delivery | S6-230861 | Huawei
| SEAL NRM determines time synchronization activation for TSC stream | S6-232169 | Ericsson |  | C3-233543
| Background Data Transfer Configuration | S6-231614, S6-232737, S6-233923, S6-233715, S6-233875, S6-233876, S6-233877, S6-233924, S6-233867 | Convida, Nokia |  | C3-241488 | > Attribute presence condition to be updated based on S6-233923 > Other updates to be aligned based on S6-233715, S6-233875, S6-233876, S6-233877, S6-233924, S6-233867
| Service description |  |  |  | C3-235523, C3-235527
| API Data model |  |  |  | C3-235525, C3-235528, C3-241490
| Open API |  |  |  | C3-235529, C3-241489
| Unified traffic pattern and monitoring management | S6-231613, S6-232507 | Convida |  | C3-241620 | Stage-2 EN: Editor's Note: It is FFS whether and how NRM supports the functionality described in this clause as service to other SEAL servers, or only to VAL servers, as currently specified. Providing the functionality as service to other SEAL servers (as well as to VAL servers) has been studied in TR 23.700-97.
Service description
API Data model
Open API
| Identity Management APIs (Service description, API definition, OpenAPI) |  |  |  | C3-241534
| SEAL Registrar service | S6-223618 | Samsung |  | C3-230724, C3-232558
| Information flow for VAL server provisioning to the Identity Management Server | S6-230457 | Samsung
| New SS_IdmParameterProvisioning API (service description, table 5.1-1, 5.1-2) |  |  |  | CT3#126: C3-230724, C3-232558, C3-235585
| New SS_IdmParameterProvisioning API (API data model) |  |  |  | C3-232558, C3-233529, C3-235585, C3-241075
| New SS_IdmParameterProvisioning API (Open API specification) |  |  |  | C3-235585
Key Management APIs (Service description, API definition, OpenAPI)
| SS_KmParameterProvisioning API (VAL Server provisioning for Key management) | S6-231906, S3-234161 | Samsung, Motorola Solutions, Nokia |  | C3-241112
Service description
API Data model
Open API
Events APIs (Service description, API definition, OpenAPI)
| Impacts resulting from other APIs are specified under this API. |  |  |  | C3-241622 | Editor's note: The application errors for the SS_Events API are FFS.
Network slice capability management API (Service description, API definition, OpenAPI)
| add Cause IE to NSCE information flows | S6-223209 | China Mobile |  |  | Moved to new TS related to NSCALE
| update the NSCE functional | S6-223032 | China Mobile |  |  | Moved to new TS related to NSCALE
Notification Management Services API (if any) (Service description, API definition, OpenAPI)
| SEAL Notification Management Service - Information Flows and Procedures | S6-221957 | Samsung |  |  | 17.3.2.4 -> Notification message from VAL server to NMS server. No API or service needed for NMS to expose for VAL server, it was decided in SA6 that the URI will shared to VAL server, using which VAL server will post notification message.
| SEAL Notification Management service – Functional Model | S6-221956 | Samsung |  |  | Functional model and interface description. No stage 3 impacts in CT3.
| Any additional security aspects |  |  |  |  | No additional impacts
| Annex Updates (if needed) |  |  |  |  | Only respective Open API updates.
29.561 | 5G System; Interworking between 5G Network and external Data Networks; Stage 3
| Support the VAL server playing the role of an MBS AF |  | Huawei |  | C3-231223
29.222 | Common API Framework; Stage 3
| Service API status monitoring | S6-232147 | Ericsson |  | C3-231223, C3-234663
Target Completion - TSG CT#104 June 2024)

## Incoming LSs
Incoming liaision statements (LS)
Tdoc # | Topic | Reply LS | Related tdocs: CT3 meeting #; tdoc(s) # | Open issues | Comments

## Outgoing LSs
Outgoing liaision statements (LS)
Tdoc # | Topic | Related tdocs: CT3 meeting #; tdoc(s) # | Open issues | Comments
C3-231604 | LS out Rel-18 LS on the triggering criteria for the VAL service area in the SS_LocationReporting API | C3-231603 | Triggering criteria for VAL service area ID | > Q1: Does the triggering criteria based on the VAL service area ID support both periodic and event-triggered reporting? > Q2: If the event-triggered reporting is supported by the triggering criteria for the VAL service area ID, what event types should be supported?
C3-232465 | LS out Rel-18 LS on SS_IdmParameterProvisioning API service operations |  | Support of Update, Fetch and Delete service oprations
C3-233741 | LS on the Traffic specification for the time-synchronized TSC steam |  |  | Question: What information elements should be provided in the Traffic specification (from the TSC stream creation request defined in clause 14.3.2.25 of 3GPP TS 23.434) to determine whether the time synchronization needs to be activated for the TSC stream on the DS-TTs?