## General
3GPP TSG CT WG1 Meeting #154 PLACE, DATE |  |  | C1-251676
3GPP TSG CT WG3 Meeting #140 |  |  | C3-251046
3GPP TSG CT WG4 Meeting #128 PLACE, DATE |  |  | C4-251205
| Source | LG Electronics
| Title | Work Plan: CT Aspects of Phase3 for UAS, UAV and UAM
Agenda Item: 19.31
Document for: Discussion
Latest WID: CP-243077
Completion Status: CT#107:90% (CT1), 80%(CT3), 50%(CT4)

## SA2 Agreed CR
SA2 Agreed CRs
TS | Subject | Tdoc# | Contributor | Meeting# tdoc# | status | Affected Stage2 TS | Affected Stage3 TS | CT1 | CT3 | CT4 | Notes
General
23.256 | Addition of functionality for UAS_Ph3 to general concept | S2-2409508 (revision of S2-2408944) | LG Electronics, Ericsson, Qualcomm, InterDigital, FutureWei, Deutsche Telecom, Samsung | SA2#164 | agreed | 23.256 | NA
23.256 | Support new functionalities of UAV NF | S2-2409509 (revision of S2-2408945) | CATT | SA2#164 | agreed | 23.256 | NA
23.256 | GMLC LMF update for Ranging_SL | S2-2412596 | Nokia, Nokia Shanghai Bell | SA2#166 | agreed | 23.256 | NA
KI#1: Enhancement of NEF services to support service exposure and interactions between MNOs and UTM functions
KI#1: Pre-mission flight planing and in-mission flight monitoring
23.256 | Support of UAV flight planning and monitoring | S2-2409540 (revision of S2-2409510) | Huawei, HiSilicon, Ericsson | SA2#164 | agreed | 23.256 | NA
23.288 | Support of QoS Substainability Analytics for UAS | S2-2409511 (revision of S2-2408947) | Huawei, HiSilicon | SA2#164 | agreed | 23.288 | 29.520 |  | O |  | CT3#137, C3-245517 (LG Electronics, Nokia, agreed)
23.256 | Addressing the ENs on message names | S2-2412986 | Ericsson, Huawei, ETRI | SA2#166 | agreed | 23.256 | NA
23.256 | Instructing a UAV to perform its altitude reporting | S2-2413008 | Ericsson | SA2#166 | agreed | 23.256 | 29.518 29.522 |  | O | O
23.256 | Addressing the EN on Nnef_UAVFlightAssistance_Get service operations | S2-2413009 | Ericsson | SA2#166 | agreed | 23.256 | 29.522 |  | O |  | CT3#138, C3-246450 (Huawei, Ericsson, agreed) CT3#138, C3-246451 (Huawei, Ericsson, Nokia, agreed)
23.256 | Indicating optional steps of the pre-flight procedure | S2-2500440 | Ericsson | SA2#166AH-e | agreed | 23.256 | NA
23.256 | Service operation update | S2-2501300 | CATT | SA2#166AH-e | agreed | 23.256 | 29.522 |  | O
23.256 | Correction on UAV service operation description | S2-2501301 | Huawei, HiSilicon | SA2#166AH-e | agreed | 23.256 | 29.522 |  | O
23.256 | Clarification on reporting velocity in UAV location reporting procedure | S2-2501302 | China Mobile, Nokia, Nokia Shanghai Bell | SA2#166AH-e | agreed | 23.256 | NA
23.256 | Altitude reporting update | S2-2501304 | CATT | SA2#166AH-e | agreed | 23.256 | 29.522 |  | O
23.256 | Timestamping UAV's altitude information reports | S2-2502385 | Ericsson, Huawei | SA2#167 | agreed | 23.256 | 29.522 |  | O
KI#1: Multiple USS
23.256 | Support for multiple USS serving different geographical areas | S2-2409541 (revision of S2-2409512) | Ericsson | SA2#164 | agreed | 23.256 | 24.501 24.301 | O |  |  | CT1#151, C1-245881 (Ericsson, LG Electronics, Nokia, InterDigital, Sharp, agreed) CT1#151, C1-245883 (Ericsson, LG Electronics, Nokia, InterDigital, Sharp, agreed)
23.256 | Adding a new NEF service operations for USS | S2-2409513 (revision of S2-2408949) | Ericsson | SA2#164 | agreed | 23.256 | 29.522 |  | O |  | CT3#137, C3-245506 (Ericsson, Nokia, agreed) CT3#137, C3-245515 (Huawei, Ericsson, Nokia, agreed) CT3#138, C3-246272 (Ericsson, Nokia, agreed)
23.502 | Adding a new AMF event filter for UE/UAV deviation from the expected trajectory | S2-2409514 (revision of S2-2408950) | Ericsson | SA2#164 | agreed | 23.502 | 29.518 |  |  | O | CT4#125, C4-242291 (Ericsson, LG Electronics, Huawei, agreed) CT4#126, C4-245182 (Ericsson, LG Electronics, Huawei, agreed)
23.256 | USS discovery in multiple USS deployment | S2-2409515 (revision of S2-2408951) | Samsung, InterDigital, Huawei | SA2#164 | agreed | 23.256 | 29.518 29.522 |  | O | O | CT3#137, C3-245471(Huawei, agreed)
23.256 | Addressing the EN on security aspects of USS changeover | S2-2412590 | Ericsson | SA2#166 | agreed | 23.256 | NA
23.256 | Removing EN about border-crossing point | S2-2500385 | LG Electronics | SA2#166AHe | agreed | 23.256 | NA
23.256 | Correction on USS changeover aspects | S2-2501303 | Huawei, HiSilicon | SA2#166AHe | agreed | 23.256 | NA
23.256 | Correcting the USS changeover procedure | S2-2502386 | Ericsson | SA2#167 | agreed | 23.256 | NA
KI#1: C2 communication reliablity
23.256 | Support of C2 communication reliability | S2-2409516 (revision of S2-2408952) | Huawei, HiSilicon | SA2#164 | agreed | 23.256 | NA
23.256 | Adding C2 Communication Reliability with Redundant User Plane Paths to Annex | S2-2411158 | Ericsson, Huawei | SA2#165 | agreed | 23.256 | NA
KI#1: NEF enhancement
23.256 | Addressing the ENs on geographical description | S2-2411159 | Ericsson, Huawei | SA2#165 | agreed | 23.256 | NA |  | O
23.256 | Addressing the ENs on message names | S2-2411160 | Ericsson, Huawei | SA2#165 | agreed | 23.256 | NA
23.256 | Addressing the EN on Nnef_UAVFlightAssistance_Get service operations | S2-2410853 | Ericsson | SA2#165 | agreed | 23.256 | 29.522 |  | O |  | CT3#138, C3-246457 (Ericsson, agreed) CT3#138, C3-246458 (Ericsson, agreed) CT3#138, C3-246459 (Ericsson, agreed) CT3#138, C3-246518 (Ericsson, Huawei, agreed)
23.256 | Update to multiple USS serving different geographical areas | S2-2411161 | Huawei, HiSilicon | SA2#165 | agreed | 23.256 | NA
23.256 | Provisioning of information about USSes to UAVs and UAS NF | S2-2410856 | Ericsson, InterDigital, Samsung, LG Electronics, Huawei | SA2#165 | agreed | 23.256 | 24.501 24.301 29.255 | O | O |  | CT1#151, C1-245881 (Ericsson, LG Electronics, Nokia, InterDigital, Sharp, agreed) CT1#151, C1-245883 (Ericsson, LG Electronics, Nokia, InterDigital, Sharp, agreed)
23.288 | Adding a list of UEs as input for NWDAF analytics | S2-2410858 | Ericsson | SA2#165 | agreed | 23.288 | 29.520 29.522 |  | O |  | CT3#138, C3-246452 (Huawei, Ericsson, agreed) CT3#138, C3-246454 (Ericsson, Nokia, Huawei, agreed) CT3#138, C3-246453 (Ericsson, Huawei, agreed)
23.502 | Addressing the EN on UE's altitude reporting | S2-2411661 | Ericsson | SA2#166 | agreed | 23.502 | 29.518 |  |  | O
23.288 | Adding a list of UEs as input for NWDAF analytics | S2-2412593 (revision of S2-2410858) | Ericsson | SA2#166 | agreed | 23.288 | 29.520 |  | O
23.502 | Update Namf_EventExposure | S2-2500476 | CATT | SA2#166AHe | agreed | 23.502 | 29.518 |  |  | O
KI#2: NW-assisted DAA
23.256 | Adding support of network-assisted/ground-based mechanism for Detect And Avoid with 5GS information | S2-2409543 (revision of S2-2408953) | CATT, Ericsson, Huawei, HiSilicon, Nokia, Nokia Shanghai Bell | SA2#164 | agreed | 23.256 | 29.122 29.522 |  | O
23.256 | Updates to Network-Based/Assisted DAA Procedures | S2-2409998 | Ericsson | SA2#165 | agreed | 23.256 | 29.520 29.522 |  | O
23.256 | Update of procedure for UAV Triggered Network-assisted DAA | S2-2410857 | Huawei, HiSilicon, CATT | SA2#165 | agreed | 23.256 | NA
23.288 | Updates to Relative Proximity Analytics | S2-2410859 | Ericsson | SA2#165 | agreed | 23.288 | 29.522 |  | O
23.256 | Update of procedure for UAV Triggered Network-assisted DAA | S2-2412595 | Huawei, HiSilicon, CATT, Ericsson | SA2#166 | agreed | 23.256 | NA
KI#3: NTZ
23.256 | Support of No-Transmit Zones | S2-2411157 | LG Electronics, Qualcomm Incorporated, Ericsson, Futurewei, Samsung, Nokia, Nokia Shanghai Bell, Deutsche Telekom, SHARP | SA2#165 | agreed | 23.256 | 24.501 24.301 27.007 | O |  |  | CT1#151, C1-246020 (Ericsson, LG Electronics, agreed) CT1#151, C1-246021 (Ericsson, LG Electronics, agreed) CT1#152, C1-247030 (Ericsson, LG Electronics, Qualcomm Incorporated, Huawei, HiSilicon, Nokia, agreed) CT1#152, C1-247031 (Ericsson, LG Electronics, Qualcomm Incorporated, Huawei, HiSilicon, Nokia, agreed)
23.256 | Support of No-Transmit Zones | S2-2412987 | LG Electronics, Qualcomm Incorporated, Ericsson, Futurewei, Samsung, Nokia, Nokia Shanghai Bell, Deutsche Telekom, SHARP | SA2#166 | agreed | 23.256 | 24.501 24.301 27.007 | O |  |  | CT1#151, C1-246020 (Ericsson, LG Electronics, agreed) CT1#151, C1-246021 (Ericsson, LG Electronics, agreed) CT1#152, C1-247030 (Ericsson, LG Electronics, Qualcomm Incorporated, Huawei, HiSilicon, Nokia, agreed) CT1#152, C1-247031 (Ericsson, LG Electronics, Qualcomm Incorporated, Huawei, HiSilicon, Nokia, agreed)
23.256 | Clarifications to NTZ support | S2-2501305 | Qualcomm Incorporated | SA2#166AHe | agreed | 23.256 | 24.501 24.301 27.007 | O |  |  | CT1#153, C1-251013 (Ericsson, InterDigital, LG Electronics, Qualcomm Incorporated, Huawei, HiSilicon, Nokia, agreed) CT1#153, C1-251014 (Ericsson, InterDigital, LG Electronics, Qualcomm Incorporated, Huawei, HiSilicon, Nokia, agreed) CT1#153, C1-251017 (ZTE, agreed) CT1#153, C1-251018 (ZTE, agreed) CT1#153, C1-251019 (LG Electronics, Qualcomm, InterDigital, agreed)

## CT1 Topics
CT1 Topics
Topic number | Description | Stage-2 reference | TS | Contributor or Volunteered company | Meeting# tdoc# | status | Notes
A | General
B | Support of multiple USS serving different geographical areas corresponding to the UAV flight path
B-1 | List of USS addresses in 5GS | S2-240996 | 24.501 | Ericsson, LG Electronics, Nokia, InterDigital, Sharp | CT1#151, C1-245881 | agreed
B-2 | List of USS addresses in EPS | S2-240996 | 24.301 | Ericsson, LG Electronics, Nokia, InterDigital, Sharp | CT1#151, C1-245883 | agreed
C | Support of enforcement of the NTZ assistance information by the UE
C-1 | No-transmit zone restriction in 5GS | S2-2411157 | 24.501 | Ericsson, LG Electronics | CT1#151, C1-246020 | agreed | TR23.700-59 KI#3 final conclusion Revised version will be submitted to CT1#152 meeting
C-2 | No-transmit zone restriction in EPS | S2-2411157 | 24.301 | Ericsson, LG Electronics | CT1#151, C1-246021 | agreed | TR23.700-59 KI#3 final conclusion Revised version will be submitted to CT1#152 meeting
C-3 | No-transmit zone restriction in 5GS | S2-2411157 | 24.501 | Ericsson, LG Electronics, Qualcomm Incorporated, Huawei, HiSilicon, Nokia | CT1#152, C1-247030 | agreed
C-4 | No-transmit zone restriction in EPS | S2-2411157 | 24.301 | Ericsson, LG Electronics, Qualcomm Incorporated, Huawei, HiSilicon, Nokia | CT1#152, C1-247031 | agreed
C-5 | NTZ improvements | S2-2501305 | 24.501 | Ericsson, InterDigital, LG Electronics, Qualcomm Incorporated, Huawei, HiSilicon, Nokia | CT1#153, C1-251013 | agreed
C-6 | NTZ improvements | S2-2501305 | 24.301 | Ericsson, InterDigital, LG Electronics, Qualcomm Incorporated, Huawei, HiSilicon, Nokia | CT1#153, C1-251014 | agreed
C-7 | Clause subject and general description updates for support of NTZ | S2-2501305 | 24.501 | ZTE | CT1#153, C1-251017 | agreed
C-8 | Clause subject and general description updates for support of NTZ | S2-2501305 | 24.301 | ZTE | CT1#153, C1-251018 | agreed
D | (Potential) Update for corresponding AT command
D1 | Introduce new AT command +CNTZAI | S2-2501305 | 27.007 | LG Electronics, Qualcomm, interDigital | CT1#153, C1-251019 | agreed

## CT3 Topics
CT3 Topics
Topic number | Description | Stage-2 reference | TS | Contributor or Volunteered company | Meeting# tdoc# | status | Notes
A | General
| Enhancements to the MonitoringEvent API |  | 29.122
B | Update to the NEF northbound and USS interface to support
B1 | Pre-mission flight or in-mission planing assistance service
B1-1 | UAVFlightAssistance service descriptions and procedures | 23.288: S2-2409513 | 29.522 | Ericsson, Nokia | CT3#137, C3-245506 | agreed
B1-2 | UAVFlightAssistance API and data model definition | 23.288: S2-2409513 | 29.522 | Huawei, Ericsson, Nokia | CT3#137, C3-245515 | agreed
B1-3 | Add the new UAVFlightAssistance API in clause 5.1 | 23.288: S2-2413009 | 29.522 | Huawei, Ericsson | CT3#138, C3-246450 | agreed
B1-4 | UAVFlightAssistance API and data model definition | 23.288: S2-2413009 | 29.522 | Huawei, Ericsson, Nokia | CT3#138, C3-246451 | agreed
B1-5 | RetrieveInfoUAVFlight service descriptions and procedures | 23.256: S2-2410853 | 29.522 | Ericsson | CT3#138, C3-246457 | agreed
B1-6 | RetrieveInfoUAVFlight API definitions | 23.256: S2-2410853 | 29.522 | Ericsson | CT3#138, C3-246458 | agreed
B1-7 | RetrieveInfoUAVFlight API OpenAPI definitions | 23.256: S2-2410853 | 29.522 | Ericsson | CT3#138, C3-246459 | agreed
B1-8 | UAVFlightAssistance service descriptions and procedures | 23.288: S2-2409513 | 29.522 | Ericsson, Nokia | CT3#138, C3-246272 | agreed
B1-9 | UAVFlightAssistanceAPI OpenAPI definitions | 23.256: S2-2410853 | 29.522 | Ericsson, Huawei | CT3#138, C3-246518 | agreed
B1-10 | Support Altitude reporting information in the RetrieveInfoUAVFlight API | 23.256: S2-2501300 | 29.522 | Nokia, CATT | CT3#139, C3-250080 | agreed
B1-11 | Support Altitude reporting information in the Nnef_UAVFlightAssistance API | 23.256: S2-2501300, S2-2501304 | 29.522 | Nokia, CATT, LG Electronics, Huawei | CT3#139, C3-250634 | agreed
B1-12 | Updates and corrections to the RetrieveInfoUAVFlight API | NA | 29.522 | Huawei | CT3#139, C3-250607 | agreed
B1-13 | Updates and corrections to the UAVFlightAssistance API | NA | 29.522 | Huawei, Ericsson | CT3#139, C3-250609 | agreed
| Update timestamp in UAV's altitude information reports | 23.256: S2-2502385 | 29.522
B2 | Multiple USS service (e.g. USS/UTM changeover procedure for an UAV)
B2-1 | Support of provisioning of multiple USS information | 23.256: S2-2409515 | 29.522 | Huawei | CT3#137, C3-245471 | agreed
B2-2 | Add the missing USS information in the OpenAPI file | NA | 29.255 | Huawei | CT3#139, C3-250385 | agreed
B3 | Network-assisted DAA service
B3-1 | USS service to support Network-assisted DAA service |  | 29.255
B3-2 | Updates to the NEF northbound with USS interface to support Network-assisted DAA service |  | 29.522
C | Update to the NEF northbound to support the exposure of NWDAF Analytics service (e.g. Movement Behavior Analytics with height information or QoS Sustainability Analytics with 3D location waypoint)
C1-1 | Support of list of UEs for Movement Behaviour analytics | 23.288: S2-2410858 | 29.522 | Huawei, Ericsson | CT3#138, C3-246452 | agreed
C1-2 | Support list of UEs in QoS Sustanability and Movement Behaviour Analyses Exposure | 23.288: S2-2410858 | 29.522 | Ericsson, Nokia, Huawei | CT3#138, C3-246454 | agreed
C1-3 | NEF updates to Relative Proximity Analytics for UAS | 23.288: S2-2410859 | 29.522 | Ericsson | CT3#139, C3-250535 | agreed
D | Update to the NWDAF interface to enhance the inputs of NWDAF analytic service (e.g. Movement Behaviour Analytics with height information, QoS Sustainablity Analytics with 3D location waypoints)
D1-1 | Support for QoS Substainablity analytics for UAS | 23.288: S2-2409511 | 29.520 | LG Electronics, Nokia | CT3#137, C3-245517 | agreed
D1-2 | Support list of UEs in QoS Sustanability and Movement Behaviour Analyses | 23.288: S2-2410858 | 29.520 | Ericsson, Huawei | CT3#138, C3-246453 | agreed
D1-3 | Corrections and clarifications for Movement Behaviour analytics supporting list of Ues | NA | 29.520 | Huawei | CT3#139, C3-250386 | agreed
D1-4 | Update TTC predictions in Relative Proximity Analytics | 23.288: S2-2410859 | 29.520 | Ericsson, Nokia | CT3#139, C3-250534 | agreed

## CT4 Topics
CT4 Topics
Topic number | Description | Stage-2 reference | TS | Contributor or Volunteered company | Meeting# tdoc# | status | Notes
A | General
B | Update to the AMF event exposure service for new event filter includes new elements for assigned trajectory
B1 | New AMF Event of Trajectory Tracking for USS Change over | 23.502 S2-2409514 | 29.518 | Ericsson, LG Electronics, Huawei | CT4#125, C4-242291 | agreed
B2 | New AMF Event of Trajectory Tracking for USS Change over | 23.502 S2-2409514 | 29.518 | Ericsson, LG Electronics, Huawei | CT4#126, C4-245182 | agreed
| Update Namf_EventExposure | S2-2500476 S2-2413008 | 29.518
C | Update to the UDM service for expected UE behavior provisioning, e.g. for new elements for assigned trajactory
| Update to UDM services for expected UE behavior provisioning, e.g. for new elements for assigned trajectory. |  | 29.503
D | Enhancements to NEF (UAS-NF) southbound service in Nnef_Authentication API
| Clarifications on the scope | NA | 29.256 | CATT | CT4#127, C4-250441 | agreed

## LSs
Incoming liaision statements (LS)
Tdoc # | Topic | Reply LS | Related tdocs: CT1 meeting #; tdoc(s) # | Open issues | Comments
Outgoing liaision statements (LS)
Tdoc # | Topic | Reply LS | Related tdocs: CT1/3/4 meeting #; tdoc(s) # | Open issues | Comments
C3-250027 | Clarification of Nnef_RetrieveInfoUAVFlight_Get service operation | C3-250399 | C3-250384 | NA