## General
Latest update: 30/Oct/2023
| Source | Qualcomm Incorporated
| Title | Work Plan: CT Aspect of Further Architecture Enhancement for UAV and UAM (UAS_Ph2)
Agenda Item: UAS_Ph2
Document for: Discussion
Latest WID: CP-230191
Completion Status: CT#99:0% CT#100:50% CT#101:80%

## CT1 Topics
Latest update: 30/Oct/2023
CT1 Topics
Topic number | Description | Stage-2 reference | TS | Contributor | Meeting# tdoc# | status | Notes
A | General
1 | Skeleton of TS 24.577 |  | 24.577 | Qualcomm | CT1#141e, C1-232773 | agreed | Aircraft-to-Everything (A2X) services in 5G System (5GS) protocol aspects; Stage 3
2 | Skeleton of TS 24.578 |  | 24.578 | Qualcomm | CT1#141e, C1-232212 | agreed | Aircraft-to-Everything (A2X) services in 5G System (5GS); UE policies
3 | Scope of TS 24.577 |  | 24.577 | Qualcomm | CT1#141e, C1-232772 | agreed
4 | Scope of TS 24.578 |  | 24.578 | Qualcomm | CT1#141e, C1-232777 | agreed
5 | Abbreviation and definitions | 3.1, 3.2 of TS 23.256 | 24.577 24.578 | Qualcomm | CT1#141e, C1-232772, C1-232777 | agreed | Aircraft-to-everything
6 | AMF should not release NAS signalling after Registration procedure if the UE is authorized A2X |  | 24.501 | SHARP | CT1#141e, C1-232658 | agreed
7 | A2X over Uu |  | 24.501 24.577 | Ericsson | CT1#143 | agreed | MBS related
B | A2X communication over PC5
1 | General section for A2X | 4.2.1.2 of TS 23.256 | 24.577 | Qualcomm | CT1#141e | agreed
2 | A2X communication policy configuration | 4.2.1.2.2 of TS 23.256 | 24.577 | Nokia | CT1#141e, C1-232714, C1-232717 | agreed
3 | A2X communication policy configuration - policy encoding |  | 24.578 | ZTE | C1-234213 | agreed
4 | A2X capability indication | 4.3.3 and 4.3.4 of TS 23.256 | 24.501 | Nokia | CT1#140_Athens, C1-230986 | agreed
5 | A2X policy request indicator | 4.3.3 of TS 23.256 | 24.501 | Nokia | CT1#140_Athens, C1-230333 CT1#141e, C1-232139 | agreed
6 | A2X Communication procedures: Unicast mode A2X communication over NR-PC5 |  | 24.577 | Nokia | CT1#141e, C1-232718 | agreed
7 | A2X PC5 unicast link modification procedure |  | 24.577 | Nokia | CT1#141e, C1-232719 | agreed
8 | A2X PC5 unicast link release procedure |  | 24.577 | Nokia | CT1#141e, C1-232720 | agreed
9 | A2X Communication procedures: Broadcast mode A2X communication over PC5 |  | 24.577 | Nokia | CT1#141e, C1-232721 | agreed
10 | Clarification on inter-PLMN case for A2X communication |  | 24.577 | Nokia | CT1#142, C1-233237 | agreed | S2-2305580 (agreed)
11 | Clarification on independency to UUAA |  | 24.577 | Nokia | CT1#142, C1-233945 | agreed | S2-2305581 (agreed)
12 | A2X PC5 unicast link identifier update procedure |  | 24.577 | Nokia | CT1#142, C1-233943 | agreed
13 | A2X PC5 unicast link keep-alive procedure |  | 24.577 | Nokia | CT1#142, C1-233944 | agreed
14 | A2X PC5 unicast link QoS flow establishment |  | 24.577 | Nokia | CT1#142, C1-233235 | agreed
15 | A2X PC5 unicast link re-keying |  | 24.577 | Nokia | CT1#144 | agreed | message encoding will be proposed by Nokia in CT1#145
16 | A2X PC5 unicast link security |  | 24.577 | Nokia | CT1#144 | agreed | message encoding will be proposed by Nokia in CT1#145
17 | A2X authentication procedures |  | 24.577 | Nokia, Ericsson | CT1#144 | agreed | message encoding will be proposed by Nokia in CT1#145
C | BRID
1 | General description for BRID | 5.5 of TS 23.256 | 24.577 | Qualcomm | CT1#141e, C1-232774 | agreed
2 | BRID configuration parameters | 5.5 of TS 23.256 | 24.577 | Qualcomm | CT1#144 | agreed
3 | BRID configuration parameters - policy encoding |  | 24.578 | Qualcomm | CT1#144 | agreed
4 | procedures for BRID: Broadcast mode A2X communication over PC5 |  | 24.577 | Qualcomm | CT1#143 | agreed
5 | MBS support for Broadcast Remote ID based on and by referring to MBS support for V2X specified in TS 23.287. |  | 24.577 | Ericsson | CT1#143 | agreed | One EN remains. Ericsson will resolve the EN
6 | BRID configuration for MBS |  | 24.578 | ZTE | CT1#144 | agreed | One EN remains. Ericsson will resolve the EN
D | DDAA
1 | General description for DDAA | 5.6 of TS 23.256 | 24.577 | Qualcomm | CT1#141e, C1-232774 | agreed
2 | DDAA configuration parameters | 5.6 of TS 23.256 | 24.577 | Qualcomm | CT1#143 | agreed
3 | DDAA configuration parameters - policy encoding |  | 24.578 | Qualcomm | CT1#143 | agreed
4 | procedures for DDAA: Unicast mode A2X communication over NR-PC5 |  | 24.577 | Qualcomm | CT1#143 | agreed
5 | procedures for DDAA: Broadcast mode A2X communication over PC5 |  | 24.577 | Qualcomm | CT1#143 | agreed
E | Direct C2 communication
1 | General section for authorization of Direct C2 communication | 5.4 of TS 23.256 | 24.577 | ZTE | CT1#141e, C1-232755 | agreed
2 | Direct C2 communicationconfiguration parameters | 5.4 of TS 23.256 | 24.577 | ZTE | CT1#143, C1-233939 | agreed
3 | Direct C2 communicationconfiguration parameters - policy encoding |  | 24.578 | ZTE | CT1#142, C1-233941 CT1#143 | agreed
4 | C2 authorization procedure for Direct C2 communication using Service-level-AA procedure - 5GS | 5.4.3 of TS 23.256 | 24.501 | Nokia | CT1#141e, C1-232715 | agreed
5 | C2 authorization procedure for Direct C2 communication using Service-level-AA procedure - EPS | 5.4.3 of TS 23.256 | 24.301 | Nokia | CT1#141e, C1-232716 | agreed
5 | Direct C2 communication procedures | 5.4.4 of TS 23.256 | 24.577 | ZTE | CT1#141e, C1-232846 CT1#143 | agreed
7 | Direct C2 authorization during Registration procedure | 5.4.3.2 of TS 23.256 | 24.501 | Nokia | CT1#143, C1-234214 | agreed
8 | Clarification on Direct C2 authorization |  | 24.577 | Nokia | CT1#143, C1-233947 | agreed
F | Network-assisted (ground-based) DAA
1 | A2X service for Ground-based DAA for an area and its related operations | [5 empty] | One EN remains. Qualcomm will resolve the EN
G | AT command
Not applicable

## CT3 Topics
Latest update: 30/Oct/2023
CT3 Topics
Topic number | Description | Stage-2 reference | TS | Contributor | Meeting# tdoc# | status | Notes
A | PCF services
| Update to policy parameters to support A2X services |  | 29.513 | Nokia, Huawei, Qualcomm | CT3#127e, C3-231505 | agreed
| Update to support A2X services in UE policy control service |  | 29.525 | Nokia, Huawei | CT3#127e, C3-231506 | agreed
| Enhancements to AF-based service parameter provisioning for A2X communication |  | 29.513 | Huawei, Nokia | CT3#127e, C3-231465 | agreed
B | NEF services
| Update to Nnef_ServiceParameter service or Nnef_ParameterProvision service to support A2X services |  | 29.522 | Huawei, Nokia | CT3#127e, C3-231464 | agreed
C | UDR services for App data
| Update UDR services for Application Data to support A2X services |  | 29.519 | Nokia, Huawei | CT3#127e, C3-231501 | agreed
D | USS(Naf) services
| Update to support Direct C2 communication authorization |  | 29.255 | Huawei, Nokia, Qualcomm | CT3#127e, C3-231466 | agreed
E | support Broadcast Remote ID based on MBS location-dependent broadcast service | [5 empty] | nothing specific to A2X

## CT4 Topics
Latest update: 30/Oct/2023
CT4 Topics
Topic number | Description | Stage-2 reference | TS | Contributor | Meeting# tdoc# | status | Notes
A | Common
| Definition of new common data types applicable for multiple 5G services to support A2X services |  | 29.571 | Qualcomm Incorporated | CT4#117 | agreed
B | AMF services
| Update on AMF services to support A2X services |  | 29.518 | Qualcomm Incorporated | CT4#117 | agreed
C | UDM services
| Update to UDM services to support A2X services |  | 29.503 | Qualcomm Incorporated | CT4#117 | agreed
| A2X service authorization information per PC5 RAT |  | 29.503 | Qualcomm Incorporated | CT4#117 | agreed
D | Subscription data
| Update to UDR services for subscription data to support A2X services |  | 29.505 | Qualcomm Incorporated | CT4#117 | agreed
| Support for A2X service parameters provisioning |  | 29.504 | Nokia | CT4#115e, C4-231474 | agreed
E | NRF services
| Update on NRF for NF / NF service selection to support A2X services |  | 29.51 | Qualcomm Incorporated | CT4#117 | agreed
F | UAS-NF services
| Update to support C2 authorization for Direct C2 communication |  | 29.256 | Qualcomm Incorporated | CT4#117 | agreed

## CT6 Topics
Latest update: 28/Sep/2023
CT6 Topics
Topic number | Description | Stage-2 reference | TS | Contributor | Meeting# tdoc# | status | Notes
A | Configuration prarameter for A2X in USIM
| Update to add support for A2X services |  | 31.102

## Others
Incoming liaision statements (LS)
Tdoc # | Topic | Reply LS | Related tdocs: CT1 meeting #; tdoc(s) # | Open issues | Comments
Outgoing liaision statements (LS)
Tdoc # | Topic | Reply LS | Related tdocs: CT1 meeting #; tdoc(s) # | Open issues | Comments