## Tdoc cover sheet
3GPP TSG-CT WG4 Meeting #121 Athens, Greece, 26 February-1 March 2024 |  |  | C4-240482
Source: |  | Xiaomi
Title: | Title | Work Plan: CT aspects of Ranging based services and sidelink positioning
Agenda Item: |  | 6.2.20
Document for: |  | Information

## CT1 Topics
Topic number | Description | Stage-2 reference | TS | Volunteered company/Contributor | Meeting# | agreed tdoc# | status | Notes
A | General
| Skeleton of TS 24.514 |  | 24.514 | Xiaomi | CT1#141 | C1-232663 | agreed
| Scope of TS 24.514 |  | 24.514 | Xiaomi | CT1#141 | C1-232665 | agreed
| General section for ranging and sidelink positioning control |  | 24.514 | QUALCOMM | CT1#141 | C1-232783 | agreed | Clause 4
| Ranging SL related terms cleanup |  | 24.501 | ZTE | CT1#144 | C1-238144 | agreed
| Resolve the EN on RSPP referenced specification |  | 24.514 | ZTE | CT1#144 | C1-238146 | agreed
| Removing clarified ENs and alignment udpate |  | 24.514 | Xiaomi | CT1#147 | 1 | expected
B | Provisioning of configuration information for Ranging/SL positioning service
Ranging_SL capability | Ranging capability over NAS | 23.586 Clause 5.1&6.2 | 24.501 | OPPO, ZTE, Qualcomm Incorporated, Nokia, Nokia Shanghai Bell, Ericsson | CT1#141 | C1-232640 | agreed | CR 5225 revised to CP-231304 (CT Meeting #100)
| Service request for ranging |  | 24.501 | OPPO | CT1#141 | C1-232750 | agreed | CR 5226
| Capability of SL Positioning Server UE over PC5 |  | 24.501 | vivo | CT1#142 | C1-234001 | agreed | CR 5437
| Correction to ranging and sidelink positioning capability |  | 24.501 | Nokia, Nokia Shanghai Bell | CT1#144 | C1-237339 | agreed
| Clarification on service request for ranging |  | 24.501 | ZTE | CT1#144 | C1-238145 | agreed
| Network capability to UE |  | 24.501 | OPPO | CT1#145 | C1-239447 | agreed
| Update UE ranging and sidelink positioning capability per role | S2-2401381 | 24.501 | Xiaomi | CT1#147 | 1 | expected | SA2 contributor: vivo
Provisioning of configuration information for Ranging/SL | UE requested policy provisioning procedure for ranging | 23.586 Clause 5.1&6.2 | 24.514 | OPPO | CT1#141 | C1-232639 | agreed | Clause
| Extending “Requested UE policies IE” with an indicator for Ranging/SL Positioning policies |  | 24.587 | Nokia, Nokia Shanghai Bell, OPPO, xiaomi, Ericsson | CT1#141 | C1-232722 | agreed | CR 0269
| Transmission of Ranging/SL Positioning Policy |  | 24.501 | Nokia, Nokia Shanghai Bell, Ericsson | CT1#141 | C1-232723 | agreed | CR 5197
| Specifying and adding reference for Ranging/SL Positioning Policy |  | 24.526 | Nokia, Nokia Shanghai Bell, Ericsson | CT1#141 | C1-232724 | agreed | CR 0181
| RSLPP parameters |  | 24.514 | OPPO | CT1#142 | C1-234000 | agreed
| update RSLPP |  | 24.514 | OPPO | CT1#143 | C1-236094 | agreed
| RSLPP encoding |  | 24.514 | OPPO | CT1#143 | C1-236095 | agreed
| Correction on RSLPP request timer |  |  | OPPO | CT1#144 | C1-238142 | agreed
| Pseudo-CR on clarification of the roles of the UE for RSPP |  | 24.514 | QUALCOMM JAPAN LLC. | CT1#144 | C1-238141 | agreed
| Pseudo-CR on editorial correction in UE-requested RSLPP provisioning procedure initiation |  | 24.514 | Nokia, Nokia Shanghai Bell | CT1#145 | C1-238572 | agreed
| Policy request indicator for Ranging/SL Positioning policies |  | 24.587 | Nokia, Nokia Shanghai Bell | CT1#145 | C1-238573 | agreed
| Pseudo-CR on aligning the UE-requested RSLPP provisioning procedure to the single RSLPP request indicator “RSPI” |  | 24.514 | Nokia, Nokia Shanghai Bell | CT1#145 | C1-238574 | agreed
| Adding SLPKMF address information as part of configuration parameters for ranging and sidelink positioning |  | 24.514 | xiaomi | CT1#145 | C1-239457 | agreed
| Add Priority level and Delay Budget for Ranging/SL Positioning QoS | S2-2313462 | 24.514 | xiaomi | CT1#147 | 1 | expected | SA2 contributor: Huawei
| Remove Target UE and Reference UE authorization | S2-2401382 | 24.514 | xiaomi | CT1#147 | 1 | expected | SA2 contributor: Huawei
| User Info ID for Ranging/SL Positioning UE discovery in UE policy | S2-2401390 | 24.514 | Xiaomi/Interdigital | CT1#147 | 1 | expected | SA2 contributor: Interdigital, OPPO
C | Ranging/Sidelink Positioning UE discovery
| General description for 5G ProSe capable UEs discovery over PC5 interface | 23.586 Clause 5.2&6.4.2.1 | 24.514 | xiaomi | CT1#142 | C1-234207 | agreed | Tdoc agreed with EN to be solved, depending on the outcome from RAN2/SA2/SA3
| Ranging/SL Positioning UE discovery in Model A with 5G ProSe capable Ues | 23.586 Clause 5.2&6.4.2.1 | 24.514 | xiaomi | CT1#142 | C1-234208 | agreed | Tdoc agreed with EN to be solved, depending on the outcome from RAN2/SA2/SA3
| Ranging/SL Positioning UE discovery in Model B with 5G ProSe capable Ues | 23.586 Clause 5.2&6.4.2.1 | 24.514 | xiaomi | CT1#143 | C1-236367 | agreed | Tdoc agreed with EN to be solved, depending on the outcome from RAN2/SA2/SA3
| Ranging/SL Positioning Group member discovery in Model A with 5G ProSe capable Ues | 23.586 Clause 5.2&6.4.2.2 | 24.514 | xiaomi | CT1#143 | C1-236101 | agreed | Tdoc agreed with EN to be solved, depending on the outcome from RAN2/SA2/SA3
| Ranging/SL Positioning Group member discovery in Model B with 5G ProSe capable Ues | 23.586 Clause 5.2&6.4.2.2 | 24.514 | xiaomi | CT1#143 | C1-236102 | agreed | Tdoc agreed with EN to be solved, depending on the outcome from RAN2/SA2/SA3
| Pseudo-CR on ProSe direct discovery PC5 message type for ranging_SL |  | 24.514 | Qualcomm Korea | CT1#145 | C1-238710 | agreed
| Pseudo-CR on clarification on Ranging and sidelink positioning UE discovery |  | 24.514 | Qualcomm Korea | CT1#145 | C1-239449 | agreed
| Solve security aspects' ENs in the discovery procedures |  | 24.514 | xiaomi | CT1#147 | 1 | expected
| Ranging/SL Positioning UE discoverywith V2X capable UE | 23.586 Clause 5.2&6.4.3 | 24.514 | xiaomi | CT1#142 | C1-234209 | agreed
| Ranging and sidelink positioning UE discovery | 23.586 Clause 5.2&6.4.2.1 | 24.514 | ZTE | CT1#143 | C1-235869 | agreed
| Adding the role(s) of the discovered UE | 23.586 Clause 5.2&6.4.2.1 | 24.587 | xiaomi | CT1#145 | C1-239450 | agreed
| Correction on IE coding format |  | 24.514 | vivo | CT1#144 | C1-237080 | agreed
| Located UE discovery and selection |  | 24.514 | xiaomi | CT1#145 | C1-239451 | agreed
| Sidellink positioning server UE discovery and selection |  | 24.514 | xiaomi | CT1#145 | C1-239452 | agreed
| Clarification on content type for ranging and sidelink positioning in discovery message |  | 24.554 | ZTE | CT1#146 | C1-240179 | agreed
| Pseudo-CR on correction for located UE discovery and selection |  | 24.514 | Nokia, Nokia Shanghai Bell | CT1#146 | C1-240322 | agreed
| General description on located UE discovery and selection |  | 24.514 | ZTE | CT1#146 | C1-240341 | agreed
| Update on Located UE discovery and selection | 23.586 Clause 5.2&23.273 Clause 6.20 | 24.514 | xiaomi | CT1#146 | C1-240369 | agreed
| Update on Sidelink positioning server UE discovery and selection | 23.586 Clause 5.2 | 24.514 | xiaomi | CT1#146 | C1-240370 | agreed
| Information elements coding for UE discovery procedures |  | 24.514 | xiaomi | CT1#146 | C1-240371 | agreed
| SL Reference UE Selection | S2-2401386 | 24.514 | xiaomi/InterDigital | CT1#147 | 1 | expected | SA2 contributor: InterDigital
| Clarify including serving PLMN ID for Located UE during UE discovery | S2-2401395 | 24.514 | vivo | CT1#147 | 1 | expected | SA2 contributor: vivo
D | Ranging/Sidelink Positioning communication
Ranging and sidelink positioning direct communication over PC5 | General for Ranging and sidelink positioning direct communication over PC5 |  | 24.514 | QUALCOMM | CT1#142 | C1-232783 | agreed | clause 7.2.1
| 5G ProSe communication for ranging and sidelink positioning | the ProSe PC5 link establishment and maintainance, which is common to all the stage 2 procedures for Ranging/Sidelink Positioning communication over PC5 | 24.514 | xiaomi | CT1#142 | C1-234011 | agreed | The general part and referring part in 24.514
| Security aspects to support ranging and sidelink positioning in 5G ProSe direct link establishment procedure |  | 24.554 | xiaomi | CT1#145 | C1-239459 | agreed | Update for procedure description and messages in 24.554 is missing and expected.
| Update Security aspects to support ranging and sidelink positioning in 5G ProSe DCR procedure |  | 24.554 | xiaomi | CT1#147 | 1 | expected | description and messages in 24.554
| V2X communication for ranging and sidelink positioning | The V2X PC5 link establishment and maintainance, which is common to all the stage 2 procedures for Ranging/Sidelink Positioning communication over PC5 | 24.514 | xiaomi | CT1#142 | C1-234209 | agreed | The general part and referring part in 24.514 is agreed.
| Message udpate for V2X direct link establishment procedure for ranging and sidelink positioning |  | 24.587 | xiaomi | CT1#142 | C1-234007 | agreed | Messge in 24.587 for establishment is agreed.Update for procedure description and messages other than that for establishment is missing and expected.
| Adding SLPP in V2X message family encoding |  | 24.587 | Qualcomm Incorporated | CT1#144 | C1-237305 | agreed
| Pseudo-CR on V2X non-IP PDU handling for RSPP |  | 24.514 | Qualcomm Incorporated | CT1#144 | C1-238143 | agreed
| Pseudo-CR on V2X support for supplementary RSPP signaling |  | 24.514 | Qualcomm Incorporated | CT1#146 | C1-240104 | agreed
| Adding new V2X message family encoding for supplementary RSPP signaling |  | 24.587 | Qualcomm Incorporated, Ericsson | CT1#146 | C1-240368 | agreed
Ranging and sidelink positioning procedure on LCS aspect | Pseudo-CR on general description for ranging and sidelink positioning communication on LCS aspect | 23.586 Clause 5.5&6.5 23.273 Clause 6.20 | 24.514 | vivo/xiaomi | CT1#143 | C1-236348 | agreed
| Additional of the SL-MO-LR procedure |  | 24.571 | vivo | CT1#144 | C1-238139 | agreed
| Pseudo-CR on clarifying the ranging communication over LCS |  | 24.571 | vivo | CT1#145 | C1-239453 | agreed
| NAS transport for RSPP |  | 24.571 | InterDigital, Ericsson, vivo | CT1#145 | C1-239454 | agreed
| SLPP introduction |  | 24.571 | Ericsson, InterDigital, vivo | CT1#145 | C1-239455 | agreed
| SLPP transport |  | 24.501 | Ericsson, InterDigital | CT1#145 | C1-238967 | agreed
| Correction to NAS signalling transport for downlink SLPP messages |  | 24.571 | ZTE | CT1#146 | C1-240177 | agreed
| SL-MO-LR response in case of network congestion |  | 24.571 | Nokia, Nokia Shanghai Bell | CT1#146 | C1-240321 | agreed
| Clarification on location information |  | 24.514 | ZTE | CT1#146 | C1-240342 | agreed
| Mobile Terminated Location Request for Ranging_SL |  | 24.571 | Xiaomi, Ericsson | CT1#146 | C1-240375 | agreed | Latest clause 6.20 of 23.273 based on S2-2313706&S2-2313707&S2-2313892 agreed in SA2. (SA2 contributors: Ericsson; OPPO, vivo; Huawei, HiSilicon, Sony, CATT) C1-236099 postponed from CT1#143 because of the following EN in clause 6.20.3 of 23.273 Editor's note: Whether supplementary services message or lpp will be sent from LMF to UE is FFS and needs the coordination with RAN WGs.
| Pseudo-CR on removing EN for SL-MT-LR |  | 24.514 | vivo | CT1#146 | C1-240400 | agreed
| DL Supplementary service message between LMF and UE for Ranging_SL |  | 24.571 | xiaomi | CT1#147 | 1 | expected | Latest clause 6.20 of 23.273 based on S2-2313708&S2-2313891 agreed in SA2. (SA2 contributors: ZTE; Sony, Philips, Vivo, Interdigital, Ericsson, Huawei. CATT, OPPO)
| UL Supplementary service message between LMF and UE for Ranging_SL |  | 24.571 | xiaomi | CT1#147 | 1 | expected | Latest clause 6.20 of 23.273 based on S2-2313708&S2-2313891 agreed in SA2. (SA2 contributors: ZTE; Sony, Philips, Vivo, Interdigital, Ericsson, Huawei. CATT, OPPO)
| SL-MO-LR request supporting service exposure |  | 24.571 or 24.501/24.571 | Nokia? Nokia Shanghai Bell? Ericsson? xiaomi | CT1#147 | 1 | expected
Ranging and sidelink positioning control over PC5-U | Ranging and sidelink positioning control over PC5-U |  | 24.514 | xiaomi | CT1#145 | C1-239456 | agreed
| Pseudo-CR on introduction of supplementary RSPP signaling |  | 24.514 | Qualcomm Korea | CT1#146 | C1-240367 | agreed
| Update sidelink positioning service request procedure to support the target UE request location from SL server UE |  | 24.514 | xiaomi | CT1#147 | 1 | expected | Including the case for rangingsl involving LMF and the case for UE-only. step 17 of 6.20.1 in TS 23.273 (CR 0416 of TS 23.273) The related contributor in SA2 include but not limited to Ericsson, OPPO, vivo, Huawei, CATT, ZTE, Sony, Philips, Interdigital, MediaTek Inc, Xiaomi.
| Message functional definition and contents for sidelink positioning service request procedure |  | 24.514 | xiaomi | CT1#147 | 1 | expected
| Solve ENs in Sidelink positioning SLPP transport procedure |  | 24.514 | Qualcomm Korea | CT1#147 | 1 | expected
E | Security for ranging and sidelink positioning
General Description | General for Security for ranging and sidelink positioning |  | 24.514 | xiaomi | CT1#144 | C1-238215 | agreed
Security for ranging and sidelink positioning UE discovery | Security for ranging and sidelink positioning UE discovery with 5G ProSe capable UE |  | 24.514 | xiaomi | CT1#146 | C1-240372 | agreed
Security for ranging and sidelink positioning communication | Security for unicast direct communication over RSPP between the Ues |  | 24.514 | xiaomi | CT1#144 | C1-238148 | agreed
| SLP key request procedure |  | 24.514 | xiaomi | CT1#145 | C1-239458 | agreed
| Security aspects to support ranging and sidelink positioning in 5G ProSe direct link establishment procedure |  | 24.554 | xiaomi | CT1#145 | C1-239459 | agreed
| Message definition and information elements coding for 5G ProSe UE SLP key request procedure |  | 24.514 | xiaomi | CT1#146 | C1-240373 | agreed
| Message definition and information elements coding for SLP key request procedure |  | 24.514 | xiaomi | CT1#146 | C1-240374 | agreed
F | Others
| Handling of unknown, unforeseen, and erroneous PC5 signalling protocol data |  | 24.514 | xiaomi | CT1#144 | C1-238216 | agreed

## CT3 Topics
Topic number | Description | Stage-2 reference | TS | Contributor | Meeting# | tdoc# | status | Notes
A | PCF services/procedures
| Add RSLPP in call flows of Policy Control | 23.586 clause 5.1&6.2 &S2-2305280 | 29.513 | Xiaomi | CT3#129 | C3-233730 | agreed
| Update UE Policy Control Service for Ranging_SL |  | 29.525 | Xiaomi | CT3#130 | C3-234638 | agreed
| Removal of Editor’s Note related to the Npcf_UEPolicyControl support |  | 29.513 | Ericsson | CT3#131 | C3-235482 | agreed
B | NEF services
| Add ParmForRangingSl | 23.586 clause 5.1&6.2 &S2-2305280 | 29.522 | Xiaomi | CT3#129 | C3-233755 | agreed
| Location exposure for Ranging_SL | 23.586 clause 5.6&6.7.2 &S2-2305280 | 29.122 | Xiaomi | CT3#129 | C3-233733 | agreed
| Location exposure for Ranging_SL |  | 29.522 | Xiaomi | CT3#129 | CP-232177 | agreed
| Update Location exposure for Ranging_SL |  | 29.122 | Xiaomi | CT3#130 | C3-234637 | agreed
| Service for mapping between application layer ID and GPSI | S2-2309831 | 29.522/29.122/29.591 | Ericsson | CT3#133 |  | expected | S2-2309831 agreed in SA2#158 for Updating UDR, NEF, GMLC functionality in order to execute UE ID translation, however how and which service is used to implement the related functionality is not defined.
C | UDR services for policy data
| Add ParmForRangingSl | 23.586 clause 5.1&6.2 &S2-2305280 | 29.519 | Xiaomi | CT3#129 | C3-233731 | agreed
18.44 | CT aspects of Ranging based services and sidelink positioning [Ranging_SL] | [5 empty] | CP-230331 (CT1 leading)

## CT4 Topics
Topic number | Description | Stage-2 reference | TS | Contributor | Meeting# | tdoc# | status | Notes
A | Common
| Add Ranging Sidelink Positioning Subscription data | S2-2304508 | 29.571 | Huawei | CT4#116 | C4-232610 | agreed | With EN for assistant UE
| Update common data for Ranging Sidelink Positioning | 23.586 | 29.571 | Xiaomi | CT4#117 | C4-233881 | agreed
| Resolve Editor’s note |  | 29.571 | Huawei | CT4#118 | C4-234210 | agreed
B | UDM services
| Add Ranging Sidelink Positioning Subscription data | S2-2304508 | 29.503 | Huawei | CT4#116 | C4-232609 | agreed | With EN for QoS parameters
| Resolve Editor’s Note | 23.586 clause 5.7.2 | 29.503 | Huawei | CT4#117 | C4-233859 | agreed | PC5 QoS parameters related to RSPP transport over PC5
| Update to support SLPKMF |  | 29.503 | Xiaomi | CT4#118 | C4-234345 | agreed
| update information in the subscription data for exposure via CP | S2-2312306 | 29.503 | Xiaomi | CT4#121 |  | expected | 1
C | Subscription data
| Add Ranging Sidelink Positioning Subscription data | S2-2304508 | 29.504 | Huawei | CT4#116 | C4-232274 | agreed
| Add Ranging Sidelink Positioning Subscription data | S2-2304508 | 29.505 | Huawei | CT4#116 | C4-232510 | agreed
D | NRF services
| PCF selection considering the Ranging/SL Positioning Capability | 23.586 clause 5.1&6.2 | 29.510 | Xiaomi | CT4#117 | C4-233860 | agreed
| LMF selection considering ranging_SL support | S2-2305278 | 29.510 | Xiaomi | CT4#117 | C4-233723 | agreed
| Update to support SLPKMF |  | 29.510 | Xiaomi | CT4#118 | C4-234346 | agreed
| Correction of query parameter Ranging-Sl-Pos-Indication |  | 29.510 | Ericsson | CT4#119 | C4-235289 | agreed
E | GMLC services
| Update on Ngmlc_Location_ProvideLocation service for ranging_SL |  | 29.515 | Xiaomi, Ericsson |  | C4-235689 | agreed
| Add new service operation of Ngmlc_Location_PrivacyCheck_IDMapping | S2-2401387 & S2-2400203 | 29.515 | Ericsson | CT4#121 |  | expected
| Update on Ngmlc_Location service for alignment and UEs belonging to different PLMN(s) |  | 29.515 | Xiaomi | CT4#121 |  | expected
| Add new service operation of Ngmlc_Location_ProvideRanging | S2-2401394 | 29.515/29.572 | Xiaomi | CT4#121 |  | expected
| Coordinate ID in case of absolute locations | S2-2313892 | 29.515 | Xiaomi | CT4#121 |  | expected
F | LMF services
| Update on LMF service for MT procedures for ranging_SL | 23.586 Clause 5.5&6.5 | 29.572 | Xiaomi | CT4#117 | CP-232178 | agreed
| Update on LMF service for ranging_SL |  | 29.572 | Xiaomi, Ericsson | CT4#119 | C4-235688 | agreed
| Update Nlmf_Location_DetermineLocation service to include Ranging/Sidelink Positioning Capability | S2-2401394 | 29.572 | Huawei | CT4#121 |  | expected
| Coordinate ID in case of absolute locations | S2-2313892 | 29.572 | Xiaomi | CT4#121 |  | expected
G | AMF services
| Update on AMF service for MT procedures for ranging_SL | 23.586 Clause 5.5&6.5 | 29.518 | Xiaomi | CT4#117 | C4-233861 | agreed | Including: - Namf_Location_ProvidePositioningInfo (SL-MT) - Namf_Communication_N1N2MessageTransfer((Periodic-Triggered)SL-MT-LR, Event Report Ack) - Namf_Communication_N1MessageNotify((Periodic-Triggered)SL-MT-LR response, Event Report)
| Update on AMF services for ranging_SL |  | 29.518 | Xiaomi, Ericsson | CT4#119 | C4-235483 | agreed
| PC5 QoS parameters related to RSPP transport over PC5 | 23.586 clause 6.3.7 | 29.518 | Huawei | CT4#117 | C4-233866 | agreed
| Update on delivery of N2 information for rangingsl |  | 29.518 | Xiaomi | CT4#119 | C4-235490 | agreed
| Coordinate ID in case of absolute locations | S2-2313892 | 29.518 | Xiaomi | CT4#121 |  | expected
H | SLPKMF services
| Skeleton with General parts for the specification for SLPKMF services |  | 29.586 | Xiaomi | CT4#119 | C4-235487 | agreed
| 3GPP TS 29.586 on 5G System; SideLink Positioning Key Management Services; Stage 3 v0.1.0 |  | 29.586 | Xiaomi | CT4#119 | C4-235663 | agreed
| Nslpkmf_Discovery service |  | 29.586 | Xiaomi | CT4#119 | C4-235690 | agreed
| Nslpkmf_SLPKMFKeyRequest service |  | 29.586 | Xiaomi | CT4#119 | C4-235691 | agreed
| Editorial update for the specification for SLPKMF services |  | 29.586 | Xiaomi | CT4#121 |  | expected
I | Supplementary messages
| Addition of the LCS-SLMOLR |  | 24.080 | vivo | CT4#119 | C4-235607 | agreed
| Addition of the supplementary message for ranging_SL |  | 24.080 | Xiaomi | CT4#121 |  | expected | 1
6.2.20 CT aspects of Ranging based services and sidelink positioning [Ranging_SL]

## others
Incoming liaision statements (LS)
Tdoc # | Topic | Reply LS | Related tdocs: CT1 meeting #; tdoc(s) # | Open issues | Comments
S2-2311767 | Reply LS on procedures for UE discovery for Ranging_SL | NA | reply to C1-236527
S2-2311896 | Reply LS to Reply LS to SA2 on assistance information provided to UE
S3-235078 | Reply LS on security aspects for Ranging/Sidelink Positioning | NA | reply to C1-237928
S2-2313889 | LS to RAN WG2/CT WGs on RAN&CT alignment issues | NA
Outgoing liaision statements (LS)
Tdoc # | Topic | Reply LS | Related tdocs: CT1 meeting #; tdoc(s) # | Open issues | Comments
C1-236527 | LS on procedures for UE discovery for Ranging_SL | S2-2311767 | CT1#143 |  | Send to SA2 Clarification on how to applying the "discovery type" to support UE discovery for ranging_SL
C1-237928 | LS on key and security materials used for Ranging_SL |  | 33.503 approved in SA#101 in September, 2023.
C1-240431 | LS on UE selection for Ranging_SL |  |  |  | Send to SA2 Clarification on the criteria used for Located UE selection and SL server UE selection
General
Latest WID: | CP-230331
Completion Status: | CT#99:0%

## Annex A
CRs agreed in SA2
No | TDoc | Meting# | Title | Source | Spec | Version | Summary | Stage3 Impact | note
| S2-2401383 | SA2#160AH | LS on coverage condition during Ranging/Sidelink Positioning UE Discovery & Selection | SA WG2 |  |  | To RAN WG2 Clarify the Ran impact for some of the SL reference UE(s) are out of coverage for LMF involved case and some of the SL reference UE(s) are in coverage for UE only case. |  | stage 3 impact after stage 2 is clear Whether UE only or LMF involved is determined by whether target UE is in coverage or not?
| S2-2401651 | SA2#160AH | Reply LS on security aspects for Ranging/Sidelink Positioning | SA WG2 |  |  | To SA WG3 - not include user info of the Client UE within the SL-MO-LR for exposure via PC5(network based) - supplementary RSPP message(s) can be sent with the required user info of the Client UE
| S2-2400120 | SA2#160AH | LCS UE Privacy profile updated with a list of allowed UE(s) | Sony | 23.273 | 18.4.0 | Adding SL Positioning Client UE in LCS privacy profile to suppor service exposure via control plane. | CT4: 29.503 to update the subscription data for LcsPrivacyData Suggest to wait the outcome of SA3 Feb meeting as there were concerns raised during the discussion in SA2 Jan meeting.
| S2-2401379 | SA2#160AH | Corrections of usage of SLPP and supplementary service messages for Ranging_SL procedures | Qualcomm Incorporated, vivo, Xiaomi | 23.273 | 18.4.0 | Clarifications on usage of SLPP and supplementary service messages | Clarifications, no new stage 3 updates required comparing with the previous version (CT1: 24.571: - SLPP delivery for other Ues - RSPP supplementary serive message between UE and LMF to support SL-MT-LR procedure 24.514: SLPP forwarded/sent by UE1 to other Ues or LMF)
| S2-2401380 | SA2#160AH | Corrections to SL-MT-LR procedure | Philips International B.V. | 23.273 | 18.4.0 | Corrections to SL-MT-LR to support absolute location with adding located UE(s) in the request | Clarifications, no new stage 3 updates required comparing with the previous version
| S2-2401387 | SA2#160AH | Handling ID Translation and privacy check in case of UEs belong to different PLMNs | Ericsson | 23.273 | 18.4.0 | To support the case that UEs belonging to different PLMN(s) than the one of the GMLC: -Adding new Ngmlc_Location_PrivacyCheck_IDMapping service operation for SL-MT-LR - (V)GMLC triggers 5GC-MT-LR procedure to the home GMLC of each of these roaming Located UE(s) to acquire the absolute location of the UE(s) | CT4: 29.515: add the new service operation and update the consumer for ProvideLocation
| S2-2401388 | SA2#160AH | Update about the usage of SUPI in SL-MT-LR | OPPO | 23.273 | 18.4.0 | Clarification on SUPI-GPSI, and GPSI->application layer ID mapping. | Clarifications, no new stage 3 updates required comparing with the previous version
| S2-2401393 | SA2#160AH | Corrections for alignments to TS 23.273/TS 23.586/SA3/RAN WGs | Xiaomi | 23.273 | 18.4.0 | Clarification on the SL-MO-LR mainly "UE based calculation"->"Network-assisted SL Positioning" | Clarifications, no new stage 3 updates required comparing with the previous version
| S2-2401394 | SA2#160AH | Update on GMLC and LMF Services | Huawei, HiSilicon | 23.273 | 18.4.0 | Add Ngmlc_Location_ProvideRanging service operation Update Ngmlc_Location_ProvideLocation service operation and Nlmf_Location_DetermineLocation service operation | CT4: 29.515: add the new service operation and update the consumer for ProvideLocation, and update Ngmlc_Location_ProvideLocation service operation 29.572: Nlmf_Location_DetermineLocation service operation update to include Ranging/Sidelink Positioning Capability(aligned with S2-2313893) | stage 2 clarifcation is needed. 1) 29.515: update Ngmlc_Location_ProvideLocation service operation, the service operation is not aligned with the procedure defined in 23.273 clause 6.20.3, as Ngmlc_Location_ProvideLocation service operation is also used to request relative location which is already covered in our stage 3 spec.
| S2-2400118 | SA2#160AH | Update parameter provisioning | Sony | 23.586 | 18.2.0 | Policy to UE - The PCF provisions one or more of the following Ranging/SL Positioning Policy/parameters: - Policy/parameters for Ranging/Sidelink Positioning UE Discovery & Selection as specified in clause 5.2. - Policy/parameters for Ranging/Sidelink Positioning UE Control as specified in clause 5.3. - Policy/parameters for Ranging/Sidelink Positioning service exposure as specified in clause 5.6. | Not clear what new information is added | stage 2 clarification is needed, nothing new
| S2-2400119 | SA2#160AH | Add missing Ranging/SL Positioning security description | Sony | 23.586 | 18.2.0 | General description for security aspect | Genral, no new stage 3 updates required comparing with the previous version, stage 3 security aspects follows SA3 spec(33.533)
| S2-2400201 | SA2#160AH | Correction/clarification to AF provisioning service parameters for Ranging/SL Positioning | Ericsson | 23.586 | 18.2.0 | Clarification on the mapping between Application Layer ID and GPSI provisioning from AF. | CT3 29.522? CT4 29.504? | stage 2 clarification may be needed Not sure how the data key and data block for parameters for Ranging/SL Positioning service is constructed in stage 2.
| S2-2400203 | SA2#160AH | Handling ID translation and privacy check in case of UEs belong to different PLMNs | Ericsson | 23.586 | 18.2.0 | related to S2-2401387 | Same as S2-2401387
| S2-2400491 | SA2#160AH | Clarification on the term and functionality | ZTE | 23.586 | 18.2.0 | NF functionalities update | General, no new stage 3 updates required comparing with the previous version
| S2-2400516 | SA2#160AH | Protocol stack for RSPP transport | CATT | 23.586 | 18.2.0 | Protocol stack for RSPP transport | General, no new stage 3 updates required comparing with the previous version
| S2-2400618 | SA2#160AH | Update on functional entity | Huawei, HiSilicon | 23.586 | 18.2.0 | NF functionalities update | General, no new stage 3 updates required comparing with the previous version
| S2-2401378 | SA2#160AH | Update service exposure via control plane. | Sony | 23.586 | 18.2.0 | Update on check SL Positioning Client UE authorization and privacy check | General, no new stage 3 updates required comparing with the previous version, stage 3 security aspects follows SA3 spec(33.533), and authorization check requires UDM update for inlcuding subscription for SL Positioning Client UE already covered in the previous version
| S2-2401381 | SA2#160AH | Ranging capability and subscription | vivo | 23.586 | 18.2.0 | 1. UE capability udapted to have 3 sub-items: - Ranging/SL Positioning operations over PC5 (i.e., for Target UE and SL Reference UE); - Located UE; - SL Positioning Server UE.; 2. Subscription udpate | CT1:24.501 UE capabilities update to have 3 itmes for rangingsl CT4: 29.503 update "6.1.6.2.98 Type: RangingSlPosPlmn" to include the allowed UE role.
| S2-2401382 | SA2#160AH | Update on Policy/Parameter and scheduled location time | Huawei, HiSilicon | 23.586 | 18.2.0 | Clarification Target UE and Reference UE are removed from the authorized Ranging/SL positioning role | CT1:24.514 UE policy update
| S2-2401384 | SA2#160AH | Update on Located UE Discovery and Selection | Huawei, HiSilicon | 23.586 | 18.2.0 | Clarification on UE discovery for announcing UE. And clarification on UE only procedure to add SL server UE request absolute location of located UE, and critieria for target UE selecting located UE. | New stage 3 updates required comparing with the previous version: CT1 24.514: Located UE selection considering "the absolute location of UE2/.../UEn" | Located UE selection considering "the absolute location of UE2/.../UEn" described UE only procedure in clause 6.8 of TS 23.586, but not covered in UE discovery procedure in clause 6.4 of TS 23.586, not clear whether needed or not.
| S2-2401385 | SA2#160AH | EN remove for the indication for capability exchange | vivo | 23.586 | 18.2.0 | Add indication of whether its serving network supports Ranging/SL Positioning included in the UE discovery procedure | CT1 24.514: Add indication of whether its serving network supports Ranging/SL Positioning included in the UE discovery procedure
| S2-2401386 | SA2#160AH | Update in the UE discovery and selection | InterDigital | 23.586 | 18.2.0 | Add SL Reference UE Discovery & Selection | CT1 24.514: Add SL Reference UE Selection
| S2-2401389 | SA2#160AH | Update about the usage of application layer ID | OPPO | 23.586 | 18.2.0 | Clarification on the usage of application layer ID | General, no new stage 3 updates required comparing with the previous version
| S2-2401390 | SA2#160AH | Update on Application layer ID resolution | Interdigital, OPPO | 23.586 | 18.2.0 | Clarification and "User Info ID for Ranging/SL Positioning UE discovery" added to Policy/Parameter provisioned to UE | CT1 24.514: Add "User Info ID for Ranging/SL Positioning UE discovery" in UE policy
| S2-2401391 | SA2#160AH | Modification to the Registration description | ZTE | 23.586 | 18.2.0 | Clarify the AMF may include Ranging/SL Positioning Support indicator in the Registration Accept | Clarification, no new stage 3 updates required comparing with the previous version
| S2-2401392 | SA2#160AH | Corrections for alignments to TS 23.273/TS 23.586/SA3/RAN WGs | Xiaomi | 23.586 | 18.2.0 | Alignment and clarification | Clarification, no new stage 3 updates required comparing with the previous version
| S2-2401395 | SA2#160AH | Updates to dicovery | vivo | 23.586 | 18.2.0 | Clarification on RSPP and including serving PLMN ID for Located UE | CT1 24.514: Clarify including serving PLMN ID for Located UE during UE discovery
| S2-2401396 | SA2#160AH | Updates SL positioning control using supplementary RSPP signalling message | InterDigital | 23.586 | 18.2.0 | Clarification on SL positioning control using supplementary RSPP signalling message | Clarification, no new stage 3 updates required comparing with the previous version
| S2-2401397 | SA2#160AH | Corrections for UE-only operation procedures | Qualcomm Incorporated | 23.586 | 18.2.0 | Clarification on UE only procedure | Clarification, no new stage 3 updates required comparing with the previous version
| S2-2400515 | SA2#160AH | Ranging/SL Positioning policy information | CATT | 23.503 | 18.4.0 | Add RSLPP | no new stage 3 updates required comparing with the previous version
| S2-2313889 | SA2#160 | LS to RAN WG2/CT WGs on RAN&CT alignment issues | SA WG2 |  |  | Agreements that SLPP defined by RAN only used for transferring capability, assistance data and Location estimate, all other information exchanged between UE and LMF, among UE are all developed by CT WGs as the LCS SS message or new Supplementary Service messages. | CT1: 24.571&24.514 implement RSPP supplementary serive messages between UE and LMF and among Ues based on lates SA2 specs.
| S2-2312306 | SA2#160 | Missing information in the subscription data for exposure via CP | Sony | 23.273 | 18.3.0 | the subscription data for exposure via CP | CT4: 29.503 to update the subscription data for LcsMoServiceClass | CT4
| S2-2313706 | SA2#160 | Adding SLPP to SL-MT-LR supplementary service response | Ericsson | 23.273 | 18.3.0 | SL-MT-LR request/response as supplementary service and SLPP of UE capabilities may be included in SL-MT-LR response | CT1: 24.571, to add procedure of SL-MT-LR request/response as LCS-SS with SLPP embedded in the response | CT1: SL-MT-LR | 1
| S2-2313707 | SA2#160 | Updates about the discovery and selection of Located UE | OPPO, vivo | 23.273 | 18.3.0 | Update 5GC-MO-LR Procedure using SL positioning, the using SL positioning part refer to step 10-16 of SL-MT-LR procedure | CT1: 24.571: SL-MT-LR request includes the indication of Target UE/LMF selecting Located UE, impacting UE behavior. | CT1: SL-MT-LR | 1
| S2-2313708 | SA2#160 | Resolving the SLPP message forwarding | ZTE | 23.273 | 18.3.0 | Add clarificaiton that in SL-MT-LR procedure the SLPP messages between UE 2 to n and LMF are forwarded by UE-1 in the SLPP container in the supplementary services message. | CT1: 24.571: - SLPP delivery for other Ues - RSPP supplementary serive message between UE and LMF to support SL-MT-LR procedure 24.514: SLPP forwarded/sent by UE1 to other Ues or LMF | CT1: SLPP between LMF and other Ues
| S2-2313891 | SA2#160 | SL-MO-LR for Ranging and Sidelink Positioning corrections | Sony, Philips, Vivo, Interdigital, Ericsson, Huawei. CATT, OPPO | 23.273 | 18.3.0 | Mainly clarify that in SL-MO-LR procedure the SLPP messages between UE 2 to n and LMF are forwarded by UE-1 in the SLPP container in the supplementary services message, and the application layer information, e.g. the application layer IDs of UE2 to n . | CT1: 24.571: - SLPP delivery for other Ues - RSPP supplementary serive message bwteen UE and LMF to support SL-MO-LR procedure 24.514: SLPP forwarded/sent by UE1 to other Ues or LMF | CT1: SLPP between LMF and other Ues
| S2-2313892 | SA2#160 | Solution update for ranging procedure | Huawei, HiSilicon, Sony, CATT | 23.273 | 18.3.0 | Clarification on 5GC-MT-LR Procedure using SL positioning and SL-MT-LR procedure mainly about: -GMLC behavior clarification -Coordinate ID included for obtaining absolute location -failure cause included in the provided result | CT1:24.571: - Coordinate ID included in SL-MT-LR request CT4: 29.518&29.515&29.572 -Coordinate ID included for obtaining absolute location -failure cause included in the provided result | CT1: SL-MT-LR (adding Coordinate ID) CT4: adding Coordinate ID | 1
| S2-2313893 | SA2#160 | UE Capability Update for SL-MT-LR and SL-MO-LR | Nokia, Nokia Shanghai Bell | 23.273 | 18.3.0 | UE capabilities stored in AMF/sent to LMF in location req/received from LMFin location resp | CT4: 29.518 -UE capabilities for rangingsl sent to LMF in location req/received from LMF in location resp | CT4
| S2-2313462 | SA2#160 | Update on Ranging/SL Positioning QoS | Huawei, HiSilicon | 23.586 | 18.1.0 | Add Priority level and Delay Budget for Ranging/SL Positioning QoS | CT1:24.514 - Update QoS part of UE policy | CT1: UE policy
| S2-2313464 | SA2#160 | Update Network Reject Use Case for UE only operation | Ericsson | 23.586 | 18.1.0 | Update trigger of UE only(Response to SL-MO-LR allows the UE only operation for a period of time by the network due to congestion.) | CT1 24.571 & CT4 24.080: - new cause included Response to SL-MO-LR | CT1: cause in Response to SL-MO-LR
| S2-2313711 | SA2#160 | Clarification on SL positioning service exposure through PC5 | Interdigital | 23.586 | 18.1.0 | Clarification on general descirption on Clarification on SL positioning service exposure through PC5SL positioning service exposure through PC5 | NA, related stage 3 udpate can align with the related procedure
| S2-2313712 | SA2#160 | Correction to service exposure to SL Positioning Client UE for absolute position. | Philips International B.V. | 23.586 | 18.1.0 | General editorial udpate | NA
| S2-2313713 | SA2#160 | SL positioning operation with proximity indication | Interdigital | 23.586 | 18.1.0 | Update Service exposure to SL Positioning Client UE via PC5 procedure that SL Positioning Service Request is responded with reject when UE1/UE2 are not in proximity, and information update for the req/resp | CT1 24.514: covered in procedure for interaction between Client UE and UE1/UE2 | CT1: interaction between Client UE and UE1/UE2 | 1
| S2-2313716 | SA2#160 | Update exposure via PC5 and add missing information in the subscription data | Sony | 23.586 | 18.1.0 | UE privacy clarification for Ranging/SL Positioning service exposure through PC5 Subscription for UE acting as SL Positioning Client UE. | CT1 24.514: removed EN about client UE For UE privacy part, align with SA3 | CT1: client UE EN
| S2-2313770 | SA2#160 | Correction on authorization for Ranging and Sidelink Positioning | Qualcomm Incorporated, CATT, ZTE, Huawei, HiSilicon | 23.586 | 18.1.0 | Mainly include: 1) Remove per UE role for Authorisation and policy/parameter provisioning to NG-RAN 2) remove subscription for UE acting as Target UE and SL reference UE | !) related to RAN3 2) may need further check as the UE suscription is also used to provide the authorization/parameters to UE, the information of acting as Target UE and SL reference UE are needed. | CT1: TBD
| S2-2313772 | SA2#160 | Updates to the UE-only operation using Located UE | Vivo | 23.586 | 18.1.0 | Update on UE-only operations, mainly clarify: - location req/resp interaction between target UE and server UE - cappabilies exchange/assistance data transfer/location measurement data transfer between UE1 and server UE, and between UE2 to n and server UE | CT1 24.514: covered in procedure for interaction between server UE and UE1 and between UE1 and UE 2 to n | CT1: SLPP between server UE and other Ues | 1
| S2-2313890 | SA2#160 | Updates to the UE-only operation procedure | Vivo, Interdigital, MediaTek Inc, Xiaomi. | 23.586 | 18.1.0 |  |  |  | 1
| S2-2310491 | SA2#159 | Ranging and Sidelink Positioning feature corrections | Sony | 23.273 | 18.3.0 | general update | NA
| S2-2310494 | SA2#159 | SL-MT-LR for periodic, triggered Location Events corrections | Sony, OPPO | 23.273 | 18.3.0 | term alignment | NA
| S2-2311465 | SA2#159 | SL-MO-LR for Ranging and Sidelink Positioning corrections | Sony, Philips, Vivo, Interdigital, Ericsson, Huawei | 23.273 | 18.3.0 | Update SL-MO-LR procedure with alignment and apply 5GC-MT-LR procedure first to obtain absolute location of Located Ues | CT1 24.571: infromation about UE2 to n included in the exchange message between target and LMF, implement stage 3 based on the lasted version
| S2-2311476 | SA2#159 | Updates about the discovery and selection of Located UE | OPPO | 23.273 | 18.3.0 | Update to have located Ues discovered before performing steps of SL-MO-LR using SL positioning | NA as the update is not included in the latest version
| S2-2311478 | SA2#159 | Update on 5GC-MT-LR Procedure using SL positioning | Huawei, HiSilicon | 23.273 | 18.3.0 | Clarification on Target UE or LMF selects Located UE | NA on the change on Target UE or LMF selects Located UE, for others, stage 3 implementation aligns with latest version of this procedure.
| S2-2311770 | SA2#159 | Updates to MO and MT LR for SL positioning | Vivo | 23.273 | 18.3.0 | Update procedures for 5GC-MO-LR Procedure using SL positioning & 5GC-MT-LR Procedure using SL positioning for steps before LMF triggering SL positioning: - AMF selects LMF considering the UE’s SL positioning capability - AMF provides the UE’s SL positioning capability to LMF | CT4: 29.518 -UE capabilities for rangingsl sent to LMF in location req(capabilities to support rangingsl or capabilities of the detailed supporting positioining method for rangingsl?) | CT4
| S2-2311877 | SA2#159 | Solution update for ranging procedure | Huawei, HiSilicon | 23.273 | 18.3.0 | Updated in S2-2313892 | Refer to S2-2313892
| S2-2311664 | SA2#159 | Corrections to TS 23.586 | Philips International B.V. | 23.586 | 18.1.0 | Alignements and editorials | NA and related stage 3 implementation aligns the latest version
| S2-2311766 | SA2#159 | Update Selection Criteria based on RAN agreement | Nokia, Nokia Shanghai Bell | 23.586 | 18.1.0 | Server UE/Located UE selection considering UE’s information including whether UE is in coverage or not, UE’s location | CT1(24.514): UE discovery and selection procedure. However further clarification for how to deliver related information should be described first in stage 2
| S2-2311767 | SA2#159 | Reply LS on procedures for UE discovery for Ranging_SL | SA WG2 |  |  | Using "content type" for discovery type | CT1(24.514/24.554): UE discovery messages "content type" only have 4 bits | OK
| S2-2311768 | SA2#159 | Clarification on the discovery type for ProSe capable UE | ZTE | 23.586 | 18.1.0
| S2-2311874 | SA2#159 | Updates to the UE-only operation procedure | Vivo | 23.586 | 18.1.0 | Further updated in S2-2313890 | Refer to S2-2313890
| S2-2311876 | SA2#159 | SL Positioning for UE without NAS connection | Xiaomi | 23.586 | 18.1.0 | Clarifies that In this Release, for Network based SL Positioning and Network-assisted SL Positioning, positioning of a Target UE having no NAS signalling connection is not supported. | partial coverage or without NAS connection case of Network-assisted SL Positioning is not implemented
| S2-2311878 | SA2#159 | Update on Procedures of Ranging/Sidelink Positioning control | Huawei, HiSilicon | 23.586 | 18.1.0 | Clarification of QoS used for located Ues in the 5GC-MO-LR Request | NA
| S2-2311896 | SA2#159 | Reply LS to Reply LS to SA2 on assistance information provided to UE | SA WG2 |  |  | Agreement 1 updated in S2-2313889 Agreement 2, The SL Positioning Service Request / SL Positioning Service Response messages are transmitted over SR5 as the non-SLPP messages to be developed by SA2 and CT WGs. | For agreement 1, refer to S2-2313889 and the latest spec of SA2 For agreement 2, CT1(24.514): Add descriptions for SL Positioning Service Req/Resp between Target UE/SL Reference UE and the SL Client UE for Ranging/SL Positioning service exposure
| S2-2311905 | SA2#159 | Updates to the network assisted SL positioning | Vivo | 23.586 | 18.1.0 | Clarifications on general description for the network assisted SL positioning | NA, related stage 3 udpate can align with the related latest procedures
| S2-2309281 | SA2#158 | Remove Editor s Note on feasiblity of the Relative Velocity with Uncertainty shape | Qualcomm Incorporated | 23.032 | 18.0.0 | Remove the editor's note on the Relative Velocity with Uncertainty shape in clause 8.4a. | NA
| S2-2309832 | SA2#158 | Cleanup about the usage of GPSI | OPPO | 23.273 | 18.2.0 | Update clause 6.20.3 to support the GPSI only scenario. | (H)GMLC queries the NEF for the mapping Application Layer ID from the only GPSI. | CT4: NEF service TBD rely on SA2
| S2-2307514 | SA2#157 | Support of MT-LR for Ranging and Sidelink Positioning | Qualcomm Incorporated, Huawei, HiSilicon, Xiaomi | 23.273 | 18.1.0 | Add MT Ranging/Sidelink Positioning procedures | 1) LCS service request/response to/from the 5GC for Ranging/Sidelink Positioning location results for the n UEs from AF/Client UE - CT1(24.571/ 24.501)/ CT4(29.572/24.080/29.518) 2) UE descovery -CT1 (24.514/ 24.571) 3) Ranging and sidelink positioning communication over PC5/ CT1(24.514)
| S2-2307552 | SA2#157 | Ranging and Sidelink Positioning MO-LR procedure | Qualcomm Incorporated, Xiaomi, Sony, vivo, Interdigital, Huawei, HiSilicon, Philips International B.V. | 23.273 | 18.1.0 | Add MO Ranging/Sidelink Positioning procedures | 1)Provisioning of configuration information for Ranging/SL positioning service -CT1 (24.514/ 24.587/ 24.526) -CT3 ((29.522/29.525/29.519)) 2) UE discovery -CT1 (24.514/ 24.571) 3) Ranging and sidelink positioning procedure - over PC5/ CT1(24.514) - between UE/AMF/LMF CT1(24.571/ 24.501)/ CT4(29.572/24.080/29.518)
| S2-2304508 | SA2#156e | Ranging Sidelink Positioning Subscription data | Huawei, HiSilicon | 23.502 | 18.1.1 | Add Ranging Sidelink Positioning Subscription data stored in UDR | CT4 (29.503/29.504/29.505)
| S2-2305278 | SA2#156e | Updates to LMF selection to support Ranging/Sidelink Positioning | Xiaomi | 23.273 | 18.1.0 | LMF selection considering ranging_SL support | CT4 29.510
| S2-2305280 | SA2#156e | Updates to support Ranging/Sidelink Positioning | Xiaomi | 23.503 | 18.1.0 | Provisioning of configuration information for Ranging/SL positioning service | CT3 (29.122/29.522/29.525/29.519)
| S2-2305340 | SA2#156e | TS23.501 Support of SL Positioning | Intel | 23.501 | 18.1.0 | General feature support | NA
| S2-2305748 | SA2#156e | Support of MT-LR for Ranging and Sidelink Positioning | Qualcomm Incorporated | 23.273 | 18.1.0 | SL_MT_LR procedure | 1) LCS service request/response to/from the 5GC for Ranging/Sidelink Positioning location results for the n UEs from AF/Client UE -CT4 ((29.515/29.518/29.572)) 2) UE descovery -CT1 (24.514/ 24.571) 3) Ranging and sidelink positioning communication - over PC5/ CT1(24.514) - between UE and LMF. CT1(24.571/ 24.501)/ CT4(29.572)
| S2-2305749 | SA2#156e | Ranging and Sidelink Positioning MO-LR procedure | Qualcomm Incorporated | 23.273 | 18.1.0 | SL_MO_LR procedure | 1)Provisioning of configuration information for Ranging/SL positioning service -CT1 (24.514/ 24.587/ 24.526) -CT3((29.522/29.525/29.519)) 2) UE discovery -CT1 (24.514/ 24.571) 3) Ranging and sidelink positioning communication - over PC5/ CT1(24.514) - between UE and LMF. CT1(24.571/ 24.501)/ CT4(29.572)
| S2-2305751 | SA2#156e | New GAD Shapes for Ranging and Sidelink Positioning Location Results | Qualcomm Incorporated | 23.032 | 17.2.0 | New GAD Shapes definition for ranging_SL | NA
| S2-2303193 | SA2#155 | Support of Ranging and Sidelink Positioning | Qualcomm Incorporated | 23.273 | 18.0.0 | General feature support | NA
| S2-2303258 | SA2#155 | Introduce Sidelink positioning procedure into LCS architecture | Ericsson | 23.273 | 18.0.0 | Architecture update | NA
TS 23.586 with responsible group of SA2
No | Stage 2 Clause# | Stage 3 Impact
|  | Responsible group | Impacted Spec | Status | Impacted items |  |  | Notes
A | Provisioning of configuration information for Ranging/SL positioning service
| Clause 5.1&6.2 | CT1 | 24.501/24.514, 24.587/24.526 | done | UE capability and UE policy
|  | CT3 | 29.513//29.525/29.519 | done | 1) updates to the NEF northbound interface (i.e. Nnef_ServiceParameter API) to support the provisioning of Ranging/SideLink Positioning service parameters by an AF; 2) updates to the UDR to support the provisioning and storage of Ranging/SideLink Positioning service parameters 3) updates to the PCF to support service authorisation policy and parameters provisioning in Ranging based services and sidelink positioning;
|  | CT4 | 29.510 | done | PCF selection
B | Ranging/Sidelink Positioning UE discovery
| Clause 5.2&6.4.2.1 | CT1 | 24.514/24.554 | partially done | General procedure for 1) Ranging/SL Positioning UE discovery in Model A with 5G ProSe capable UEs 2) Ranging/SL Positioning UE discovery in Model B with 5G ProSe capable Ues |  |  | Tdoc agreed with EN to be solved depending on RAN2 and SA3 aspects
|  | CT1 | 24.514/24.554/24.571 | expected when SA2 is clear | 3) UE-LMF interaction for Located UE Discovery 4) UE-LMF interaction for SL Positioning Server UE
| Clause 5.2&6.4.2.2 | CT1 | 24.514/24.554 | partially done | Ranging/SL Positioning Group member discovery 1) Model A with 5G ProSe capable UEs 2) Model B with 5G ProSe capable Ues |  |  | Tdoc agreed with EN to be solved depending on RAN2 and SA3 aspects
| Clause 5.2&6.4.3 | CT1 | 24.514/24.587 | done | Ranging/SL Positioning UE discoverywith V2X capable UE
C | Ranging/Sidelink Positioning communication
| Clause 5.5&6.5 | CT1 | 24.514/24.501/24.571 | expected | Network/UE based SL Positioning for UE with/without NAS connection using MO/MT location procedure - between UE and LMF. CT1(24.571/ 24.501) |  |  | CT1 impacts include the following parts: - UE discovery (refer to UE discovery part) - the PC5 link establishment and maintainance - SL positioning information request/response between target UE and Located UE in stage 2 is transported over PC5-U - SL positioning information request/response between Target UE/SL Reference UE and the SL Client UE in stage 2 is transported over PC5-U - SL positioning information request/response between Target UE/SL Reference UE and the server UE in stage 2 is transported over PC5-U - QoS flow management/data transmission/security/authentication
|  | CT4 | 29.515/29.518/29.572/29.510 | done | Network/UE based SL Positioning for UE with/without NAS connection using MO/MT location procedure - GMLC - LMF - AMF - NRF for LMF selection
| S2-2309831 | CT3 | 29.591 | expected | Application Layer ID translation to GPSI during the MO/MT or exposure procedure
| Clause 5.11&6.6 | CT1 | 24.514 | expected | refer to Clause 5.5&6.5 for the interaction over PC5 and between UE-LMF
| Clause 6.7.1.1 | CT1 | 24.514 | expected | the interaction over PC5
| Clause 6.7.1.2 | CT3 | 29.122/29.522 | done | Updates to the NEF northbound interface (i.e. Nnef_EventExposure API reusing the eLCS feature) to support the exposing of Ranging based services and sidelink positioning services to an AF.
| Clause 6.7.1.2 | CT1 | 24.514/24.501/24.571 | expected | In addtion to clause 5.5&6.5 interaction between SL Positioning Client UE and the AMF is needed
| Clause 6.8 | CT1 | 24.514 | expected
TS 33.503 with responsible group of SA3
No | Stage 2 Clause# | Stage 3 Impact
|  | Responsible group | Impacted Spec | Status | Impacted items |  |  | Notes
A | Security for Ranging/SL positioning UE discovery | [6 empty] | CT1: key&security materials used over PC5 - 24.514 key&security materials used for PC5 UE discovery procedures. - 24.554/24.587 key&security materials used for PC5 communication procedures. CT4: Support SLPKMF - 29.503 interact with UDM - 29.510 support SLPKMF - 29.586 support SLPKMF services
| clause 6.2 | CT1 | 24.514 | expected | key&security materials used for PC5 UE discovery procedures.
|  | CT4 | 29.503/29.510/29.586 | expected | SLPKMF services
B | Authorization for Ranging/SL positioning service
| clause 6.3 | refer to clause 6.2&6.4
C | Security for communication of Ranging/SL positioning control
| clause 6.4 | CT1 | 24.514 | expected | key&security materials used for PC5 communication procedures.
|  | CT4 | 29.503/29.510/29.586 | expected | SLPKMF services
Note on D2: Free text. Maximum length: 200 characters
Note on E2: Free text. Maximum length: 200 characters